## R1 - Summary
NS Power 2025 Capital Spend Detail - As per 2025 ACE Plan
1st Quarter Overview - as of March 31, 2025
| Generation | Distribution | Transmission | General Property | Total NS Power
2025 ACE Plan Total
2025 Submitted ACE Total | 188123238.18 | 182568886.69 | 256543819.14 | 65139528.19 | 692375472.2
Total YTD Spend* | 22752839.49 | 47996207.5 | 45032281.81 | 16701885.81 | 132483214.61
Variance YTD/ACE Spend | -165370398.69 | -134572679.19 | -211511537.33 | -48437642.38 | -559892257.59
Percentage of ACE Spent as of March 31, 2025 | 12.09% | 26.29% | 17.55% | 25.64% | 19.13%
Add:
ATOs | 1048240 | 0 | 3256426.96 |  | 4304666.96
U&Us/P&As | 3741135.82 | 0 |  |  | 3741135.82
Changes to ACE Items for Subsequent Approval** | -417402.05 |  | -21069355.21 | 1938332.31 | -19548424.95
Total Increase | 4371973.77 | 0 | -17812928.25 | 1938332.31 | -11502622.17
Less:
Projects cancelled | -2454007.23 | 0 | 0 | -725124.01 | -3179131.24
Projects deferred | -2385498.48 | 0 | -50000 | 0 | -2435498.48
Total Decrease | -4839505.71 | 0 | -50000 | -725124.01 | -5614629.72
2025 Potential Capital Spend*** | 187655706.24 | 182568886.69 | 238680890.89 | 66352736.49 | 675258220.31
*Total YTD Transmission spend includes ($11M) of proceeds received from WTI for the transfer of pre-2025 development costs transferred to Wasoqonatl Transmission Inc. (WTI) for CI C0044391 NS-NB Reliability Tie.
**The Changes to ACE Items for Subsequent Approval amount listed under Transmission includes the removal of C0044391 that was filed on April 10, 2025 by Wasoqonatl Transmission Inc.
*** Amounts do not reflect the reforecast of capital projects since the 2025 ACE Plan submission, or reforecasting of subsequent items filed.

## R2 - Capital Items Status
NS Power Capital Item Status Update
1st Quarter Overview - as of March 31, 2025
This report includes all projects submitted to the NSUARB and remain active, as well as ACE Plan subsequent submittal projects. Projects are removed from this report once the project has been final costed (internal or external), cancelled, or falls below $1M.
Status | Category | CI Number | Title | ACE Plan Reference (or U&U and P&A) | Submission/Date | ACE Amount | Submission or Approved Amount | Actual Spend | FIN Submission Date | FIN Amount | Variance
Deferred | Generation | 39472 | HYD - Mersey Redevelopment Phase 1 | 2022 ACE Plan (for Subsequent Approval) |  | 189447075.51 |  | 20978080.51
Less than $1M | General Plant | 47751 | ECC Dynamic Line Rating Implementation | 2022 ACE Plan (for Subsequent Approval) | OTQ - December 2, 2019 | 5144525.08 | 4978090.12 | 312467.69
Approved | Generation | 49634 | HYD - Trout River Diversion Structure Replacement | 2022 ACE Plan (for Subsequent Approval) | Q1 - May 13, 2024 | 1822299.7 | 3402776 | 3309527.65
Approved | Distribution | C0008638 | Cogswell HRM Redevelopment Program | 2022 ACE Plan (for Subsequent Approval) | OTQ - June 6, 2022 | 6982854.44 | 6617148.24 | 5351829.77
Deferred | Transmission | C0022247 | 1N-Onslow 138 kV Add Second 42 MVA Power Transformer | 2022 ACE Plan (for Subsequent Approval) |  | 4500000 |  | 1514067.3
Approved | Transmission | 43267 | 13V Gulch Hydro Replace 13V-GT1 and 13V-VR1 | 2015 ACE Plan | 2015 ACE Plan | 1061901.92 | 1061901.92 | 1011993.16
Approved | Transmission | 52314 | 1C-GT1/UT1 Replacement | 2018 ACE Plan | 2018 ACE Plan | 2032393 | 2032393 | 1678006.2
Approved | Transmission | 49815 | 2017 / 2018 Steel Tower Refurbishment | 2017 ACE Plan | 2017 ACE Plan | 2003316.81 | 2003316.81 | 1937432.56
Approved | Distribution | 49919 | 2017 PCB Pole Top Transformer Replacement | 2017 ACE Plan | 2017 ACE Plan | 2446051.2 | 2446051.2 | 2550603.38
Internally FIN'd | Transmission | 49818 | 2017/2018 Transmission Switch & Breaker Replacement | 2017 ACE Plan | 2017 ACE Plan | 1074471.9 | 1074471.9 | 1096990.7
Approved | Distribution | 51493 | 2018 PCB Pole Top Transformer Replacement | 2018 ACE Plan | 2018 ACE Plan | 1360354 | 1360354 | 1384292.41
Approved | Transmission | 51403 | 2018 PCB Removal Program | 2018 ACE Plan | 2018 ACE Plan | 4402342 | 4402342 | 3533544.92
Approved | Transmission | 52258 | 2018/2019 Isolated Structure Replacement | 2018 ACE Plan | 2018 ACE Plan | 4818521 | 4818521 | 294849.4
Approved | Transmission | 51398 | 2018/2019 Steel Tower Refurbishment | 2018 ACE Plan | 2018 ACE Plan | 1992692 | 1992692 | 2055520.97
Approved | Transmission | 51406 | 2018/2019 Transmission Switch & Breaker Replacement | 2018 ACE Plan | 2018 ACE Plan | 1405891 | 1405891 | 1136172.52 | Q4 - February 3, 2025 | 1136173 | -269718
Approved | Distribution | 47787 | 2H Armdale New Feeders | 2017 ACE Plan (for Subsequent Approval) | OTQ - April 6, 2020 | 1285679 | 1734221 | 1723920.45
Approved | Transmission | 52328 | 56N-T1 Transformer Upgrades | 2018 ACE Plan | 2018 ACE Plan | 1279271 | 1279271 | 1307910.2
Approved | Transmission | 51975 | 5P Mobile Substation Replacement | 2018 ACE Plan | 2018 ACE Plan | 4829458 | 4829458 | 2970054.49
Approved | Transmission | 51956 | 6P Mobile Substation Rewind U&U | U&U | Q3 2017 - October 30, 2017 | 0 | 1516120.57 | 1056955.81
Approved | Distribution | 47124 | Advanced Metering Infrastructure | 2017 ACE Plan (for Subsequent Approval) | OTQ - February 17, 2023 | 8274738 | 143495843.8622 | 142919875.14
Approved | Generation | 48914 | HYD - Malay Falls Facility Repair | 2017 ACE Plan (for Subsequent Approval) | Q3 2017 - October 30, 2017 | 446237 | 1034045 | 1101832
Approved | Generation | 47551 | HYD - SHH Controls Upgrade | 2016 ACE Plan (for Subsequent Approval) | Q4 2015 - January 29, 2016 | 1092850.61 | 1749212 | 1955373.8
Deferred | Generation | 49942 | HYD - Tidewater Facility Refurbishment | 2018 ACE Plan | 2018 ACE Plan | 1234178 | 1234178 | 83158.61
Withdrawn | Generation | 29807 | HYD - Tusket Falls Main Dam | 2017 ACE Plan (for Subsequent Approval) | OTQ - July 23, 2021 | 9940664 | 36826119 | 24940879.97
Approved | Generation | 51234 | HYD - WRC HVAC Upgrade | 2018 ACE Plan | 2018 ACE Plan | 1876537 | 1876537 | 1877263.33
Internally FIN'd | Generation | 51235 | HYD - WRC Main Access Rd Refurbishment | 2018 ACE Plan | 2018 ACE Plan | 2686075 | 2686075 | 2684742.69
Approved | Generation | 48791 | HYD - WRC Safety Standards Upgrades | 2018 ACE Plan (for Subsequent Approval) | OTQ - June 4, 2018 | 1019927.73 | 1760570 | 1919440.54
Approved | Generation | 51236 | HYD - WRC Tailrace Rock Bolting | 2018 ACE Plan | 2018 ACE Plan | 8861996 | 8861996 | 7113810.55
Approved | Generation | 48052 | HYD Annapolis HVAC Upgrade | 2017 ACE Plan (for Subsequent Approval) | OTQ - March 8, 2017 | 1498367 | 1573596 | 1774912.33
Approved | Generation | 44978 | HYD-Wreck Cove Automation | 2015 ACE Plan (for Subsequent Approval) | Q2 2015 - July 31, 2015 | 2379999.4 | 3802446.04 | 4022223.92
Deferred | General Plant | 49600 | IT - Network Architecture Redesign | 2017 ACE Plan (for Subsequent Approval) |  | 1183826 |  | 0
Approved | General Plant | 49855 | IT Desktop SW Modernization | 2017 ACE Plan (for Subsequent Approval) | Q3 2017 - October 30, 2017 | 2013034 | 4620515.89 | 4501620.94
Approved | Transmission | 47950 | L5017 Replacements & Upgrades | 2016 ACE Plan | Q1 2018 - May 7, 2018 | 2182142.33 | 3062664 | 3012632.2
Approved | Transmission | 47949 | L5028 Replacements and Upgrades | 2016 ACE Plan | 2016 ACE Plan | 1144354.64 | 1144354.64 | 943265
Approved | Transmission | 49790 | L5505 Replacements and Upgrades | 2017 ACE Plan | 2017 ACE Plan | 1223571.35 | 1223571.35 | 816588.04
Approved | Transmission | 49778 | L5535 Replacements and Upgrades | 2017 ACE Plan | OTQ - April 16, 2018 | 1261920.05 | 2590269 | 2837177.2
Approved | Transmission | 49779 | L6537 Replacements and Upgrades | 2018 ACE Plan | OTQ - March 4, 2019 | 1255220 | 2331474.13 | 2284615.84
Approved | Transmission | 52320 | L6549 2018 Replacements & Upgrades | 2018 ACE Plan | 2018 ACE Plan | 1406535 | 1406535 | 1452522.7
Approved | Transmission | 44987 | L7003 Lidar Upgrades | 2015 ACE Plan (for Subsequent Approval) | OTQ - August 31, 2015 | 6885816.76 | 11032275 | 10906621.99
Approved | Transmission | 49793 | L7011 Replacements and Upgrades | 2017 ACE Plan | OTQ - April 1, 2019 | 3343484.22 | 4810276 | 4591706.24
Approved | Transmission | 47954 | L7012 Replacements and Upgrades | 2017 ACE Plan | 2017 ACE Plan | 4428519.78 | 4428519.78 | 4392085.97
Approved | Generation | 49940 | LM6000 TUC5 Control System Upgrade | 2017 ACE Plan (for Subsequent Approval) | OTQ - July 3, 2018 | 1018769 | 1275559 | 1070506.19
Approved | Transmission | C0001900 | Mount Hope 69-25kV Substation | 2018 ACE Plan | 2018 ACE Plan | 2982338 | 2982338 | 2997775.64
Approved | Transmission | 52323 | Port Hastings 2C BPS Upgrade | P&A | Q2 - August 7, 2018 | 0 | 4201448.53 | 3997957.67
Approved | General Plant | 50153 | Self Serve Development Phase 2 | 2017 ACE Plan (for Subsequent Approval) | OTQ - September 15, 2017 | 1827720 | 1160528 | 1316269.11
Not Approved at this time | Transmission | 43678 | Separate L8004/L7005 on Canso Crossing Double Circuit Tower(DCT) | 2017 ACE Plan (for Subsequent Approval) | OTQ - January 27, 2022* | 16183691 | 20387278 | 20387277.51
Not Approved at this time | Transmission | 45066 | Upgrade L6511 and L7019 Thermal Rating | 2015 ACE Plan (for Subsequent Approval) | OTQ - January 27, 2022* | 3693032.91 | 2691017 | 2691016.62
Not Approved at this time | Transmission | 43324 | Replace L6513 / Upgrade Line Terminals | 2015 ACE Plan (for Subsequent Approval) | OTQ - January 27, 2022* | 23429902 | 18626428 | 18625081.5
Not Approved at this time | Transmission | 45067 | 67N Onslow 345 KV Node Swap | 2014 ACE Plan (for Subsequent Approval) | OTQ - January 27, 2022* | 3006487 | 2982714 | 2982585.13
Approved | Transmission | 48022 | Spider Lake Substation Addition | 2016 ACE Plan (for Subsequent Approval) | OTQ - March 4, 2019 | 6348980.72 | 9158260 | 9066397.53
Awaiting Approval | Generation | 50518 | HYD - Ruth Falls Main Dam Refurbishment | 2019 ACE Plan | OTQ - October 11, 2024 | 7244422 | 15445507.77 | 4259126.67
Internally FIN'd | Generation | 48638 | TRE - Rail Car Fuel Delivery Upgrade | 2019 ACE Plan | 2019 ACE Plan | 1236623 | 1236623 | 1209419.23
Approved | Transmission | C0010042 | 2019 Transmission Right-of-Way Widening 69kV | 2019 ACE Plan | 2019 ACE Plan | 5650794 | 5650794 | 5634125.15
Approved | Transmission | C0010948 | 2019/2020 Sacrificial Anode Installation Program | 2019 ACE Plan | 2019 ACE Plan | 3099862 | 3099862 | 3244208.44
Approved | Transmission | C0010952 | 2019/2020 Substation Polychlorinated Biphenyl (PCB) Equipment Removal | 2019 ACE Plan | 2019 ACE Plan | 2786245 | 2786245 | 2688210.09
Approved | Transmission | C0010949 | 2019/2020 Steel Tower Life Extension | 2019 ACE Plan | 2019 ACE Plan | 2414140 | 2414140 | 2178231.16
Approved | Transmission | C0011339 | L6549 - Replacements and Upgrades Phase 2 | 2019 ACE Plan | Q1 - May 13, 2024 | 2209907 | 3993973.66 | 3903389.95
Approved | Transmission | C0011241 | L5026 - Replacements and Upgrades | 2019 ACE Plan | 2019 ACE Plan | 1498789 | 1498789 | 1379562.67
Approved | Transmission | C0010978 | 2019/2020 Transmission Switch & Breaker Replacement | 2019 ACE Plan | 2019 ACE Plan | 1044148 | 1044148 | 1029498.49
Approved | Transmission | C0011243 | L5551 - Replacements and Upgrades | 2019 ACE Plan | 2019 ACE Plan | 1014077 | 1014077 | 1115386.39
Approved | Distribution | C0011208 | 2019 Padmount Replacement Program | 2019 ACE Plan | 2019 ACE Plan | 1413544 | 1413544 | 1464939.72
Approved | Distribution | C0006319 | 2019 PCB Pole Top Transformer Replacements | 2019 ACE Plan | 2019 ACE Plan | 1177592 | 1177592 | 1411359.32
Approved | General Plant | C0013438 | IT - T&D WAM Phase 1 - GIS and Field Design System | 2019 ACE Plan (2018 Pending Submission) | OTQ - December 7, 2018 | 7978434 | 7978434 | 8098332.98
Partial Approval | Generation | C0013838 | HYD WRC LEM Unit Rehabilitation | 2020 ACE Plan (2019 Pending Submission) | OTQ - February 21, 2020 | 109691966.51 | 101787264 | 93557568.36
Approved | Distribution | 47794 | Heckman's Island Submarine Cable Replacement | 2021 ACE Plan (for Subsequent Approval) | Q1 2021 - May 3, 2021 | 1296112.43 | 1338363.88 | 1554832.82
Approved | General Plant | C0011378 | Route Network Upgrades | 2020 ACE Plan (2019 Pending Submission) | OTQ - December 2, 2019 | 5724239.86 | 5717751.93 | 5837970.64
Approved | General Plant | 49480 | IT - Data Centre Disaster Recovery | 2020 ACE Plan (2019 Pending Submission) | OTQ - December 2, 2019 | 6103797.71 | 6335161.85 | 6249505.23
Approved | General Plant | C0010838 | MCC - HVAC Replacement | 2019 ACE Plan (for Subsequent Approval) | OTQ - October 4, 2021 | 1071364 | 1606253.82 | 1531909.94
Approved | General Plant | C0002137 | ECC - Map Board and Technology Modernization | 2019 ACE Plan (for Subsequent Approval) | Q3 - November 4, 2019 | 2568789 | 2506267.89 | 2274318.45
Approved | Transmission | C0021105 | L7002 Replacements and Upgrades Phase 2 | P&A | Q3 - November 4, 2019 | 0 | 3121441.58 | 3320026.92
Approved | Distribution | C0020623 | New Distribution Rights-of-Way Phase 5 | 2020 ACE Plan | 2020 ACE Plan | 10015266.14 | 10015266.14 | 9930357.98
Approved | Transmission | C0020627 | 2020 Transmission Right-of-Way Widening 69kV | 2020 ACE Plan | 2020 ACE Plan | 5489820 | 5489820 | 5617281.86
Approved | Transmission | C0011261 | 101W Port Mersey Substation Expansion | 2020 ACE Plan | 2020 ACE Plan | 4651384 | 4651384 | 4635408.81
Approved | Transmission | C0021123 | 2020/2021 Substation Polychlorinated Biphenyl (PCB) Equipment Removal | 2020 ACE Plan | 2020 ACE Plan | 5197371.63 | 5197371.63 | 5365749.62
Approved | Generation | 49949 | LM6000 TUC4 Control System Replacement | 2020 ACE Plan | 2020 ACE Plan | 1149996.27 | 1149996.27 | 901766.31
Approved | Transmission | C0011321 | L5031 Replacements and Upgrades Phase 1 | 2020 ACE Plan | 2020 ACE Plan | 2147211.75 | 2147211.75 | 367756.27
Approved | Transmission | C0021107 | L8001 Replacements and Upgrades Phase 1 | 2020 ACE Plan | 2020 ACE Plan | 2292092.86 | 2292092.86 | 2517260.08
Approved | Distribution | C0020835 | 2020 Padmount Replacement Program | 2020 ACE Plan | 2020 ACE Plan | 1612389.23 | 1612389.23 | 1515135.61
Approved | Transmission | C0021122 | 2020/2021 Transmission Switch & Breaker Replacement | 2020 ACE Plan | 2020 ACE Plan | 1312642.8 | 1312642.8 | 1502536.63
Approved | Distribution | C0020834 | 2020/2021 Inaccessible PCB Transformer Replacements | 2020 ACE Plan | 2020 ACE Plan | 2950294.39 | 2950294.39 | 3103288.75
Approved | General Plant | C0021109 | New RTU Deployment Project | 2020 ACE Plan | 2020 ACE Plan | 8028097.17 | 8028097.17 | 7187214.02
Approved | Transmission | 52303 | L7019 Replacements and Upgrades | 2020 ACE Plan | 2020 ACE Plan | 1374091.91 | 1374091.91 | 1383195.98
Internally FIN'd | Transmission | C0021323 | Trenton 50N-T13 Replacement | 2020 ACE Plan | 2020 ACE Plan | 1516880.03 | 1516880.03 | 1336009
Approved | Transmission | C0021026 | Willow Lane 15N-T3 Replacement | 2020 ACE Plan | 2020 ACE Plan | 1326646.57 | 1326646.57 | 1179586.14
Approved | Generation | 49756 | HYD - Marshall Falls Main Dam Refurbishment | 2020 ACE Plan | 2020 ACE Plan | 5452793.82 | 5452793.82 | 597422.33
Approved | Transmission | C0021142 | 19W-T51 Transformer Replacement | 2020 ACE Plan | 2020 ACE Plan | 1512336.33 | 1512336.33 | 1473278.51
Approved | Distribution | C0021182 | 93V-313-Meteghan Rebuild | 2020 ACE Plan | 2020 ACE Plan | 1075624.51 | 1075624.51 | 927225.44
Approved | Distribution | C0010778 | Smart Grid Nova Scotia Project | 2020 ACE Plan (for Subsequent Approval) | OTQ - December 5, 2019 | 6740589.05 | 7053622 | 6409573.21
Approved | Distribution | C0019379 | 50N-410 - 4C-430 Highway 104 Twinning | 2020 ACE Plan (for Subsequent Approval) | OTQ - June 1, 2020 | 1361237.37 | 1137222.61 | 1228681.6
Approved | Generation | C0020385 | LIN Heavy Oil Tank Refurbishment | 2020 ACE Plan (for Subsequent Approval) | OTQ - January 28, 2021 | 1162324.53 | 3396731.06 | 2805663.88 | Q4 - February 3, 2025 | 2805664 | -591067.06
Approved | General Plant | C0023622 | AMO Substation and Transmission APM Program | 2020 ACE Plan (for Subsequent Approval) | OTQ - April 6, 2020 | 2087848.28 | 2217589 | 2369151.05
Partial Approval | Generation | C0014218 | HYD WRC LEM Balance of Plant | 2021 ACE Plan (2020 Pending Submission) | OTQ - April 30, 2021 | 21186378.42 | 27637896 | 20315430.12
Approved | General Plant | C0023623 | AMO Distribution APM Program | 2020 ACE Plan (for Subsequent Approval) | OTQ - April 6, 2020 | 1708239.85 | 1721484.45 | 1817850.92
Approved | Generation | 16374 | HYD Gaspereau Dam Safety | 2008 ACE Plan | OTQ - February 23, 2020 | 4354889 | 22703451 | 12113588.15
Approved | General Plant | C0017098 | Ragged Lake Generator Replacement | P&A | Q2 2020 - August 4, 2020 | 0 | 2229266.75 | 1671461.07
Approved | Distribution | C0031083 | New Distribution Rights-of-Way Phase 6 | 2021 ACE Plan | 2021 ACE Plan | 9762734.52 | 9762734.52 | 9705372.68
Approved | Transmission | C0031263 | 2021/2022 Substation Polychlorinated Biphenyl (PCB) Equipment Removal | 2021 ACE Plan | 2021 ACE Plan | 7512225.73 | 7512225.73 | 7013147.46
Approved | Transmission | C0031089 | 2021/2022 Transmission Right-of-Way Widening 69kV | 2021 ACE Plan | 2021 ACE Plan | 5288520 | 5288520 | 5512846.46
Awaiting Approval | Transmission | C0031122 | L6539 Replacements and Upgrades | 2021 ACE Plan | OTQ - April 7, 2025 | 2821842.28 | 5584042.12 | 1376667.32
Approved | Transmission | C0031085 | L6516 Line Replacement and Upgrades | 2021 ACE Plan | 2021 ACE Plan | 2730591.81 | 2730591.81 | 2542688.17
Approved | Transmission | C0031050 | New Spare Large Autotransformer | 2021 ACE Plan | 2021 ACE Plan | 2398564.03 | 2398564.03 | 2373248.72
Approved | Transmission | C0033644 | 2021/2022 Steel Tower Life Extension | 2021 ACE Plan | 2021 ACE Plan | 2332745.87 | 2332745.87 | 1830410.86
Approved | Transmission | C0033645 | 2021/2022 Steel Tower Refurbishment | 2021 ACE Plan | 2021 ACE Plan | 1944004.84 | 1944004.84 | 2181016.61
Approved | Distribution | C0031145 | 2021 Padmount Replacement Program | 2021 ACE Plan | 2021 ACE Plan | 1636152.76 | 1636152.76 | 1166366.12
Approved | Transmission | C0031262 | 2020/2021 Transmission Switch and Breaker Replacement | 2021 ACE Plan | 2021 ACE Plan | 1483047.6 | 1483047.6 | 1455067.72
Approved | Transmission | C0031064 | L5054 Replacements and Upgrades | 2021 ACE Plan | 2021 ACE Plan | 1134737.48 | 1134737.48 | 996871.76
Approved | Generation | 46483 | CT - TUS Control System Upgrade | 2021 ACE Plan | 2021 ACE Plan | 1046322.12 | 1046322.12 | 1096634.88
Approved | Generation | C0026285 | TRE Heavy Fuel Oil Tank Refurbishment | 2021 ACE Plan (for Subsequent Approval) | OTQ - June 10, 2021 | 1732920.72 | 2979545.51 | 2288961.61
Approved | General Plant | C0030987 | IT - NERC CIP Environment Refresh | 2022 ACE Plan (2021 Pending Submission) | OTQ - March 7, 2022 | 1446131 | 1259927 | 1309292.99
Approved | Distribution | C0041892 | New Distribution Rights-of-Way Phase 7 | 2022 ACE Plan | 2022 ACE Plan | 9854290.53 | 9854290.53 | 10221583.54
Approved | Transmission | C0041893 | 2022/2023 Transmission Right-of-Way Widening 69kV | 2022 ACE Plan | 2022 ACE Plan | 5312315 | 5312315 | 5186446.8
Approved | Transmission | C0041837 | 2022/2023 Substation Polychlorinated Biphenyl (PCB) Equipment Removal | 2022 ACE Plan | 2022 ACE Plan | 3805434.21 | 3805434.21 | 3147888.34
Approved | Transmission | C0041793 | L7002 Replacements and Upgrades Phase 2 | 2022 ACE Plan | 2022 ACE Plan | 3640960.16 | 3640960.16 | 3856784.58
Approved | Transmission | C0041805 | L7005 Replacements and Upgrades Phase 2 | 2022 ACE Plan | 2022 ACE Plan | 3182518.11 | 3182518.11 | 2910451.19
Approved | Transmission | C0041989 | 2022/2023 Sacrificial Anode Installation Program | 2022 ACE Plan | 2022 ACE Plan | 3015106.56 | 3015106.56 | 2773422.66
Deferred | Transmission | C0041794 | L5031 Replacements and Upgrades Phase 2 | 2022 ACE Plan | 2022 ACE Plan | 2905019.26 | 2905019.26 | 0
Approved | Transmission | C0041810 | L5022 Replacements and Upgrades | 2022 ACE Plan | 2022 ACE Plan | 2172200.18 | 2172200.18 | 1618002.65 | Q4 - February 3, 2025 | 1618003 | -554197.18
Approved | Transmission | C0041791 | L6551 Replacements and Upgrades | 2022 ACE Plan | 2022 ACE Plan | 1988245.66 | 1988245.66 | 476639.12
Approved | Distribution | C0043130 | 2022 Padmount Replacement Program | 2022 ACE Plan | 2022 ACE Plan | 1807359.37 | 1807359.37 | 1815397.85
Internally FIN'd | Generation | C0030529 | TUC3 Generator Refurbishment | 2022 ACE Plan | 2022 ACE Plan | 1629925.63 | 1629925.63 | 1593296.76
Approved | Transmission | C0043571 | 2022/2023 Transmission Switch & Breaker Replacement | 2022 ACE Plan | 2022 ACE Plan | 1612637.79 | 1612637.79 | 1538695.57
Internally FIN'd | Transmission | C0041790 | L8001 Replacements and Upgrades Phase 2 | 2022 ACE Plan | 2022 ACE Plan | 1395536.96 | 1395536.96 | 1169625.77
Approved | Generation | C0036368 | HYD - Lower Great Brook Switchgear Replacement | 2022 ACE Plan | 2022 ACE Plan | 1362281.36 | 1362281.36 | 1414575.19
Approved | Transmission | C0043010 | 2022/2023 Wood Pole Retreatment Program | 2022 ACE Plan | 2022 ACE Plan | 1300037.21 | 1300037.21 | 791054.43
Approved | Transmission | C0041804 | 2022 Line Retirement Program | 2022 ACE Plan | 2022 ACE Plan | 1242178.29 | 1242178.29 | 159284.4
Approved | Generation | C0024484 | HYD - Fourth Lake Switchgear Replacement | 2022 ACE Plan | 2022 ACE Plan | 1145245.46 | 1145245.46 | 1455262.57
Approved | Generation | C0029691 | CT - VJ1 Control System Upgrade | 2022 ACE Plan | 2022 ACE Plan | 1016224.92 | 1016224.92 | 1002085.09
Approved | Transmission | C0045132 | ECEI - Battery Energy Storage System Project | 2022 ACE Plan (for Subsequent Approval) | OTQ - January 25, 2024 | 171207919.79 | 237772259 | 87857938.7
Deferred | Generation | C0044392 | Eastern Clean Energy Initiative (ECEI) - Coal Conversion | 2022 ACE Plan (for Subsequent Approval) |  | 32341324.51 |  | 1810843.13
Deferred | Generation | C0034486 | HYD - WRC LEM Penstock intake | 2022 ACE Plan (for Subsequent Approval) |  | 11239850.61 |  | 1206698.21
Approved | Generation | C0000979 | HYD - Governor Dam Refurbishment | 2022 ACE Plan (for Subsequent Approval) | OTQ - November 6, 2023 | 2696629.84 | 4844345.32 | 4795018.52
Approved | Distribution | C0022662 | 22C-404GA Lennox Passage Rebuild | 2022 ACE Plan (for Subsequent Approval) | OTQ - July 4, 2022 | 2352190.78 | 2609595.48 | 2540026.98
Deferred | Transmission | C0036826 | L8004 Parallel Canso Strait Crossing | 2022 ACE Plan (for Subsequent Approval) |  | 2139081.25 |  | 0
Approved | General Plant | C0041994 | NERC CIP 2022 | 2022 ACE Plan (for Subsequent Approval) | OTQ - April 4, 2022 | 1379473.59 | 1247663 | 1186070.49
Approved | Generation | C0041651 | TUC HFO Tank 4 Refurbishment | 2022 ACE Plan (for Subsequent Approval) | Q4 - February 6, 2023 | 1110292.77 | 2734313 | 2756903.42
Approved | Transmission | C0010956 | 78W-Martin’s Brook Substation Relocation | P&A | OTQ - March 3, 2025 | 0 | 5122761 | 4377563.63
Approved | Transmission | C0045510 | 20V-T52 Transformer Replacement | U&U | Q3 - November 7, 2022 | 0 | 1506565.52 | 1428135.67
Approved | Transmission | C0041807 | L5534 Replacements and Upgrades | P&A | OTQ - December 5, 2022 | 0 | 1426418.29 | 1555748.02
Approved | Transmission | C0049212 | L8001 Replacements and Upgrades Phase 3 | P&A | OTQ - December 5, 2022 | 0 | 1263906.4 | 1208027.05
Approved | Transmission | C0050835 | 2023/2024 Steel Tower Refurbishment | P&A | OTQ - December 5, 2022 | 0 | 2056634.87 | 1473216.56
Approved | Transmission | C0052055 | 2023/2024 Transmission Right-of-Way Widening 69kV | P&A | OTQ - December 5, 2022 | 0 | 5332315 | 4951305.64
Approved | Distribution | C0052056 | New Distribution Rights-of-Way Phase 8 | P&A | OTQ - December 5, 2022 | 0 | 9796663.1 | 9088167.29
Approved | Transmission | C0052634 | L5016 Replacements and Upgrades | P&A | OTQ - December 5, 2022 | 0 | 2697636.73 | 2944095.87
Approved | Generation | C0001222 | CT BGT1 Engine Exchange | P&A | OTQ - January 9, 2023 | 0 | 2338747 | 2350941.06
Approved | Generation | C0055376 | TUC1 - LP Blade Refurbishment U&U | U&U | Q4 - February 6, 2023 | 0 | 2025440.22 | 1988074.59
Approved | Generation | C0041506 | LM6000 Engine 191-253 Refurbishment | 2023 ACE Plan | OTQ - March 7, 2024 | 8740978.85 | 13473407 | 13067188.47
Approved | Generation | C0012838 | HYD - Lequille Canal Dyke, Gates and Tailrace Refurbishment | 2023 ACE Plan | 2023 ACE Plan | 7058816.14 | 7058816.14 | 1668264.32
Approved | Generation | C0029682 | CT VJ2 - Replace Generator Assembly | 2023 ACE Plan | 2023 ACE Plan | 5397737.93 | 5397737.93 | 1507924.62
Approved | Generation | C0051134 | TUC2 - L-0 Blade Replacement | 2023 ACE Plan | 2023 ACE Plan | 4157503.35 | 4157503.35 | 4172144.35
Approved | Transmission | C0041788 | L6516 Replacements and Upgrades Phase 2 | 2023 ACE Plan | OTQ July 2, 2024 | 3123474.28 | 5442793.92 | 4233741.71
Approved | Transmission | C0055539 | 10H-T1 Transformer Replacement | 2023 ACE Plan | 2023 ACE Plan | 2420891.67 | 2420891.67 | 37218.72
Approved | Transmission | C0052299 | 2023/2024 Steel Tower Life Extension | 2023 ACE Plan | 2023 ACE Plan | 2195463.46 | 2195463.46 | 705665.6
Approved | Transmission | C0055796 | 2023 EHV Breaker Replacements | 2023 ACE Plan | OTQ - October 2, 2023 | 2048410.56 | 3463488.74 | 64183.86
Approved | Transmission | C0055696 | L5031 Replacement and Upgrades Robinson Corner Tap | 2023 ACE Plan | 2023 ACE Plan | 1357477.23 | 1357477.23 | 997734.18
Approved | Distribution | C0050836 | 2023 Padmount Replacement Program | 2023 ACE Plan | 2023 ACE Plan | 1309551.39 | 1309551.39 | 1495445.16
Approved | Generation | C0051135 | TUC2 - Turbine Valves Refurbishment 2023 | 2023 ACE Plan | 2023 ACE Plan | 1048924 | 1048924 | 967771.84
Approved | Transmission | C0052654 | L5541 Water Crossing Upgrades | 2023 ACE Plan | 2023 ACE Plan | 1047073.87 | 1047073.87 | 0
Approved | Transmission | C0053316 | Michelin Voltage Sag Reduction DVR | 2023 ACE Plan (for Subsequent Approval) | OTQ - April 12, 2024 | 21007507.1 | 31170675 | 30852918.09
Approved | General Plant | C0042166 | IT - Data Loss Prevention (DLP) Platform | 2023 ACE Plan (for Subsequent Approval) | OTQ - June 7, 2023 | 3233905.29 | 4261239.1945 | 3944009.61
Approved | Generation | C0051894 | TUC - HFO Tank 3 Refurbishment | 2023 ACE Plan (for Subsequent Approval) | OTQ - March 7, 2024 | 2053937.48 | 2218012 | 2251679.75
Approved | General Plant | C0030984 | IT - Cisco UCS Lifecycle | 2023 ACE Plan (for Subsequent Approval) | OTQ - September 5, 2023 | 2047690.67 | 2456609.31 | 2088998.46
Approved | Generation | C0044030 | WIN - DIG Haight's Brook Crossing Replacement | 2023 ACE Plan (for Subsequent Approval) | OTQ - November 6, 2023 | 2046984.81 | 2024051.53 | 278441.16
Deferred | Generation | C0047973 | HYD - ANN Sluice Gates and Check Refurbishment | 2023 ACE Plan (for Subsequent Approval) |  | 1957500.93 |  | 206463.89
Awaiting Approval | Transmission | C0055557 | 76V-T1 Transformer Replacement | 2023 ACE Plan (for Subsequent Approval) | OTQ - April 7, 2025 | 1751258.26 | 3244385.61 | 1577545.44
Approved | General Plant | C0011167 | IT - Backup Infrastructure Upgrade | 2023 ACE Plan (for Subsequent Approval) | OTQ - June 7, 2023 | 1557470.73 | 2315457.44 | 2310349.58
Approved | Generation | C0048591 | CT VJ1 Engine P686621 Refurbishment | P&A | OTQ - March 6, 2023 | 0 | 2312509.06 | 2283878.09
Approved | Generation | C0054356 | TUC – Roof Replacement U&U | U&U | OTQ - March 6, 2023 | 0 | 1459455.09 | 1412184.76
Approved | Generation | C0053916 | CT BGT4 Engine P686630 Refurbishment | U&U | OTQ - April 3, 2023 | 0 | 1850500.99 | 1718317.45
Approved | Transmission | C0031052 | Replenish Spare Transformer Used at 58C | 2021 ACE Plan (Less than $1M) | OTQ - June 7, 2023 | 982910 | 1303826.93 | 1071232.74
Approved | Generation | 51761 | LIN2 2022/2023 Winter Capacity Requirement | U&U | OTQ - September 5, 2023 | 0 | 2512340.71 | 2526651.43
Internally FIN'd | Transmission | C0059403 | 62H Low Voltage Switchgear Replacement | U&U | OTQ - September 5, 2023 | 0 | 1485175.79 | 1525601.88
Approved | Generation | C0006418 | HYD WRC Tailrace Tunnel Rock Bolting Phase 2 | 2024 ACE Plan | 2024 ACE Plan | 15722669.17 | 15722669.17 | 1200720.21
Internally FIN'd | Generation | C0041050 | LIN 824 Wheeled Dozer Replacement | 2024 ACE Plan | 2024 ACE Plan | 1607861.85 | 1607861.85 | 1530934.61
Approved | General Plant | C0047277 | IT - GIS Utility Network Upgrade | 2024 ACE Plan | 2024 ACE Plan | 6175229.82 | 6175229.82 | 2579657.73
Approved | Generation | C0049013 | HYD - Lower Great Brook Log Hoist Replacement | 2024 ACE Plan | 2024 ACE Plan | 2158657.9 | 2158657.9 | 1770797.91
Approved | Generation | C0049032 | HYD - Cowie Falls Log Hoist Replacement | 2024 ACE Plan | 2024 ACE Plan | 2237991.11 | 2237991.11 | 1629054.77
Approved | General Plant | C0049619 | IT - ERP Upgrade (EBS, PS, PP, OBIA) | 2024 ACE Plan | 2024 ACE Plan | 6198799.37 | 6198799.37 | 5058003.68
Approved | Transmission | C0050842 | 2024 Bulk Oil Breaker Replacement Program | 2024 ACE Plan | 2024 ACE Plan | 3274755.9 | 3274755.9 | 851278.12
Awaiting Approval | Generation | C0051136 | TUC2 - HP/IP Turbine Refurbishment | 2024 ACE Plan | Q1 - May 16, 2025 | 4264777.44 | 5965028 | 5965094.02
Approved | Transmission | C0056240 | 2024/2025 Transmission Switch and Breaker Replacements | 2024 ACE Plan | 2024 ACE Plan | 3271621.79 | 3271621.79 | 2478449.54
Approved | Distribution | C0057142 | New Distribution Rights-of-Way Phase 9 | 2024 ACE Plan | 2024 ACE Plan | 19141913.7 | 19141913.7 | 19189121.4
Approved | Transmission | C0057882 | 2024 Pennsylvania Breaker Replacements | 2024 ACE Plan | 2024 ACE Plan | 2163831.86 | 2163831.86 | 491554.93
Approved | Generation | C0058942 | WRC D11-2 Foundation Stabilization | 2024 ACE Plan | 2024 ACE Plan | 1540602.39 | 1540602.39 | 1416577.81
Approved | Transmission | C0059046 | 101S and 79N Reactor Replacements | 2024 ACE Plan | 2024 ACE Plan | 1460062.22 | 1460062.22 | 814148.33
Approved | Generation | C0060608 | TUC6 Turbine Refurbishment | 2024 ACE Plan | 2024 ACE Plan | 2472311.19 | 2472311.19 | 538138.28
Approved | Generation | C0060707 | CT BGT1 Generator Refurbishment | 2024 ACE Plan | 2024 ACE Plan | 3482602.45 | 3482602.45 | 7307.73
Approved | Distribution | C0060749 | 2024 Padmount Replacement Program | 2024 ACE Plan | 2024 ACE Plan | 1288197.9 | 1288197.9 | 1042013.63
Approved | Transmission | C0061023 | 2024 EHV Breaker Replacements | 2024 ACE Plan | 2024 ACE Plan | 3638479.75 | 3638479.75 | 0
Approved | Transmission | C0061046 | 2024 Merlin Gerin Breaker Replacements | 2024 ACE Plan | 2024 ACE Plan | 1169590.5 | 1169590.5 | 225890.69
Approved | Transmission | C0061387 | 2024 2025 Wood Pole Retreatment Program | 2024 ACE Plan | 2024 ACE Plan | 1209391.21 | 1209391.21 | 256254.74
Approved | Transmission | C0061403 | 2024 2025 Sacrificial Anode Installation Program | 2024 ACE Plan | 2024 ACE Plan | 2382112.6 | 2382112.6 | 1732744.14
Approved | Transmission | C0061545 | L6006 Replacements and Upgrades | 2024 ACE Plan | 2024 ACE Plan | 5032640.4 | 5032640.4 | 4465995.79
Approved | Transmission | C0061546 | L6514 Replacements and Upgrades | 2024 ACE Plan | 2024 ACE Plan | 2102666.38 | 2102666.38 | 1588417.86
Approved | Transmission | C0061547 | L7022 Replacements and Upgrades | 2024 ACE Plan | 2024 ACE Plan | 2283568.76 | 2283568.76 | 36468.14
Approved | Transmission | C0061550 | L5031 Replacements and Upgrades - Hubbards to East Chester | 2024 ACE Plan | 2024 ACE Plan | 5297583.52 | 5297583.52 | 3503110.48
Approved | Transmission | C0061551 | L7009 Replacements and Upgrades | 2024 ACE Plan | 2024 ACE Plan | 3280328.4 | 3280328.4 | 2100.14
Approved | Transmission | C0061743 | L6038 Realignment | 2024 ACE Plan | 2024 ACE Plan | 1032910.93 | 1032910.93 | 129085.06
Approved | Transmission | C0061883 | 129H - Kearney Lake Substation Rebuild | 2024 ACE Plan | 2024 ACE Plan | 1017322.14 | 1017322.14 | 16424.33
Approved | General Plant | C0054755 | IT - Connect My Data (Green Button) | 2024 ACE Plan (for Subsequent Approval) | Q4 - February 5, 2024 | 2309350.36 | 2964237 | 2823922.92
Deferred | Transmission | C0031286 | Spare Padmounted Substation | 2024 ACE Plan (for Subsequent Approval) |  | 1319837.87 |  | 0
Pending Submission | General Plant | C0032664 | ECC Optimization Tools Project | 2024 ACE Plan (for Subsequent Approval) |  | 4329149.97 |  | 4011634.66
Awaiting Approval | Generation | C0050414 | HYD Roseway Asset Decommissioning | 2024 ACE Plan (for Subsequent Approval) | OTQ - December 20, 2024 | 4650648.04 | 4915649 | 3530636.48
Awaiting Approval | Generation | C0060816 | POT - HFO Tank Refurbishment | 2024 ACE Plan (for Subsequent Approval) | OTQ - December 17, 2024 | 2012802.82 | 6242633 | 3394503.46
Deferred | General Plant | C0061287 | IT - Third Party Risk Management | 2024 ACE Plan (for Subsequent Approval) |  | 1405970.41 |  | 0
Awaiting Approval | General Plant | C0061289 | IT - Network Next Generation Security Design | 2024 ACE Plan (for Subsequent Approval) | OTQ - April 7, 2025 | 2632635 | 1814215.74 | 841956.41
Approved | Distribution | C0061521 | New Distribution Rights-of-Way Phase 10 | 2024 ACE Plan (for Subsequent Approval) | OTQ - October 7, 2024 | 18904608 | 20890176 | 9975818.18
Approved | Generation | C0038126 | HYD Cowie Falls Unit 12 Overhaul | 2024 ACE Plan (Less than $1M) | Q1 - May 13, 2024 | 964521.17 | 1274890 | 823640.42
Approved | Generation | C0053655 | HYD Cowie Falls Unit 11 Overhaul | 2023 ACE Plan (Less than $1M) | Q1 - May 13, 2024 | 913947.02 | 1225491 | 1291555.64
Approved | Generation | C0059283 | LIN2 PE 2023/2024 Winter Capacity Requirements | U&U | Q1 - May 13, 2024 | 0 | 1661834 | 1663857.13
Approved | Transmission | C0062123 | 143H-Mount Uniacke Substation | P&A | Q2 - August 6, 2024 | 0 | 9040869 | 1446565.64
Approved | General Plant | C0056461 | IT - Contact Centre Cloud Migration | 2024 ACE Plan (for Subsequent Approval) | OTQ - September 16, 2024 | 929372 | 3237539 | 1709695.38
Awaiting Approval | Transmission | C0031048 | 91H-T11 Transformer Replacement | 2025 ACE Plan | 2025 ACE Plan | 6914621.96 | 6914621.96 | 29527.27
Awaiting Approval | Generation | C0039266 | HYD - Gulch Overhaul | 2025 ACE Plan | 2025 ACE Plan | 1371379.09 | 1371379.09 | 75440.62
Awaiting Approval | Generation | C0048990 | HYD AVO 2 Switchgear Replacement | 2025 ACE Plan | 2025 ACE Plan | 1814631.36 | 1814631.36 | 411074.66
Awaiting Approval | Transmission | C0050834 | Spare EHV Breaker Replacements | 2025 ACE Plan | 2025 ACE Plan | 1178831.81 | 1178831.81 | 156.26
Awaiting Approval | Transmission | C0050852 | 10V-T1 Transformer Replacement | 2025 ACE Plan | 2025 ACE Plan | 2113336.98 | 2113336.98 | 18178.38
Awaiting Approval | General Plant | C0051815 | RTU Replacements Program Phase 6 | 2025 ACE Plan | 2025 ACE Plan | 5959915.27 | 5959915.27 | 414068.3
Awaiting Approval | Transmission | C0053295 | L5004 Kearney Lake Structure Replacement | 2025 ACE Plan | 2025 ACE Plan | 2478536.78 | 2478536.78 | 266816.53
Awaiting Approval | Transmission | C0057682 | Spare Transformer Replacement | 2025 ACE Plan | 2025 ACE Plan | 2286389.47 | 2286389.47 | 42422.54
Awaiting Approval | Generation | C0068659 | TRE5 - IP-LP Turbine Refurbishment | 2025 ACE Plan | 2025 ACE Plan | 1282669.84 | 1282669.84 | 76327.38
Awaiting Approval | Distribution | C0068786 | 2025 Padmount Replacement Program | 2025 ACE Plan | 2025 ACE Plan | 1354219.4 | 1354219.4 | 0
Awaiting Approval | Generation | C0068882 | TUC1 Generator Refurbishment | 2025 ACE Plan | 2025 ACE Plan | 2124210.74 | 2124210.74 | 0
Awaiting Approval | Generation | C0068887 | TUC3 Turbine Valves Refurbishment | 2025 ACE Plan | 2025 ACE Plan | 1869103.9 | 1869103.9 | 8321.49
Awaiting Approval | Distribution | C0068952 | 2025 PCB Poletop Sampling and Replacement | 2025 ACE Plan | 2025 ACE Plan | 7158973.99 | 7158973.99 | 595705.29
Awaiting Approval | Distribution | C0068953 | 2025 PCB Light Replacement | 2025 ACE Plan | 2025 ACE Plan | 4225224.41 | 4225224.41 | 0
Awaiting Approval | Distribution | C0068954 | 2025 PCB Downline Device Sampling and Replacement | 2025 ACE Plan | 2025 ACE Plan | 1716718.39 | 1716718.39 | 0
Awaiting Approval | Transmission | C0068961 | 2025 PCB Substation Sampling and Replacement | 2025 ACE Plan | 2025 ACE Plan | 6650932.5 | 6650932.5 | 0
Awaiting Approval | Transmission | C0069227 | L6516 Replacements and Upgrades Phase 3 | 2025 ACE Plan | 2025 ACE Plan | 3104924.75 | 3104924.75 | 0
Awaiting Approval | Transmission | C0069231 | L8002 Replacements and Upgrades Phase 1 | 2025 ACE Plan | 2025 ACE Plan | 3093175.63 | 3093175.63 | 0
Awaiting Approval | Transmission | C0069232 | L6021 Replacements and Upgrades Phase 1 | 2025 ACE Plan | 2025 ACE Plan | 3253068.08 | 3253068.08 | 0
Awaiting Approval | Transmission | C0069238 | 2025/2026 Steel Tower Refurbishment | 2025 ACE Plan | 2025 ACE Plan | 2337250.27 | 2337250.27 | 0
Awaiting Approval | General Plant | C0069270 | 2025 SCADA/EMS Upgrade | 2025 ACE Plan | 2025 ACE Plan | 1306288.06 | 1306288.06 | 1096.73
Awaiting Approval | Transmission | C0070048 | L5027B Replacements and Upgrades Phase 1 | 2025 ACE Plan | 2025 ACE Plan | 2916727.9 | 2916727.9 | 0
Awaiting Approval | Distribution | C0070787 | 91W-411 Labelle Road Phase Extension | 2025 ACE Plan | 2025 ACE Plan | 1150615.99 | 1150615.99 | 0
Awaiting Approval | General Plant | C0070907 | MDR-8000 Microwave Radio Replacement | 2025 ACE Plan | 2025 ACE Plan | 1572477.91 | 1572477.91 | 0
Deferred | Generation | 48913 | HYD - Tusket Facility Refurbishment | 2025 ACE Plan (for Subsequent Approval) |  | 12972226.16 |  | 784368
Pending Submission | Transmission | C0011358 | New Bridgewater Substation | 2025 ACE Plan (for Subsequent Approval) |  | 18173046.53 |  | 52220.51
Awaiting Approval | Transmission | C0021140 | New 138KV-25KV Substation Stellarton | 2025 ACE Plan (for Subsequent Approval) | Q1 - May 16, 2025 | 10511998.19 | 12960396 | 2961645.32
Pending Submission | General Plant | C0021835 | IT - CIS Replacement | 2025 ACE Plan (for Subsequent Approval) |  | 77890770.6 |  | 2585795.72
Pending Submission | General Plant | C0032202 | Sydney T&D Depot Consolidation | 2025 ACE Plan (for Subsequent Approval) |  | 1879855.12 |  | 0
Pending Submission | Transmission | C0032382 | Susie Lake Substation Addition | 2025 ACE Plan (for Subsequent Approval) |  | 13954518.14 |  | 355691.62
Awaiting Approval | Transmission | C0041830 | Spare Power Production Unit Transformer | 2025 ACE Plan (for Subsequent Approval) | OTQ - April 7, 2025 | 1264622.46 | 1266552.19 | 7453.28
Filed by WTI | Transmission | C0044391 | Eastern Clean Energy Initiative (ECEI) - Transmission | 2025 ACE Plan (for Subsequent Approval) | OTQ - April 10, 2025 | 800229290.08 | 684685646 | 750860
Pending Submission | General Plant | C0047278 | IT - Oracle MDM Upgrade | 2025 ACE Plan (for Subsequent Approval) |  | 3010689.35 |  | 25899.98
Pending Submission | Transmission | C0053214 | 76W-T1 Transformer Replacement | 2025 ACE Plan (for Subsequent Approval) |  | 2279294.98 |  | 41732.14
Pending Submission | General Plant | C0053699 | Renewable to Retail Implementation | 2025 ACE Plan (for Subsequent Approval) |  | 5062652.18 |  | 4061322.08
Pending Submission | Generation | C0057361 | HYD - ANN Facility Isolation | 2025 ACE Plan (for Subsequent Approval) |  | 2899094.29 |  | 2545562.78
Pending Submission | Generation | C0059783 | HYD Upper Lake Falls 2 Overhaul | 2025 ACE Plan (for Subsequent Approval) |  | 1678152.72 |  | 4903.79
Awaiting Approval | General Plant | C0061284 | IT - OT Cyber Security Control Implementation | 2025 ACE Plan (for Subsequent Approval) | OTQ - March 3, 2025 | 5459312.92 | 6826426 | 1891234.44
Pending Submission | General Plant | C0061285 | IT - Enterprise Governance, Risk and Compliance | 2025 ACE Plan (for Subsequent Approval) |  | 1179857.28 |  | 241943.08
Pending Submission | Generation | C0061484 | PTMT - E-Crane Refurbishment | 2025 ACE Plan (for Subsequent Approval) |  | 2433080.5 |  | 82814.33
Pending Submission | Transmission | C0061552 | L6043 Replacements and Upgrades | 2025 ACE Plan (for Subsequent Approval) |  | 1346808.78 |  | 0
Less than $1M | General Plant | C0062624 | IT - Mobile Field Connectivity Enhancements | 2025 ACE Plan (for Subsequent Approval) |  | 1576633.03 |  | 559613.35
Awaiting Approval | Generation | C0063803 | HYD AVO 2 Access Road Stabilization | 2025 ACE Plan (for Subsequent Approval) | OTQ - April 7, 2025 | 2406283.37 | 1862825.78 | 155056.3
Pending Submission | Generation | C0067023 | LIN2 2024/25 Capacity Requirement | 2025 ACE Plan (for Subsequent Approval) |  | 1083800.37 |  | 1257127.05
Pending Submission | General Plant | C0067863 | IT - Managed Detect & Respond | 2025 ACE Plan (for Subsequent Approval) |  | 1126412.56 |  | 30870.53
Awaiting Approval | Generation | C0068566 | LIN DCS Upgrade 2025 | 2025 ACE Plan (for Subsequent Approval) | Q1 - May 16, 2025 | 1440910.59 | 1544190 | 18434
Pending Submission | Generation | C0068655 | LM6000 191-332 Hot Section Refurbishment | 2025 ACE Plan (for Subsequent Approval) |  | 6013453.54 |  | 198627.45
Pending Submission | General Plant | C0068714 | IT - Identity & Access Management | 2025 ACE Plan (for Subsequent Approval) |  | 1275524.12 |  | 246764.9
Pending Submission | General Plant | C0068718 | IT - DERMS Solution Project | 2025 ACE Plan (for Subsequent Approval) |  | 2993199.75 |  | 16701.63
Pending Submission | General Plant | C0068719 | IT - Distributed Intelligence Apps | 2025 ACE Plan (for Subsequent Approval) |  | 4353461.11 |  | 14868.3
Pending Submission | Generation | C0069166 | POT-Turbine Valve Refurbishment | 2025 ACE Plan (for Subsequent Approval) |  | 2872597.56 |  | 0
Pending Submission | Generation | C0070486 | HYD LGB Spillway Drawdown | 2025 ACE Plan (for Subsequent Approval) |  | 1288403.9 |  | 98292.97
Pending Submission | Distribution | C0071528 | FLISR Implementation | 2025 ACE Plan (for Subsequent Approval) |  | 5299247.73 |  | 6568.45
Pending Submission | Transmission | C0072808 | Synchronous Condensers (ECEI) | 2025 ACE Plan (for Subsequent Approval) |  | 243807241.41 |  | 118829.19
Pending Submission | Generation | C0061003 | POA LP HIP Turbine Refurbishment | 2025 ACE Plan (for Subsequent Approval) |  | 4155130.87 |  | 9775.5
Pending Submission | Generation | C0061005 | POA Cell Capping 2025 | 2025 ACE Plan (for Subsequent Approval) |  | 3255439.91 |  | 61594.92
Pending Submission | Generation | C0067906 | POA Boiler Refurbishment 2025 | 2025 ACE Plan (for Subsequent Approval) |  | 1213152.46 |  | 30232.92
Pending Submission | Generation | C0067908 | POA Boiler Refractory Refurbishment 2025 | 2025 ACE Plan (for Subsequent Approval) |  | 1089478.33 |  | 0
Approved | General Plant | C0011159 | Plant Information System Upgrade | 2024 ACE Plan (Less than $1M) | OTQ - March 3, 2025 | 362679 | 1142652 | 94091.25
Awaiting Approval | Distribution | C0042687 | 15N-202 Arthur St Conversion | 2022 ACE Plan (Less than $1M) | OTQ - April 7, 2025 | 718195 | 1399459 | 1196610.15
Awaiting Approval | Generation | C0049192 | HYD - GUL Generator Refurbishment | 2025 ACE Plan (Less than $1M) | Q1 - May 16, 2025 | 732043 | 1316589 | 7223.89
Awaiting Approval | Generation | C0068662 | TRE5 Baghouse Filter Replacement | 2025 ACE Plan (Less than $1M) | Q1 - May 16, 2025 | 534006 | 1241640 | 0
Awaiting Approval | Generation | C0073348 | HYD - WRC Surge Lake Volume Optimization | U&U | Q1 - May 16, 2025 | 0 | 1736278 | 0
Awaiting Approval | Generation | C0073965 | TRE5 U&U Burner Nest Waterwall Tube Replacement | U&U | Q1 - May 16, 2025 | 0 | 2156407 | 0

## R3 - Deferred or Cancelled
NS Power 2025 ACE Plan Items – Deferred or Cancelled
1st Quarter Overview - as of March 31, 2025
This report includes any deferred or cancelled projects that were included in the 2025 ACE Plan.
CI | Project Title | 2025 ACE Amount | 2025 ACE Project Total | Cancelled / Deferred | Deferred To | Prior Approval | 2025 ACE Plan Reference | Commentary
Generation
48913 | HYD - Tusket Facility Refurbishment | 1093904.18 | 12972226.16 | Deferred | 2026 |  | Subsequent Submittal | As condition assessments related to the Powerhouse continue, it has been determined that additional engineering is required to prepare the capital filing. Curent assessment indicates that this can safety be deferred to 2026.
C0020329 | TRE5 Stack Expansion Joint Replacement | 362990.64 | 395290.64 | Deferred | 2026 |  | Less than $1M | Through further scoping it was determined the risk could be mitigated in 2025 with additional monitoring and detection.
C0020331 | TRE5 Air Heater Expansion Joint Replacement | 354574.99 | 385221.99 | Deferred | 2026 |  | Less than $1M | Through further scoping it was determined the risk could be mitigated in 2025 with additional monitoring and detection.
C0061366 | TRE6 - Caustic Heater Heat Exchanger | 84017.17 | 91767.17 | Cancelled |  |  | Less than $1M | This project can be cancelled. Leak test on existing heat exhange bundle and gasket replacements mitigated risk and need for project.
C0068660 | TRE5 - Boiler Refurbishment 2025 | 825181.91 | 896931.91 | Cancelled |  |  | Less than $1M | This project can be cancelled as the scope of work will not be completed under C0073965 TRE5 U&U Burner Nest Waterwall Tube Replacement
C0030122 | LIN4 HIP Insulation Replacement | 106894.37 | 126233.95 | Deferred | 2026 |  | Less than $1M | Additional scoping found the condition of the insulation allows for this project to be deferred to 2026.
C0067945 | POA Pond Transfer Pumps | 367194.18 | 417194.18 | Deferred | 2026 |  | Pt. Aconi | Additional scoping found the condition of the transfer pumps allows for this project to be deferred to 2026.
C0060572 | TUC1 Secondary Air & Recirculation Damper Replacement | 77423.62 | 77423.62 | Cancelled |  |  | Less than $1M | This project can be cancelled, as the risk can be managed through 2026 and will also be completed as part of a major boiler upgrade on TUC1 which will begin in 2027.
C0068894 | TUC1 Gas Block Valve Upgrades | 607737.24 | 607737.24 | Cancelled |  |  | Less than $1M | This project can be cancelled, as the risk can be managed through 2026 and will also be completed as part of a major boiler upgrade on TUC1 which will begin in 2027.
C0069047 | TUC2 FD Fan Duct Refurbishment | 99940.12 | 99940.12 | Deferred | 2027 |  | Less than $1M | Further scoping showed that engineering was required to determine the final project requirements and that the risks could be managed through to 2027.
C0069567 | TUC1 - Boiler Cyclone Tube Replacements | 859647.29 | 859647.29 | Cancelled |  |  | Less than $1M | This project can be cancelled, as the risk can be managed through 2026 and will also be completed as part of a major boiler upgrade on TUC1 which will begin in 2027.
Transmission
C0041822 | WRC Spare Cable Replacement & Storage System | 50000 | 189341.81 | Deferred | 2026 |  | Less than $1M | Additional engineering is required before project can progress to construction.
Distribution
General Plant
C0071652 | IT - ZTN Security and Restrictive Network Controls | 725124.01 | 869124.01 | Cancelled |  |  | Less than $1M | Scope of this project included in C0061289 - IT - Network Next Generation Security Design.

## R4 - FIN Report
NS Power Final Cost Report
1st Quarter Overview - as of March 31, 2025
This report includes a list of all FIN capital work orders that have fallen outside the timelines under the CEJC. (Within six months of in-service.)
These projects have either been completed and are outside the FIN tolerances or forecast to be outside of the FIN tolerances. (The greater of +/- 5% or +/- $250,000.)
Projects that have been in-service for 6 months, but have a project forecast within the allowed FIN tolerance, are not included on this list.
Project # | Project | In-service Date | NSEB Approval | Spend to March 31, 2025 | Comment
C0017098 | RAL Generator Replacement | 2019-12-31 | 2229266.75 | 1671461.07 | This project is now complete and a Final Cost Application is planned for submission in 2025.
C0031145 | 2021 Padmount Replacement Program | 2021-03-31 | 1636152.76 | 1166366.12 | This project is now complete and a Final Cost Application is planned for submission in 2025.
51956 | 6P Mobile Substation Rewind | 2019-01-31 | 1516120.57 | 1056955.81 | This project is now complete and a Final Cost Application is planned for submission in 2025.
49790 | L5505 Replacements and Upgrades | 2020-05-31 | 1223571.35 | 816588.04 | This project is now complete and a Final Cost Application is planned for submission in 2025.
C0041805 | L7005 Replacements and Upgrades Phase 2 | 2022-09-30 | 3182518.11 | 2910451.19 | This project is now complete and a Final Cost Application is planned for submission in 2025.
52314 | 1C-GT1/UT1 Replacement | 2020-11-30 | 2032393 | 1678006.2 | This project is now complete and a Final Cost Application is planned for submission in 2025.
C0030984 | IT- Cisco UCS Lifecycle | 2024-02-14 | 2456609.31 | 2088998.46 | This project is now complete and a Final Cost Application is planned for submission in 2025.
C0042166 | IT - Data Loss Prevention (DLP) Platform | 2023-11-30 | 4261239.1945 | 3944009.61 | This project is now complete and a Final Cost Application is planned for submission in 2025.
C0043010 | 2022/2023 Wood Pole Retreatment Program | 2022-09-30 | 1300037.21 | 791054.43 | This project is now complete and a Final Cost Application is planned for submission in 2025.
C0010778 | Smart Grid Nova Scotia Project | 2020-05-31 | 7053622 | 6409573.21 | This project is now complete, however, final costs are dependent on final asset disposition treatment under the SGNS Asset Disposition proceeding (M12178).