## IR-14 Comparison
| Current Estimate | [5 empty] | Original Estimate
[12 empty] | Variance | Variance Explanation
| Regular Labour | [5 empty] | Regular Labour |  |  |  |  | Current - Original
| SM Electrician | PD | 420 | 434 | 182280 |  | SM Electrician | PD | 922 | 450 | 414900 | -232620 | For current estimate reduced quantity of SM Electrician days due to duplication in original estimate and a minor reduction in expected reduction in days required based on RTUs completed to date
| Engineering | PD | 861 | 452 | 389172 |  | Engineering | PD | 648 | 457 | 296136 | 93036 | Current estimate has slight increase in engineering days estimate due to expected increase in days based on RTUs done to date. Current estimate also includes SCADA engineering ($22,100) from original estimate
| Telecontrol Technologist | PD | 364 | 375 | 136500 |  | Telecontrol Technologist | PD | 295 | 450 | 132750 | 3750 | Current estimate has slight increase in telecontrol technologist engineering days estimate due to expected increase in days based on RTUs done to date and assistance to PM with material management functions
| PLT - Field Resources | PD | 280 | 444 | 124320 |  | PLT - Field Resources | PD | 230 | 450 | 103500 | 20820 | Current estimate has slight increase in expected days required for PLT Field Resources for commissioning phase
| Drafting SME CADD | PD | 70 | 375 | 26250 |  | Drafting SME CADD | PD | 130 | 425 | 55250 | -29000 | Current estimate has decrease in Drafting CADD days estimate based on expected reduction in CADD days required due to improved quality assurance practices during design phase
| PM | PD | 350 | 452 | 158200 |  | PM | PD | 600 | 450 | 270000 | -111800 | Current estimate has decrease in Project Manager (PM) days estimate as the PM was determined not to be needed on a full time basis and has the capability to manage additional work outside this project.
[7 empty] | SCADA | PD | 52 | 425 | 22100 | -22100 | For current estimate SCADA engineering is included in Engineering above
0
|  |  |  | Sub-Total | 1016722 |  |  |  |  | Sub-Total | 1294636 | -277914
0
| Term Labour | [5 empty] | Term Labour |  |  |  |  | 0
| RTU Technician | PD | 630 | 434 | 273420 |  | RTU Technician | PD | 1090 | 425 | 463250 | -189830 | For current estimate reduced quantity of RTU Technician hours due to a duplication in original estimate, partially offset by an increased quantity of PDs expected based on RTUs completed to date.
0
0
| Overtime Labour | [5 empty] | Overtime Labour |  |  |  |  | 0
| Electrician/Technician | PD | 112 | 869 | 97328 |  | Electrician/Technician | PD | 20 | 900 | 18000 | 79328 | Increase in expected overtime based on RTUs done to date
| PLT | PD | 28 | 869 | 24332 |  | PLT | PD | 0 | 900 | 0 | 24332 | For current estimate added PLT overtime to cover for the commissioning phase, based on RTUs completed to date.
0
|  |  |  | Sub-Total | 121660 |  |  |  |  | Sub-Total | 18000 | 103660
0
| Contracts | [5 empty] | Contracts |  |  |  |  | 0
| Electrical Engineering Technologist | Days | 352 | 900 | 316800 |  | Electrical Engineering Technologist | Days | 546 | 900 | 491400 | -174600 | For current estimate reduced the expected days required for external engineering technologist due to some work being completed by internal engineering resources
| Civil Construction | Days | 100 | 1430 | 143000 |  | Civil Construction | Days | 156 | 1430 | 223080 | -80080 | For current estimate reduced the estimated civil construction cost because only half of the sites require civil construction. This is partially offset by one of the sites requiring significant more effort for civil construction
0
|  |  |  | Sub-Total | 459800 |  |  |  |  | Sub-Total | 714480 | -254680
0
| Travel Expense | [5 empty] | Travel Expense |  |  |  |  | 0
| Misc. Travel - Accomodation | Lot | 1 | 85050 | 85050 |  | Misc. Travel | Lot | 1 | 117150 | 117150 | -32100 | For the current estimate the rental vehicle costs are shown separately. There is an overall slight increase in estimated travel costs
| Rental Vehicle | Lot | 1 | 33992 | 33992 |  | Rental Vehicle | Lot | 0 |  | 0 | 33992 | In the original estimate the rental vehicle cost was included in Misc. Travel expenses
0
|  |  |  | Sub-Total | 119042 |  |  |  |  | Sub-Total | 117150 | 1892
0
| Meals & Entertainment | [5 empty] | Meals & Entertainment |  |  |  |  | 0
| Living Expenses (Meals) | Lot | 1 | 25200 | 25200 |  | Living Expenses (Meals) | Units | 378 | 40 | 15120 | 10080 | Updated to reflect the expenses incurred on the first two RTU sites.
|  |  |  | Sub-Total | 25200 |  |  |  |  | Sub-Total | 15120 | 10080
0
0
| Materials - Misc listing | [5 empty] | Materials - Misc listing |  |  |  |  | 0
| RTUs | Ea | 14 | 96051 | 1344714 |  | RTUs | Ea | 14 | 70664 | 989296 | 355418 | In the current estimate the unit cost estimate for RTUs is increased based on quoted cost of RTUs. Refer to C0051815 Midgard IR-3 Attachment 1 for more details.
| Cable and Accessories | Ea | 14 | 8000 | 112000 |  | Cable and Accessories | Ea | 14 | 8000 | 112000 | 0
| Power Meters | Ea | 7 | 4700 | 32900 |  | Power Meters | Ea | 14 | 5170 | 72380 | -39480 | In the current estimate the quantity of power meters is reduced as it was determined that power meters are required at 7 sites not 14. Refer to C0051815 Midgard IR-3 Attachment 1 for more details.
| Test Equipment and Tools | Lot | 1 | 10000 | 10000 |  | Test Equipment and Tools | Lot | 1 | 11000 | 11000 | -1000 | Slight reduction in current estimate for tools and test equipment
[5 empty] | 1499614 | [5 empty] | 1184676 | 314938
0
|  |  |  | Sub-Total | 1499614 |  |  |  |  | Sub-Total | 1184676 | 314938
0
| Vehicle Overhead | [5 empty] | Vehicle Overhead |  |  |  |  | 0
| Vehicle T&D Labour Regular AO | lot |  |  | 391564.41 |  | Vehicle T&D Labour Regular AO | lot |  |  | 650565 | -259000.59 | Overall internal labour is lower so correspondingly vehicle overhead is lower
[5 empty] | 0 | [5 empty] | 0 | 0
|  |  |  | Sub-Total | 391564.41 |  |  |  |  | Sub-Total | 650565 | -259000.59
0
| Contingency (10% of Forecast) | [5 empty] | Contingency (10% of Forecast) |  |  |  |  | 0
| Contingency |  | 10% | 3515458 | 351545.8 |  | Contingency |  | 10% | 3807312 | 380731.2 | -29185.4 | Overall estimate is lower so correspondingly the 10% contingency is lower
0
|  |  |  | Sub-Total | 351545.8 |  |  |  |  | Sub-Total | 380731.2 | -29185.4
0
| Interest Capitalized | [5 empty] | Interest Capitalized |  |  |  |  | 0
| Interest | lot | 1 |  | 7888.57 |  | Interest | lot | 1 |  | 17848 | -9959.43 | Overall estimate is lower so correspondingly the interest capitalized is lower
0
|  |  |  | Sub-Total | 7888.57 |  |  |  |  | Sub-Total | 17848 | -9959.43
0
| Administrative Overhead | [5 empty] | Administrative Overhead |  |  |  |  | 0
| Labour AO |  |  |  | 735271.67 |  | Labour AO |  |  |  | 1000498 | -265226.33 | Overall internal labour is lower so correspondingly administrative overhead is lower
| Contractor AO |  |  |  | 57235.15 |  | Contractor AO |  |  |  | 103533 | -46297.85 | Overall contract labour is lower so correspondingly contractor overhead is lower
|  |  |  | Sub-Total | 792506.82 |  |  |  |  | Sub-Total | 1104031 | -311524.18
0
SUB-TOTAL (no AO, AFUDC) |  |  |  |  | 3867003.8 | SUB-TOTAL (no AO, AFUDC) |  |  |  |  | 4188043.2 | -321039.4
TOTAL (AO, AFUDC included) |  |  |  |  | 5058963.6 | TOTAL (AO, AFUDC included) |  |  |  |  | 5960487.2 | -901523.6