## Sheet1
Risk Rankings for Build to Roadside Projects
Feeder Source | Feeder Section | Feeder Criticality | Feeder Condition | Feeder Risk | Adjusted Condition | Adjusted Project Risk | Key Risk Factors
100C-421 | 100C-421 | 4 | 5 | 20 | 5 | 20 | This project has some deteriorated poles and wire that will be brought to roadside.
103C-314 | 103C-314 | 4 | 4 | 16 | 5 | 20 | This project has some deteriorated poles and wire that will be brought to roadside.
126H-312 | 126H-312 | 4 | 5 | 20 | 5 | 20 | This project work is driven by the department of public works and as part of the realignment the poles will be brought to roadside.
131H-422 | 131H-422 | 5 | 4 | 20 | 5 | 25 | This project has some deteriorated poles and wire that will be brought to roadside.
19C-204 | 19C-204 | 3 | 3 | 9 | 5 | 15 | This project involves a conversion as well as moving the deteriorated poles and wire to roadside.
37N-413 | 33N-201 | 5 | 3 | 15 | 5 | 25 | This project will removes a PCB potential stepdown while also bringing a deteriorated section of line to roadside.
73W-411 | 512W-311 | 5 | 5 | 25 | 5 | 25 | This project is to improve the loading on the 512W-311 feeder section. The phases on 512W-311 are overloaded making it difficult to maintain voltages within the standard range. Through the execution of this work there is an off-road section that will was moved to roadside.
85S-401 | 85S-401 | 5 | 5 | 25 | 5 | 25 | The targeted off-road sections of 85S-401 are deteriorated and at risk of failure due to its age and condition. The reduced accessibility of the existing off-road sections limits Nova Scotia Power’s ability to maintain it and respond to outages in a timely manner.