## R1 - Summary
NS Power 2025 Capital Spend Detail - As per 2025 ACE Plan
3rd Quarter Overview - as of September 30, 2025
| Generation | Distribution | Transmission | General Property | Total NS Power
2025 ACE Plan Total
2025 Submitted ACE Total | 188123238.18 | 182568886.69 | 256543819.14 | 65139528.19 | 692375472.2
Total YTD Spend* | 155296276.5029 | 147490649.4601 | 112532563.2901 | 46718693.4816 | 462038182.7346
Variance YTD/ACE Spend | -32826961.6771 | -35078237.2299 | -144011255.8499 | -18420834.7084 | -230337289.4654
Percentage of ACE Spent as of September 30, 2025 | 82.55% | 80.79% | 43.86% | 71.72% | 66.73%
Add:
ATOs | 1048240 | 0 | 3256426.96 | 0 | 4304666.96
U&Us/P&As | 6703770.18 | 1256042 | 0 | 1493832 | 9453644.18
Changes to ACE Items for Subsequent Approval** | 17405672.4057 | -382505 | -21069355.21 | 9510868.29 | 5464680.4857
Total Increase | 25157682.5857 | 873537 | -17812928.25 | 11004700.29 | 19222991.6257
Less:
Projects cancelled | -5210407.76 | 0 | 0 | -725124.01 | -5935531.77
Projects deferred | -6386569.53 | -322773.58 | -36518252.97 | -11123068.95 | -54350665.03
Total Decrease | -11596977.29 | -322773.58 | -36518252.97 | -11848192.96 | -60286196.8
2025 Potential Capital Spend*** | 201683943.4757 | 183119650.11 | 202212637.92 | 64296035.52 | 651312267.0257
*Total YTD Transmission spend includes ($11M) of proceeds received from WTI for the transfer of pre-2025 development costs transferred to Wasoqonatl Transmission Inc. (WTI) for CI C0044391 NS-NB Reliability Tie.
**The Changes to ACE Items for Subsequent Approval amount listed under Transmission includes the removal of C0044391 that was filed on April 10, 2025 by Wasoqonatl Transmission Inc.
*** Amounts do not reflect the reforecast of capital projects since the 2025 ACE Plan submission, or reforecasting of subsequent items filed.

## R2 - Capital Items Status
NS Power Capital Item Status Update
3rd Quarter Overview - as of September 30, 2025
This report includes all projects submitted to the NSEB and remain active, as well as ACE Plan subsequent submittal projects. Projects are removed from this report once the project has been final costed (internal or external), cancelled, or falls below $1M.
Status | Category | CI Number | Title | ACE Plan Reference (or U&U and P&A) | Submission/Date | ACE Amount | Submission or Approved Amount | Actual Spend | FIN Submission Date | FIN Amount | Variance
Less than $1M | General Plant | C0061285 | IT - Enterprise Governance, Risk and Compliance | 2025 ACE Plan (for Subsequent Approval) |  | 1179857.28 |  | 256112.37
Deferred | Generation | 39472 | HYD - Mersey Redevelopment Phase 1 | 2022 ACE Plan (for Subsequent Approval) |  | 189447075.51 |  | 20987832.58
Awaiting Approval | General Plant | 47751 | ECC Dynamic Line Rating Implementation | 2022 ACE Plan (for Subsequent Approval) | OTQ - December 1, 2025 | 5144525.08 | 2148364 | 5486323.43
Approved | Generation | 49634 | HYD - Trout River Diversion Structure Replacement | 2022 ACE Plan (for Subsequent Approval) | Q1 - May 13, 2024 | 1822299.7 | 3402776 | 3309527.68
Approved | Distribution | C0008638 | Cogswell HRM Redevelopment Program | 2022 ACE Plan (for Subsequent Approval) | OTQ - June 6, 2022 | 6982854.44 | 6617148.24 | 6076172.27
Approved | Transmission | 43267 | 13V Gulch Hydro Replace 13V-GT1 and 13V-VR1 | 2015 ACE Plan | 2015 ACE Plan | 1061901.92 | 1061901.92 | 1011993
Awaiting Approval | Transmission | 52314 | 1C-GT1/UT1 Replacement | 2018 ACE Plan | 2018 ACE Plan | 2032393 | 2032393 | 1678006 | OTQ - December 1, 2025 | 1678006 | -354387
Approved | Transmission | 49815 | 2017 / 2018 Steel Tower Refurbishment | 2017 ACE Plan | 2017 ACE Plan | 2003316.81 | 2003316.81 | 1937433
Approved | Distribution | 49919 | 2017 PCB Pole Top Transformer Replacement | 2017 ACE Plan | 2017 ACE Plan | 2446051.2 | 2446051.2 | 2550603
Approved | Distribution | 51493 | 2018 PCB Pole Top Transformer Replacement | 2018 ACE Plan | 2018 ACE Plan | 1360354 | 1360354 | 1384291.97
Approved | Transmission | 51403 | 2018 PCB Removal Program | 2018 ACE Plan | 2018 ACE Plan | 4402342 | 4402342 | 3533869.48
Approved | Transmission | 52258 | 2018/2019 Isolated Structure Replacement | 2018 ACE Plan | 2018 ACE Plan | 4818521 | 4818521 | 294849
Approved | Transmission | 51398 | 2018/2019 Steel Tower Refurbishment | 2018 ACE Plan | 2018 ACE Plan | 1992692 | 1992692 | 2055803.96
Approved | Distribution | 47787 | 2H Armdale New Feeders | 2017 ACE Plan (for Subsequent Approval) | OTQ - April 6, 2020 | 1285679 | 1734221 | 1723920
Approved | Transmission | 52328 | 56N-T1 Transformer Upgrades | 2018 ACE Plan | 2018 ACE Plan | 1279271 | 1279271 | 1307910
Approved | Transmission | 51975 | 5P Mobile Substation Replacement | 2018 ACE Plan | 2018 ACE Plan | 4829458 | 4829458 | 2970054.74
Awaiting Approval | Transmission | 51956 | 6P Mobile Substation Rewind U&U | U&U | Q3 2017 - October 30, 2017 | 0 | 1516120.57 | 635776 | OTQ - December 1, 2025 | 635776 | -880344.57
Approved | Distribution | 47124 | Advanced Metering Infrastructure | 2017 ACE Plan (for Subsequent Approval) | OTQ - February 17, 2023 | 8274738 | 143495843.8622 | 142777897.12
Approved | Generation | 48914 | HYD - Malay Falls Facility Repair | 2017 ACE Plan (for Subsequent Approval) | Q3 2017 - October 30, 2017 | 446237 | 1034045 | 1101869.02
Approved | Generation | 47551 | HYD - SHH Controls Upgrade | 2016 ACE Plan (for Subsequent Approval) | Q4 2015 - January 29, 2016 | 1092850.61 | 1749212 | 1955374
Deferred | Generation | 49942 | HYD - Tidewater Facility Refurbishment | 2018 ACE Plan | 2018 ACE Plan | 1234178 | 1234178 | 914558.47
Withdrawn | Generation | 29807 | HYD - Tusket Falls Main Dam | 2017 ACE Plan (for Subsequent Approval) | OTQ - July 23, 2021 | 9940664 | 36826119 | 25568900.73
Approved | Generation | 51234 | HYD - WRC HVAC Upgrade | 2018 ACE Plan | 2018 ACE Plan | 1876537 | 1876537 | 1880426.49
Approved | Generation | 48791 | HYD - WRC Safety Standards Upgrades | 2018 ACE Plan (for Subsequent Approval) | OTQ - June 4, 2018 | 1019927.73 | 1760570 | 1919441
Approved | Generation | 51236 | HYD - WRC Tailrace Rock Bolting | 2018 ACE Plan | 2018 ACE Plan | 8861996 | 8861996 | 7664783.64
Approved | Generation | 48052 | HYD Annapolis HVAC Upgrade | 2017 ACE Plan (for Subsequent Approval) | OTQ - March 8, 2017 | 1498367 | 1573596 | 1987326.18
Approved | Generation | 44978 | HYD-Wreck Cove Automation | 2015 ACE Plan (for Subsequent Approval) | Q2 2015 - July 31, 2015 | 2379999.4 | 3802446.04 | 4026586.47
Deferred | General Plant | 49600 | IT - Network Architecture Redesign | 2017 ACE Plan (for Subsequent Approval) |  | 1183826 |  | 0
Approved | General Plant | 49855 | IT Desktop SW Modernization | 2017 ACE Plan (for Subsequent Approval) | Q3 2017 - October 30, 2017 | 2013034 | 4620515.89 | 4501621
Approved | Transmission | 47950 | L5017 Replacements & Upgrades | 2016 ACE Plan | Q1 2018 - May 7, 2018 | 2182142.33 | 3062664 | 3012632
Approved | Transmission | 47949 | L5028 Replacements and Upgrades | 2016 ACE Plan | 2016 ACE Plan | 1144354.64 | 1144354.64 | 943264.93
Approved | Transmission | 49790 | L5505 Replacements and Upgrades | 2017 ACE Plan | 2017 ACE Plan | 1223571.35 | 1223571.35 | 816588 | OTQ - June 9, 2025 | 816588 | -406983.35
Approved | Transmission | 49778 | L5535 Replacements and Upgrades | 2017 ACE Plan | OTQ - April 16, 2018 | 1261920.05 | 2590269 | 2837177
Approved | Transmission | 49779 | L6537 Replacements and Upgrades | 2018 ACE Plan | OTQ - March 4, 2019 | 1255220 | 2331474.13 | 2284616
Approved | Transmission | 52320 | L6549 2018 Replacements & Upgrades | 2018 ACE Plan | 2018 ACE Plan | 1406535 | 1406535 | 1452523
Approved | Transmission | 44987 | L7003 Lidar Upgrades | 2015 ACE Plan (for Subsequent Approval) | OTQ - August 31, 2015 | 6885816.76 | 11032275 | 10907019.2
Approved | Transmission | 49793 | L7011 Replacements and Upgrades | 2017 ACE Plan | OTQ - April 1, 2019 | 3343484.22 | 4810276 | 4591706
Approved | Transmission | 47954 | L7012 Replacements and Upgrades | 2017 ACE Plan | 2017 ACE Plan | 4428519.78 | 4428519.78 | 4392086
Approved | Generation | 49940 | LM6000 TUC5 Control System Upgrade | 2017 ACE Plan (for Subsequent Approval) | OTQ - July 3, 2018 | 1018769 | 1275559 | 1070506
Approved | Transmission | C0001900 | Mount Hope 69-25kV Substation | 2018 ACE Plan | 2018 ACE Plan | 2982338 | 2982338 | 2998217.51
Approved | Transmission | 52323 | Port Hastings 2C BPS Upgrade | P&A | Q2 - August 7, 2018 | 0 | 4201448.53 | 3997958
Approved | General Plant | 50153 | Self Serve Development Phase 2 | 2017 ACE Plan (for Subsequent Approval) | OTQ - September 15, 2017 | 1827720 | 1160528 | 1316269
Not Approved at this time | Transmission | 43678 | Separate L8004/L7005 on Canso Crossing Double Circuit Tower(DCT) | 2017 ACE Plan (for Subsequent Approval) | OTQ - January 27, 2022* | 16183691 | 20387278 | 20387278
Not Approved at this time | Transmission | 45066 | Upgrade L6511 and L7019 Thermal Rating | 2015 ACE Plan (for Subsequent Approval) | OTQ - January 27, 2022* | 3693032.91 | 2691017 | 2691017
Not Approved at this time | Transmission | 43324 | Replace L6513 / Upgrade Line Terminals | 2015 ACE Plan (for Subsequent Approval) | OTQ - January 27, 2022* | 23429902 | 18626428 | 18625082
Not Approved at this time | Transmission | 45067 | 67N Onslow 345 KV Node Swap | 2014 ACE Plan (for Subsequent Approval) | OTQ - January 27, 2022* | 3006487 | 2982714 | 2982585
Approved | Transmission | 48022 | Spider Lake Substation Addition | 2016 ACE Plan (for Subsequent Approval) | OTQ - March 4, 2019 | 6348980.72 | 9158260 | 9066398
Approved | Generation | 50518 | HYD - Ruth Falls Main Dam Refurbishment | 2019 ACE Plan | OTQ - October 11, 2024 | 7244422 | 14839116 | 7384252.55
Approved | Transmission | C0010042 | 2019 Transmission Right-of-Way Widening 69kV | 2019 ACE Plan | 2019 ACE Plan | 5650794 | 5650794 | 5634125
Approved | Transmission | C0010948 | 2019/2020 Sacrificial Anode Installation Program | 2019 ACE Plan | 2019 ACE Plan | 3099862 | 3099862 | 3244208
Approved | Transmission | C0010952 | 2019/2020 Substation Polychlorinated Biphenyl (PCB) Equipment Removal | 2019 ACE Plan | 2019 ACE Plan | 2786245 | 2786245 | 2792347.32
Approved | Transmission | C0010949 | 2019/2020 Steel Tower Life Extension | 2019 ACE Plan | 2019 ACE Plan | 2414140 | 2414140 | 2178231
Approved | Transmission | C0011339 | L6549 - Replacements and Upgrades Phase 2 | 2019 ACE Plan | Q1 - May 13, 2024 | 2209907 | 3993973.66 | 3904480.74
Approved | Transmission | C0011241 | L5026 - Replacements and Upgrades | 2019 ACE Plan | 2019 ACE Plan | 1498789 | 1498789 | 1379563
Approved | Transmission | C0010978 | 2019/2020 Transmission Switch & Breaker Replacement | 2019 ACE Plan | 2019 ACE Plan | 1044148 | 1044148 | 1029498
Approved | Transmission | C0011243 | L5551 - Replacements and Upgrades | 2019 ACE Plan | 2019 ACE Plan | 1014077 | 1014077 | 1115386
Approved | Distribution | C0011208 | 2019 Padmount Replacement Program | 2019 ACE Plan | 2019 ACE Plan | 1413544 | 1413544 | 1464939.76
Approved | Distribution | C0006319 | 2019 PCB Pole Top Transformer Replacements | 2019 ACE Plan | 2019 ACE Plan | 1177592 | 1177592 | 1456958.69
Approved | General Plant | C0013438 | IT - T&D WAM Phase 1 - GIS and Field Design System | 2019 ACE Plan (2018 Pending Submission) | OTQ - December 7, 2018 | 7978434 | 7978434 | 8098333
Partial Approval | Generation | C0013838 | HYD WRC LEM Unit Rehabilitation | 2020 ACE Plan (2019 Pending Submission) | OTQ - February 21, 2020 | 109691966.51 | 101787264 | 103396872.33
Approved | Distribution | 47794 | Heckman's Island Submarine Cable Replacement | 2021 ACE Plan (for Subsequent Approval) | Q1 2021 - May 3, 2021 | 1296112.43 | 1338363.88 | 1554832.58
Approved | General Plant | C0011378 | Route Network Upgrades | 2020 ACE Plan (2019 Pending Submission) | OTQ - December 2, 2019 | 5724239.86 | 5717751.93 | 6008798.07
Approved | General Plant | 49480 | IT - Data Centre Disaster Recovery | 2020 ACE Plan (2019 Pending Submission) | OTQ - December 2, 2019 | 6103797.71 | 6335161.85 | 6249505
Approved | General Plant | C0010838 | MCC - HVAC Replacement | 2019 ACE Plan (for Subsequent Approval) | OTQ - October 4, 2021 | 1071364 | 1606253.82 | 1531910
Approved | General Plant | C0002137 | ECC - Map Board and Technology Modernization | 2019 ACE Plan (for Subsequent Approval) | Q3 - November 4, 2019 | 2568789 | 2506267.89 | 2274318
Approved | Transmission | C0021105 | L7002 Replacements and Upgrades Phase 2 | P&A | Q3 - November 4, 2019 | 0 | 3121441.58 | 3320027
Approved | Distribution | C0020623 | New Distribution Rights-of-Way Phase 5 | 2020 ACE Plan | 2020 ACE Plan | 10015266.14 | 10015266.14 | 9930358
Approved | Transmission | C0020627 | 2020 Transmission Right-of-Way Widening 69kV | 2020 ACE Plan | 2020 ACE Plan | 5489820 | 5489820 | 5617282
Approved | Transmission | C0011261 | 101W Port Mersey Substation Expansion | 2020 ACE Plan | 2020 ACE Plan | 4651384 | 4651384 | 4707039.52
Approved | Transmission | C0021123 | 2020/2021 Substation Polychlorinated Biphenyl (PCB) Equipment Removal | 2020 ACE Plan | 2020 ACE Plan | 5197371.63 | 5197371.63 | 5482882.42
Approved | Generation | 49949 | LM6000 TUC4 Control System Replacement | 2020 ACE Plan | 2020 ACE Plan | 1149996.27 | 1149996.27 | 901766
Approved | Transmission | C0011321 | L5031 Replacements and Upgrades Phase 1 | 2020 ACE Plan | 2020 ACE Plan | 2147211.75 | 2147211.75 | 368504.93
Approved | Transmission | C0021107 | L8001 Replacements and Upgrades Phase 1 | 2020 ACE Plan | 2020 ACE Plan | 2292092.86 | 2292092.86 | 2517260
Approved | Distribution | C0020835 | 2020 Padmount Replacement Program | 2020 ACE Plan | 2020 ACE Plan | 1612389.23 | 1612389.23 | 1518893.41
Approved | Transmission | C0021122 | 2020/2021 Transmission Switch & Breaker Replacement | 2020 ACE Plan | 2020 ACE Plan | 1312642.8 | 1312642.8 | 1518309.9
Approved | Distribution | C0020834 | 2020/2021 Inaccessible PCB Transformer Replacements | 2020 ACE Plan | 2020 ACE Plan | 2950294.39 | 2950294.39 | 3103289.14
Approved | General Plant | C0021109 | New RTU Deployment Project | 2020 ACE Plan | 2020 ACE Plan | 8028097.17 | 8028097.17 | 7447876.27
Approved | Transmission | 52303 | L7019 Replacements and Upgrades | 2020 ACE Plan | 2020 ACE Plan | 1374091.91 | 1374091.91 | 1383196
Approved | Transmission | C0021026 | Willow Lane 15N-T3 Replacement | 2020 ACE Plan | 2020 ACE Plan | 1326646.57 | 1326646.57 | 1179586
Approved | Generation | 49756 | HYD - Marshall Falls Main Dam Refurbishment | 2020 ACE Plan | 2020 ACE Plan | 5452793.82 | 5452793.82 | 627328.76
Approved | Transmission | C0021142 | 19W-T51 Transformer Replacement | 2020 ACE Plan | 2020 ACE Plan | 1512336.33 | 1512336.33 | 1473279
Approved | Distribution | C0021182 | 93V-313-Meteghan Rebuild | 2020 ACE Plan | 2020 ACE Plan | 1075624.51 | 1075624.51 | 927225
Approved | Distribution | C0010778 | Smart Grid Nova Scotia Project | 2020 ACE Plan (for Subsequent Approval) | OTQ - December 5, 2019 | 6740589.05 | 7053622 | 6409669.6
Approved | Distribution | C0019379 | 50N-410 - 4C-430 Highway 104 Twinning | 2020 ACE Plan (for Subsequent Approval) | OTQ - June 1, 2020 | 1361237.37 | 1137222.61 | 1228682
Approved | General Plant | C0023622 | AMO Substation and Transmission APM Program | 2020 ACE Plan (for Subsequent Approval) | OTQ - April 6, 2020 | 2087848.28 | 2217589 | 2369151
Partial Approval | Generation | C0014218 | HYD WRC LEM Balance of Plant | 2021 ACE Plan (2020 Pending Submission) | OTQ - April 30, 2021 | 21186378.42 | 27637896 | 20352612.65
Approved | General Plant | C0023623 | AMO Distribution APM Program | 2020 ACE Plan (for Subsequent Approval) | OTQ - April 6, 2020 | 1708239.85 | 1721484.45 | 1817941.9
Approved | Generation | 16374 | HYD Gaspereau Dam Safety | 2008 ACE Plan | OTQ - February 23, 2020 | 4354889 | 22703451 | 12443594.05
Approved | General Plant | C0017098 | Ragged Lake Generator Replacement | P&A | Q2 2020 - August 4, 2020 | 0 | 2229266.75 | 1681714 | OTQ - July 7, 2025 | 1681714 | -547552.75
Approved | Distribution | C0031083 | New Distribution Rights-of-Way Phase 6 | 2021 ACE Plan | 2021 ACE Plan | 9762734.52 | 9762734.52 | 9705373
Approved | Transmission | C0031263 | 2021/2022 Substation Polychlorinated Biphenyl (PCB) Equipment Removal | 2021 ACE Plan | 2021 ACE Plan | 7512225.73 | 7512225.73 | 7055536.3
Approved | Transmission | C0031089 | 2021/2022 Transmission Right-of-Way Widening 69kV | 2021 ACE Plan | 2021 ACE Plan | 5288520 | 5288520 | 5512846
Approved | Transmission | C0031122 | L6539 Replacements and Upgrades | 2021 ACE Plan | OTQ - April 7, 2025 | 2821842.28 | 5584042.12 | 1377454.67
Approved | Transmission | C0031085 | L6516 Line Replacement and Upgrades | 2021 ACE Plan | 2021 ACE Plan | 2730591.81 | 2730591.81 | 2544186.79
Approved | Transmission | C0031050 | New Spare Large Autotransformer | 2021 ACE Plan | 2021 ACE Plan | 2398564.03 | 2398564.03 | 2374092.17
Approved | Transmission | C0033644 | 2021/2022 Steel Tower Life Extension | 2021 ACE Plan | 2021 ACE Plan | 2332745.87 | 2332745.87 | 1830762.35
Approved | Transmission | C0033645 | 2021/2022 Steel Tower Refurbishment | 2021 ACE Plan | 2021 ACE Plan | 1944004.84 | 1944004.84 | 2205105.35
Approved | Distribution | C0031145 | 2021 Padmount Replacement Program | 2021 ACE Plan | 2021 ACE Plan | 1636152.76 | 1636152.76 | 1176603.75
Approved | Transmission | C0031262 | 2020/2021 Transmission Switch and Breaker Replacement | 2021 ACE Plan | 2021 ACE Plan | 1483047.6 | 1483047.6 | 1456359.54
Approved | Transmission | C0031064 | L5054 Replacements and Upgrades | 2021 ACE Plan | 2021 ACE Plan | 1134737.48 | 1134737.48 | 996871.68
Approved | Generation | 46483 | CT - TUS Control System Upgrade | 2021 ACE Plan | 2021 ACE Plan | 1046322.12 | 1046322.12 | 1093242.4
Approved | Generation | C0026285 | TRE Heavy Fuel Oil Tank Refurbishment | 2021 ACE Plan (for Subsequent Approval) | OTQ - June 10, 2021 | 1732920.72 | 2979545.51 | 2474844.07
Approved | General Plant | C0030987 | IT - NERC CIP Environment Refresh | 2022 ACE Plan (2021 Pending Submission) | OTQ - March 7, 2022 | 1446131 | 1259927 | 1309292.92
Approved | Distribution | C0041892 | New Distribution Rights-of-Way Phase 7 | 2022 ACE Plan | 2022 ACE Plan | 9854290.53 | 9854290.53 | 10221584
Approved | Transmission | C0041893 | 2022/2023 Transmission Right-of-Way Widening 69kV | 2022 ACE Plan | 2022 ACE Plan | 5312315 | 5312315 | 5187078
Approved | Transmission | C0041837 | 2022/2023 Substation Polychlorinated Biphenyl (PCB) Equipment Removal | 2022 ACE Plan | 2022 ACE Plan | 3805434.21 | 3805434.21 | 4100263.58
Approved | Transmission | C0041793 | L7002 Replacements and Upgrades Phase 2 | 2022 ACE Plan | 2022 ACE Plan | 3640960.16 | 3640960.16 | 3856785
Approved | Transmission | C0041805 | L7005 Replacements and Upgrades Phase 2 | 2022 ACE Plan | 2022 ACE Plan | 3182518.11 | 3182518.11 | 2910450.72 | OTQ - October 10, 2025 | 2910451 | -272067.11
Approved | Transmission | C0041989 | 2022/2023 Sacrificial Anode Installation Program | 2022 ACE Plan | 2022 ACE Plan | 3015106.56 | 3015106.56 | 2773423
Deferred | Transmission | C0041794 | L5031 Replacements and Upgrades Phase 2 | 2022 ACE Plan | 2022 ACE Plan | 2905019.26 | 2905019.26 | 0
Approved | Transmission | C0041791 | L6551 Replacements and Upgrades | 2022 ACE Plan | 2022 ACE Plan | 1988245.66 | 1988245.66 | 1090711.59
Approved | Distribution | C0043130 | 2022 Padmount Replacement Program | 2022 ACE Plan | 2022 ACE Plan | 1807359.37 | 1807359.37 | 1877876.37
Approved | Transmission | C0043571 | 2022/2023 Transmission Switch & Breaker Replacement | 2022 ACE Plan | 2022 ACE Plan | 1612637.79 | 1612637.79 | 1776297.77
Approved | Generation | C0036368 | HYD - Lower Great Brook Switchgear Replacement | 2022 ACE Plan | 2022 ACE Plan | 1362281.36 | 1362281.36 | 1414117.57
Awaiting Approval | Transmission | C0043010 | 2022/2023 Wood Pole Retreatment Program | 2022 ACE Plan | 2022 ACE Plan | 1300037.21 | 1300037.21 | 791054 | OTQ - October 10, 2025 | 791054 | -508983.21
Approved | Transmission | C0041804 | 2022 Line Retirement Program | 2022 ACE Plan | 2022 ACE Plan | 1242178.29 | 1242178.29 | 159806.93
Approved | Generation | C0024484 | HYD - Fourth Lake Switchgear Replacement | 2022 ACE Plan | 2022 ACE Plan | 1145245.46 | 1145245.46 | 1560285.14
Approved | Generation | C0029691 | CT - VJ1 Control System Upgrade | 2022 ACE Plan | 2022 ACE Plan | 1016224.92 | 1016224.92 | 1002085
Approved | Transmission | C0045132 | ECEI - Battery Energy Storage System Project | 2022 ACE Plan (for Subsequent Approval) | OTQ - January 25, 2024 | 171207919.79 | 237772259 | 98440934.1
Deferred | Generation | C0044392 | Eastern Clean Energy Initiative (ECEI) - Coal Conversion | 2022 ACE Plan (for Subsequent Approval) |  | 32341324.51 |  | 1810843
Deferred | Generation | C0034486 | HYD - WRC LEM Penstock intake | 2022 ACE Plan (for Subsequent Approval) |  | 11239850.61 |  | 1206698
Approved | Generation | C0000979 | HYD - Governor Dam Refurbishment | 2022 ACE Plan (for Subsequent Approval) | OTQ - November 6, 2023 | 2696629.84 | 4844345.32 | 4843592.92
Approved | Distribution | C0022662 | 22C-404GA Lennox Passage Rebuild | 2022 ACE Plan (for Subsequent Approval) | OTQ - July 4, 2022 | 2352190.78 | 2609595.48 | 2684386.1
Deferred | Transmission | C0036826 | L8004 Parallel Canso Strait Crossing | 2022 ACE Plan (for Subsequent Approval) |  | 2139081.25 |  | 0
Approved | General Plant | C0041994 | NERC CIP 2022 | 2022 ACE Plan (for Subsequent Approval) | OTQ - April 4, 2022 | 1379473.59 | 1247663 | 1186070.21
Approved | Generation | C0041651 | TUC HFO Tank 4 Refurbishment | 2022 ACE Plan (for Subsequent Approval) | Q4 - February 6, 2023 | 1110292.77 | 2734313 | 2756903
Approved | Transmission | C0010956 | 78W-Martin’s Brook Substation Relocation | P&A | OTQ - March 3, 2025 | 0 | 5122761 | 4690774.8
Approved | Transmission | C0045510 | 20V-T52 Transformer Replacement | U&U | Q3 - November 7, 2022 | 0 | 1506565.52 | 1516378.04
Approved | Transmission | C0041807 | L5534 Replacements and Upgrades | P&A | OTQ - December 5, 2022 | 0 | 1426418.29 | 1558205.31
Approved | Transmission | C0049212 | L8001 Replacements and Upgrades Phase 3 | P&A | OTQ - December 5, 2022 | 0 | 1263906.4 | 1208027
Approved | Transmission | C0050835 | 2023/2024 Steel Tower Refurbishment | P&A | OTQ - December 5, 2022 | 0 | 2056634.87 | 1553776.78
Approved | Transmission | C0052055 | 2023/2024 Transmission Right-of-Way Widening 69kV | P&A | OTQ - December 5, 2022 | 0 | 5332315 | 4826689.21
Approved | Distribution | C0052056 | New Distribution Rights-of-Way Phase 8 | P&A | OTQ - December 5, 2022 | 0 | 9796663.1 | 9088167
Approved | Transmission | C0052634 | L5016 Replacements and Upgrades | P&A | OTQ - December 5, 2022 | 0 | 2697636.73 | 2907266.49
Approved | Generation | C0001222 | CT BGT1 Engine Exchange | P&A | OTQ - January 9, 2023 | 0 | 2338747 | 2350941
Approved | Generation | C0055376 | TUC1 - LP Blade Refurbishment U&U | U&U | Q4 - February 6, 2023 | 0 | 2025440.22 | 1988075
Approved | Generation | C0041506 | LM6000 Engine 191-253 Refurbishment | 2023 ACE Plan | OTQ - March 7, 2024 | 8740978.85 | 13473407 | 13067325.03
Approved | Generation | C0012838 | HYD - Lequille Canal Dyke, Gates and Tailrace Refurbishment | 2023 ACE Plan | 2023 ACE Plan | 7058816.14 | 7058816.14 | 5666283.36
Approved | Generation | C0029682 | CT VJ2 - Replace Generator Assembly | 2023 ACE Plan | 2023 ACE Plan | 5397737.93 | 5397737.93 | 3266711.93
Approved | Generation | C0051134 | TUC2 - L-0 Blade Replacement | 2023 ACE Plan | 2023 ACE Plan | 4157503.35 | 4157503.35 | 4172144
Approved | Transmission | C0041788 | L6516 Replacements and Upgrades Phase 2 | 2023 ACE Plan | OTQ July 2, 2024 | 3123474.28 | 5442793.92 | 4417849.61
Approved | Transmission | C0055539 | 10H-T1 Transformer Replacement | 2023 ACE Plan | 2023 ACE Plan | 2420891.67 | 2420891.67 | 41916.18
Approved | Transmission | C0052299 | 2023/2024 Steel Tower Life Extension | 2023 ACE Plan | 2023 ACE Plan | 2195463.46 | 2195463.46 | 771267.91
Approved | Transmission | C0055796 | 2023 EHV Breaker Replacements | 2023 ACE Plan | OTQ - October 2, 2023 | 2048410.56 | 3463488.74 | 489114.51
Approved | Transmission | C0055696 | L5031 Replacement and Upgrades Robinson Corner Tap | 2023 ACE Plan | 2023 ACE Plan | 1357477.23 | 1357477.23 | 1481748.71
Approved | Distribution | C0050836 | 2023 Padmount Replacement Program | 2023 ACE Plan | 2023 ACE Plan | 1309551.39 | 1309551.39 | 1527045.93
Approved | Generation | C0051135 | TUC2 - Turbine Valves Refurbishment 2023 | 2023 ACE Plan | 2023 ACE Plan | 1048924 | 1048924 | 967772
Approved | Transmission | C0052654 | L5541 Water Crossing Upgrades | 2023 ACE Plan | 2023 ACE Plan | 1047073.87 | 1047073.87 | 0
Approved | Transmission | C0053316 | Michelin Voltage Sag Reduction DVR | 2023 ACE Plan (for Subsequent Approval) | OTQ - April 12, 2024 | 21007507.1 | 31170675 | 32729208
Approved | General Plant | C0042166 | IT - Data Loss Prevention (DLP) Platform | 2023 ACE Plan (for Subsequent Approval) | OTQ - June 7, 2023 | 3233905.29 | 4261239.1945 | 3944010
Approved | Generation | C0051894 | TUC - HFO Tank 3 Refurbishment | 2023 ACE Plan (for Subsequent Approval) | OTQ - March 7, 2024 | 2053937.48 | 2218012 | 2251680
Approved | General Plant | C0030984 | IT - Cisco UCS Lifecycle | 2023 ACE Plan (for Subsequent Approval) | OTQ - September 5, 2023 | 2047690.67 | 2456609.31 | 2088998 | Q2 - August 5, 2025 | 2088998 | -367611.31
Approved | Generation | C0044030 | WIN - DIG Haight's Brook Crossing Replacement | 2023 ACE Plan (for Subsequent Approval) | OTQ - November 6, 2023 | 2046984.81 | 2024051.53 | 297228.84
Approved | Transmission | C0055557 | 76V-T1 Transformer Replacement | 2023 ACE Plan (for Subsequent Approval) | OTQ - April 7, 2025 | 1751258.26 | 3151575 | 2198206.07
Approved | General Plant | C0011167 | IT - Backup Infrastructure Upgrade | 2023 ACE Plan (for Subsequent Approval) | OTQ - June 7, 2023 | 1557470.73 | 2315457.44 | 2310349.86
Approved | Generation | C0048591 | CT VJ1 Engine P686621 Refurbishment | P&A | OTQ - March 6, 2023 | 0 | 2312509.06 | 2283878
Approved | Generation | C0054356 | TUC – Roof Replacement U&U | U&U | OTQ - March 6, 2023 | 0 | 1459455.09 | 1412165
Approved | Generation | C0053916 | CT BGT4 Engine P686630 Refurbishment | U&U | OTQ - April 3, 2023 | 0 | 1850500.99 | 1718317
Approved | Transmission | C0031052 | Replenish Spare Transformer Used at 58C | 2021 ACE Plan (Less than $1M) | OTQ - June 7, 2023 | 982910 | 1303826.93 | 1183122
Approved | Generation | 51761 | LIN2 2022/2023 Winter Capacity Requirement | U&U | OTQ - September 5, 2023 | 0 | 2512340.71 | 2526651
Approved | Generation | C0006418 | HYD WRC Tailrace Tunnel Rock Bolting Phase 2 | 2024 ACE Plan | 2024 ACE Plan | 15722669.17 | 15722669.17 | 9787742.97
Approved | General Plant | C0047277 | IT - GIS Utility Network Upgrade | 2024 ACE Plan | 2024 ACE Plan | 6175229.82 | 6175229.82 | 3336285
Approved | Generation | C0049013 | HYD - Lower Great Brook Log Hoist Replacement | 2024 ACE Plan | 2024 ACE Plan | 2158657.9 | 2158657.9 | 1816361.64
Approved | Generation | C0049032 | HYD - Cowie Falls Log Hoist Replacement | 2024 ACE Plan | 2024 ACE Plan | 2237991.11 | 2237991.11 | 1886112.01
Approved | General Plant | C0049619 | IT - ERP Upgrade (EBS, PS, PP, OBIA) | 2024 ACE Plan | 2024 ACE Plan | 6198799.37 | 6198799.37 | 5392636.86
Approved | Transmission | C0050842 | 2024 Bulk Oil Breaker Replacement Program | 2024 ACE Plan | 2024 ACE Plan | 3274755.9 | 3274755.9 | 859083.52
Approved | Generation | C0051136 | TUC2 - HP/IP Turbine Refurbishment | 2024 ACE Plan | 2024 ACE Plan | 4264777.44 | 5965028 | 5921806.59
Approved | Transmission | C0056240 | 2024/2025 Transmission Switch and Breaker Replacements | 2024 ACE Plan | 2024 ACE Plan | 3271621.79 | 3271621.79 | 3081410.77
Approved | Distribution | C0057142 | New Distribution Rights-of-Way Phase 9 | 2024 ACE Plan | 2024 ACE Plan | 19141913.7 | 19141913.7 | 19189121.18
Approved | Transmission | C0057882 | 2024 Pennsylvania Breaker Replacements | 2024 ACE Plan | 2024 ACE Plan | 2163831.86 | 2163831.86 | 520212.35
Approved | Generation | C0058942 | WRC D11-2 Foundation Stabilization | 2024 ACE Plan | 2024 ACE Plan | 1540602.39 | 1540602.39 | 1451471.04
Approved | Transmission | C0059046 | 101S and 79N Reactor Replacements | 2024 ACE Plan | 2024 ACE Plan | 1460062.22 | 1460062.22 | 822764.5
Approved | Generation | C0060608 | TUC6 Turbine Refurbishment | 2024 ACE Plan | 2024 ACE Plan | 2472311.19 | 2472311.19 | 562395.71
Approved | Generation | C0060707 | CT BGT1 Generator Refurbishment | 2024 ACE Plan | 2024 ACE Plan | 3482602.45 | 3482602.45 | 7684.02
Approved | Distribution | C0060749 | 2024 Padmount Replacement Program | 2024 ACE Plan | 2024 ACE Plan | 1288197.9 | 1288197.9 | 1868270.86
Approved | Transmission | C0061023 | 2024 EHV Breaker Replacements | 2024 ACE Plan | 2024 ACE Plan | 3638479.75 | 3638479.75 | 434.87
Approved | Transmission | C0061046 | 2024 Merlin Gerin Breaker Replacements | 2024 ACE Plan | 2024 ACE Plan | 1169590.5 | 1169590.5 | 326311.5
Approved | Transmission | C0061387 | 2024 2025 Wood Pole Retreatment Program | 2024 ACE Plan | 2024 ACE Plan | 1209391.21 | 1209391.21 | 258382.01
Approved | Transmission | C0061403 | 2024 2025 Sacrificial Anode Installation Program | 2024 ACE Plan | 2024 ACE Plan | 2382112.6 | 2382112.6 | 2586371.8
Approved | Transmission | C0061545 | L6006 Replacements and Upgrades | 2024 ACE Plan | 2024 ACE Plan | 5032640.4 | 5032640.4 | 6015794.38
Approved | Transmission | C0061546 | L6514 Replacements and Upgrades | 2024 ACE Plan | 2024 ACE Plan | 2102666.38 | 2102666.38 | 1588417.41
Approved | Transmission | C0061547 | L7022 Replacements and Upgrades | 2024 ACE Plan | 2024 ACE Plan | 2283568.76 | 2283568.76 | 21085.05
Approved | Transmission | C0061550 | L5031 Replacements and Upgrades - Hubbards to East Chester | 2024 ACE Plan | 2024 ACE Plan | 5297583.52 | 5297583.52 | 4001201.25
Approved | Transmission | C0061551 | L7009 Replacements and Upgrades | 2024 ACE Plan | 2024 ACE Plan | 3280328.4 | 3280328.4 | 1317704.93
Approved | Transmission | C0061743 | L6038 Realignment | 2024 ACE Plan | 2024 ACE Plan | 1032910.93 | 1032910.93 | 1485549.3
Approved | Transmission | C0061883 | 129H - Kearney Lake Substation Rebuild | 2024 ACE Plan | 2024 ACE Plan | 1017322.14 | 1017322.14 | 53949.41
Approved | General Plant | C0054755 | IT - Connect My Data (Green Button) | 2024 ACE Plan (for Subsequent Approval) | Q4 - February 5, 2024 | 2309350.36 | 2964237 | 2884398.07
Deferred | Transmission | C0031286 | Spare Padmounted Substation | 2024 ACE Plan (for Subsequent Approval) |  | 1319837.87 |  | 0
Awaiting Approval | General Plant | C0032664 | ECC Optimization Tools Project | 2024 ACE Plan (for Subsequent Approval) | OTQ - December 1, 2025 | 4329149.97 | 7486068 | 1776697
Approved | Generation | C0050414 | HYD Roseway Asset Decommissioning | 2024 ACE Plan (for Subsequent Approval) | OTQ - December 20, 2024 | 4650648.04 | 4915649 | 3657666.9
Approved | Generation | C0060816 | POT - HFO Tank Refurbishment | 2024 ACE Plan (for Subsequent Approval) | OTQ - December 17, 2024 | 2012802.82 | 3684622 | 3628104.17
Deferred | General Plant | C0061287 | IT - Third Party Risk Management | 2024 ACE Plan (for Subsequent Approval) |  | 1405970.41 |  | 0
Approved | General Plant | C0061289 | IT - Network Next Generation Security Design | 2024 ACE Plan (for Subsequent Approval) | OTQ - April 7, 2025 | 2632635 | 1814215.74 | 1884878.48
Approved | Distribution | C0061521 | New Distribution Rights-of-Way Phase 10 | 2024 ACE Plan (for Subsequent Approval) | OTQ - October 7, 2024 | 18904608 | 20890176 | 16467375.07
Approved | Generation | C0038126 | HYD Cowie Falls Unit 12 Overhaul | 2024 ACE Plan (Less than $1M) | Q1 - May 13, 2024 | 964521.17 | 1274890 | 1288270.46
Approved | Generation | C0053655 | HYD Cowie Falls Unit 11 Overhaul | 2023 ACE Plan (Less than $1M) | Q1 - May 13, 2024 | 913947.02 | 1225491 | 1291556
Approved | Generation | C0059283 | LIN2 PE 2023/2024 Winter Capacity Requirements | U&U | Q1 - May 13, 2024 | 0 | 1661834 | 1663857.83
Approved | Transmission | C0062123 | 143H-Mount Uniacke Substation | P&A | Q2 - August 6, 2024 | 0 | 9040869 | 3853852.77
Approved | General Plant | C0056461 | IT - Contact Centre Cloud Migration | 2024 ACE Plan (for Subsequent Approval) | OTQ - September 16, 2024 | 929372 | 3237539 | 2264820.78
Approved | Transmission | C0031048 | 91H-T11 Transformer Replacement | 2025 ACE Plan | 2025 ACE Plan | 6914621.96 | 6914621.96 | 85569.5
Approved | Generation | C0039266 | HYD - Gulch Overhaul | 2025 ACE Plan | 2025 ACE Plan | 1371379.09 | 1371379.09 | 287049.41
Approved | Generation | C0048990 | HYD AVO 2 Switchgear Replacement | 2025 ACE Plan | 2025 ACE Plan | 1814631.36 | 1814631.36 | 777175.91
Approved | Transmission | C0050834 | Spare EHV Breaker Replacements | 2025 ACE Plan | 2025 ACE Plan | 1178831.81 | 1178831.81 | 162.47
Approved | Transmission | C0050852 | 10V-T1 Transformer Replacement | 2025 ACE Plan | 2025 ACE Plan | 2113336.98 | 2113336.98 | 1453500.92
Pending Submission | General Plant | C0051815 | RTU Replacements Program Phase 6 | 2025 ACE Plan | 2025 ACE Plan | 5959915.27 | 5959915.27 | 1192508.15
Approved | Transmission | C0053295 | L5004 Kearney Lake Structure Replacement | 2025 ACE Plan | 2025 ACE Plan | 2478536.78 | 2478536.78 | 304280.71
Approved | Transmission | C0057682 | Spare Transformer Replacement | 2025 ACE Plan | 2025 ACE Plan | 2286389.47 | 2286389.47 | 3610651.31
Approved | Generation | C0068659 | TRE5 - IP-LP Turbine Refurbishment | 2025 ACE Plan | 2025 ACE Plan | 1282669.84 | 1282669.84 | 3091267.28
Approved | Distribution | C0068786 | 2025 Padmount Replacement Program | 2025 ACE Plan | 2025 ACE Plan | 1354219.4 | 1354219.4 | 0
Approved | Generation | C0068882 | TUC1 Generator Refurbishment | 2025 ACE Plan | 2025 ACE Plan | 2124210.74 | 2124210.74 | 0
Approved | Generation | C0068887 | TUC3 Turbine Valves Refurbishment | 2025 ACE Plan | 2025 ACE Plan | 1869103.9 | 1869103.9 | 1615312.14
Approved | Distribution | C0068952 | 2025 PCB Poletop Sampling and Replacement | 2025 ACE Plan | 2025 ACE Plan | 7158973.99 | 7158973.99 | 1557845.47
Approved | Distribution | C0068953 | 2025 PCB Light Replacement | 2025 ACE Plan | 2025 ACE Plan | 4225224.41 | 4225224.41 | 0
Approved | Distribution | C0068954 | 2025 PCB Downline Device Sampling and Replacement | 2025 ACE Plan | 2025 ACE Plan | 1716718.39 | 1716718.39 | 0
Approved | Transmission | C0068961 | 2025 PCB Substation Sampling and Replacement | 2025 ACE Plan | 2025 ACE Plan | 6650932.5 | 6650932.5 | 39831.35
Approved | Transmission | C0069227 | L6516 Replacements and Upgrades Phase 3 | 2025 ACE Plan | 2025 ACE Plan | 3104924.75 | 3104924.75 | 1535109.77
Approved | Transmission | C0069231 | L8002 Replacements and Upgrades Phase 1 | 2025 ACE Plan | 2025 ACE Plan | 3093175.63 | 3093175.63 | 1223077.23
Approved | Transmission | C0069232 | L6021 Replacements and Upgrades Phase 1 | 2025 ACE Plan | 2025 ACE Plan | 3253068.08 | 3253068.08 | 1614847.23
Approved | Transmission | C0069238 | 2025/2026 Steel Tower Refurbishment | 2025 ACE Plan | 2025 ACE Plan | 2337250.27 | 2337250.27 | 0
Approved | General Plant | C0069270 | 2025 SCADA/EMS Upgrade | 2025 ACE Plan | 2025 ACE Plan | 1306288.06 | 1306288.06 | 22718.46
Approved | Transmission | C0070048 | L5027B Replacements and Upgrades Phase 1 | 2025 ACE Plan | 2025 ACE Plan | 2916727.9 | 2916727.9 | 0
Approved | Distribution | C0070787 | 91W-411 Labelle Road Phase Extension | 2025 ACE Plan | 2025 ACE Plan | 1150615.99 | 1150615.99 | 0
Approved | General Plant | C0070907 | MDR-8000 Microwave Radio Replacement | 2025 ACE Plan | 2025 ACE Plan | 1572477.91 | 1572477.91 | 0
Deferred | Generation | 48913 | HYD - Tusket Facility Refurbishment | 2025 ACE Plan (for Subsequent Approval) |  | 12972226.16 |  | 1078895.28
Deferred | Transmission | C0011358 | New Bridgewater Substation | 2025 ACE Plan (for Subsequent Approval) |  | 18173046.53 |  | 2177530.09
Approved | Transmission | C0021140 | New 138KV-25KV Substation Stellarton | 2025 ACE Plan (for Subsequent Approval) | Q1 - May 16, 2025 | 10511998.19 | 12960396 | 3494363.74
Approved | Transmission | C0041830 | Spare Power Production Unit Transformer | 2025 ACE Plan (for Subsequent Approval) | OTQ - April 7, 2025 | 1264622.46 | 1266552.19 | 1212412.1
Filed by WTI | Transmission | C0044391 | Eastern Clean Energy Initiative (ECEI) - Transmission | 2025 ACE Plan (for Subsequent Approval) | OTQ - April 10, 2025 | 800229290.08 | 684685646 | 12684032.42
Awaiting Approval | General Plant | C0053699 | Renewable to Retail Implementation | 2025 ACE Plan (for Subsequent Approval) | OTQ - December 1, 2025 | 5062652.18 | 5644468 | 4635350.91
Approved | Generation | C0059783 | HYD Upper Lake Falls 2 Overhaul | 2025 ACE Plan (for Subsequent Approval) | OTQ - September 9, 2025 | 1678152.72 | 1582014 | 27268.68
Approved | General Plant | C0061284 | IT - OT Cyber Security Control Implementation | 2025 ACE Plan (for Subsequent Approval) | OTQ - March 3, 2025 | 5459312.92 | 6826426 | 1993686.27
Less than $1M | Generation | C0061484 | PTMT - E-Crane Refurbishment | 2025 ACE Plan (for Subsequent Approval) |  | 2433080.5 |  | 299710.52
Approved | Generation | C0063803 | HYD AVO 2 Access Road Stabilization | 2025 ACE Plan (for Subsequent Approval) | OTQ - April 7, 2025 | 2406283.37 | 1862825.78 | 328455.83
Approved | Generation | C0067023 | LIN2 2024/25 Capacity Requirement | 2025 ACE Plan (for Subsequent Approval) | OTQ - June 9, 2025 | 1083800.37 | 1257127 | 1290723.66
Approved | Generation | C0068566 | LIN DCS Upgrade 2025 | 2025 ACE Plan (for Subsequent Approval) | Q1 - May 16, 2025 | 1440910.59 | 1544190 | 340356.98
Awaiting Approval | Generation | C0068655 | LM6000 191-332 Life Extension | 2025 ACE Plan (for Subsequent Approval) | Q2 - August 5, 2025 | 6013453.54 | 18948560 | 18457860.07
Pending Submission | Generation | C0069166 | POT-Turbine Valve Refurbishment | 2025 ACE Plan (for Subsequent Approval) |  | 2872597.56 |  | 0
Awaiting Approval | Generation | C0070486 | HYD LGB Stoplog Replacement | 2025 ACE Plan (for Subsequent Approval) | OTQ - December 1, 2025 | 1288403.9 | 3593884 | 1418999.07
Awaiting Approval | Distribution | C0071528 | FLISR Implementation | 2025 ACE Plan (for Subsequent Approval) | Q2 - August 5, 2025 | 5299247.73 | 4638245 | 34654.49
Approved | Generation | C0061003 | POA LP HP IP Turbine Refurbishment | 2025 ACE Plan (for Subsequent Approval) | OTQ - July 7, 2025 | 4155130.87 | 4861261 | 1356414.56
Approved | Generation | C0061005 | POA Cell Capping 2025 | 2025 ACE Plan (for Subsequent Approval) | OTQ - July 7, 2025 | 3255439.91 | 2530405 | 1843307.3
Approved | Generation | C0067906 | POA Boiler Refurbishment 2025 | 2025 ACE Plan (for Subsequent Approval) | OTQ - July 7, 2025 | 1213152.46 | 1218254 | 1525526.93
Approved | Generation | C0067908 | POA Boiler Refractory Refurbishment 2025 | 2025 ACE Plan (for Subsequent Approval) | OTQ - July 7, 2025 | 1089478.33 | 1378466 | 744890.64
Approved | General Plant | C0011159 | Plant Information System Upgrade | 2024 ACE Plan (Less than $1M) | OTQ - March 3, 2025 | 362679 | 1142652 | 1081537.95
Approved | Distribution | C0042687 | 15N-202 Arthur St Conversion | 2022 ACE Plan (Less than $1M) | OTQ - April 7, 2025 | 718195 | 1399459 | 1200267.4
Approved | Generation | C0049192 | HYD - GUL Generator Refurbishment | 2025 ACE Plan (Less than $1M) | Q1 - May 16, 2025 | 732043 | 1316589 | 447455.37
Approved | Generation | C0068662 | TRE5 Baghouse Filter Replacement | 2025 ACE Plan (Less than $1M) | Q1 - May 16, 2025 | 534006 | 1241640 | 1065703.39
Approved | Generation | C0073348 | HYD - WRC Surge Lake Volume Optimization | U&U | Q1 - May 16, 2025 | 0 | 1736278 | 691019.11
Approved | Generation | C0073965 | TRE5 U&U Burner Nest Waterwall Tube Replacement | U&U | Q1 - May 16, 2025 | 0 | 2156407 | 668078.54
Approved | General Plant | C0073777 | IT - Complex Customer Projects | P&A | OTQ - June 9, 2025 | 0 | 3025518 | 396568.36
Approved | General Plant | 49036 | HYD - Avon 2 Controls Upgrade | 2025 ACE Plan (Less than $1M) | Q2 - August 5, 2025 | 0 | 1073463 | 398861.1
Awaiting Approval | Generation | C0073491 | LM6000 191-443 Engine Replacement | P&A | Q2 - August 5, 2025 | 0 | 24217289 | 22864.47
Approved | Generation | C0067183 | TUC Wharf Access Bridge Replacement | U&U | Q2 - August 5, 2025 | 0 | 2426669 | 445031.58
Approved | Transmission | C0074130 | Robie Street Underground | P&A | OTQ - September 9, 2025 | 0 | 4465119 | 1221313.73
Awaiting Approval | Generation | C0080112 | HYD Big Falls Unit 6 Rotor Re-Insulation | U&U | OTQ - October 10, 2025 | 0 | 1025626 | 48184.55
Awaiting Approval | General Plant | C0053696 | ECC Wind Integration | 2025 ACE Plan (Less than $1M) | OTQ - December 1, 2025 | 757358 | 4428335 | 16080.27
Awaiting Approval | Generation | C0080228 | HYD HOB Stator Rewind and Generator Refurbishment | U&U | OTQ - December 1,2025 | 0 | 2587170 | 0
Awaiting Approval | Generation | C0021608 | TUC Shoreline Sheetpile Refurbishment | 2026 ACE Plan | 2026 ACE Plan | 5691466 | 5691466 | 272026.72
Awaiting Approval | Transmission | C0053214 | 76W-T1 Transformer Replacement | 2026 ACE Plan | 2026 ACE Plan | 2818855 | 2818855 | 66043.49
Awaiting Approval | Transmission | C0053234 | 96H-T1 Transformer Replacement | 2026 ACE Plan | 2026 ACE Plan | 2056752 | 2056752 | 21093.21
Awaiting Approval | Generation | C0068888 | TUC3 Continuous Ash Hauling System | 2026 ACE Plan | 2026 ACE Plan | 1359984 | 1359984 | 0
Awaiting Approval | Generation | C0068898 | TUC1 IP LP Last Stage Blade Replacement | 2026 ACE Plan | 2026 ACE Plan | 5215861 | 5215861 | 0
Awaiting Approval | Transmission | C0068969 | 2026 Pennsylvania Breaker Replacements | 2026 ACE Plan | 2026 ACE Plan | 1620028 | 1620028 | 33473.99
Awaiting Approval | Transmission | C0070586 | L6536 Switch Replacements | 2026 ACE Plan | 2026 ACE Plan | 2074494 | 2074494 | 72102.81
Awaiting Approval | Transmission | C0070909 | 70W-T52 Transformer Addition | 2026 ACE Plan | 2026 ACE Plan | 3957128 | 3957128 | 11474.96
Awaiting Approval | Distribution | C0080104 | 36V-303 Baxter's Harbour Rd Reconductor Phase 1 | 2026 ACE Plan | 2026 ACE Plan | 1062416 | 1062416 | 0
Awaiting Approval | Transmission | C0080109 | L7001 Replacements and Upgrades Phase 1 | 2026 ACE Plan | 2026 ACE Plan | 3063280 | 3063280 | 0
Awaiting Approval | Transmission | C0080110 | L7012 Replacements and Upgrades Phase 1 | 2026 ACE Plan | 2026 ACE Plan | 5370318 | 5370318 | 0
Awaiting Approval | General Plant | C0080111 | 2026 RTU Deployment | 2026 ACE Plan | 2026 ACE Plan | 8322655 | 8322655 | 0
Awaiting Approval | Generation | C0080133 | TUC3 IP Turbine Refurbishment | 2026 ACE Plan | 2026 ACE Plan | 2588734 | 2588734 | 0
Awaiting Approval | Generation | C0080134 | TUC2 Stack Coating and Structural Refurbishment | 2026 ACE Plan | 2026 ACE Plan | 4256511 | 4256511 | 0
Awaiting Approval | Generation | C0080135 | CT - BGT2 Engine Refurbishment | 2026 ACE Plan | 2026 ACE Plan | 2462664 | 2462664 | 0
Awaiting Approval | Generation | C0080205 | POA Boiler Refractory Replacement 2026 | 2026 ACE Plan | 2026 ACE Plan | 1024385 | 1024385 | 0
Awaiting Approval | Generation | C0080206 | POA Boiler Refurbishment 2026 | 2026 ACE Plan | 2026 ACE Plan | 1304600 | 1304600 | 0
Awaiting Approval | General Plant | C0080252 | Intelligent Asset Data Capture & Integration Platform | 2026 ACE Plan | 2026 ACE Plan | 267941 | 267941 | 0
Awaiting Approval | Distribution | C0080266 | New Distribution Right of Way Phase 11 | 2026 ACE Plan | 2026 ACE Plan | 20889694 | 20889694 | 0
Awaiting Approval | Distribution | C0080612 | 57C-426H Melrose Reconductor and Line Extension Phase 1 | 2026 ACE Plan | 2026 ACE Plan | 1288474 | 1288474 | 0
Pending Submission | Generation | 47649 | HYD Salmontail Gate Pedestal and Main Dam Refurbishment | 2026 ACE Plan (for Subsequent Approval) |  | 5870708 |  | 705758.42
Pending Submission | Generation | 47650 | HYD - Annapolis Decision Analysis | 2026 ACE Plan (for Subsequent Approval) |  | 30732442 |  | 2873659.76
Pending Submission | Generation | 49595 | HYD - TUS 1 Overhaul | 2026 ACE Plan (for Subsequent Approval) |  | 5649954 |  | 310075.45
Pending Submission | Transmission | 51098 | L-6014 Shannon Park Transmission Towers | 2026 ACE Plan (for Subsequent Approval) |  | 39471723 |  | 1476385
Pending Submission | General Plant | C0000017 | Storm Management Software Implementation | 2026 ACE Plan (for Subsequent Approval) |  | 2235914 |  | 0
Pending Submission | General Plant | C0021835 | IT - CIS Replacement | 2026 ACE Plan (for Subsequent Approval) |  | 84502844 |  | 3517008.53
Pending Submission | Transmission | C0022247 | 1N Onslow Transformer Addition (1N-T66) | 2026 ACE Plan (for Subsequent Approval) |  | 3645131 |  | 1743771.94
Pending Submission | Transmission | C0023802 | L-6515 Canso Causeway Rebuild | 2026 ACE Plan (for Subsequent Approval) |  | 3925352 |  | 397399.67
Pending Submission | General Plant | C0032202 | Sydney Depot Improvements | 2026 ACE Plan (for Subsequent Approval) |  | 2700000 |  | 0
Pending Submission | Transmission | C0032382 | 142H - Susie Lake Substation | 2026 ACE Plan (for Subsequent Approval) |  | 8256386 |  | 671904.21
Pending Submission | General Plant | C0047278 | IT - Oracle MDM Upgrade | 2026 ACE Plan (for Subsequent Approval) |  | 7949409 |  | 29354.91
Pending Submission | General Plant | C0047301 | IT - Cloud Integration Platform | 2026 ACE Plan (for Subsequent Approval) |  | 2004962 |  | 137727.33
Pending Submission | Generation | C0047973 | HYD ANN Sluice Gates and Check Refurbishment | 2026 ACE Plan (for Subsequent Approval) |  | 5673491 |  | 215551.34
Pending Submission | Generation | C0052514 | HYD MacDonald Dam Access Improvements | 2026 ACE Plan (for Subsequent Approval) |  | 1547398 |  | 123275.26
Pending Submission | Generation | C0057361 | HYD ANN Facility Isolation | 2026 ACE Plan (for Subsequent Approval) |  | 4083925 |  | 2778286.55
Pending Submission | Transmission | C0059483 | 83V L-5017 and L-5046 Rebuild Tap | 2026 ACE Plan (for Subsequent Approval) |  | 1207318 |  | 212713.5
Pending Submission | Transmission | C0061552 | L-6043 Replacements and Upgrades | 2026 ACE Plan (for Subsequent Approval) |  | 2457629 |  | 0
Pending Submission | General Plant | C0062043 | IT - SharePoint Technical Migration | 2026 ACE Plan (for Subsequent Approval) |  | 3134674 |  | 1006383
Pending Submission | Generation | C0064967 | Tusket Powerhouse Tidal Pool Fish Passage | 2026 ACE Plan (for Subsequent Approval) |  | 1315495 |  | 0
Pending Submission | Generation | C0067686 | HYD Lumsden Rubber Dam Replacement | 2026 ACE Plan (for Subsequent Approval) |  | 1304068 |  | 54523.6
Pending Submission | General Plant | C0067863 | IT - Managed Detect & Respond | 2026 ACE Plan (for Subsequent Approval) |  | 2585071 |  | 140001.96
Pending Submission | General Plant | C0068714 | IT - Identity & Access Management | 2026 ACE Plan (for Subsequent Approval) |  | 4324589 |  | 914563.4
Pending Submission | General Plant | C0068718 | IT - DERMS Solution Project | 2026 ACE Plan (for Subsequent Approval) |  | 2954002 |  | 121256.7
Pending Submission | General Plant | C0068719 | IT - Distributed Intelligence Apps | 2026 ACE Plan (for Subsequent Approval) |  | 2637356 |  | 15821.81
Pending Submission | General Plant | C0068721 | IT - ADMS Upgrade 2026 | 2026 ACE Plan (for Subsequent Approval) |  | 7200000 |  | 0
Pending Submission | Transmission | C0069534 | IR 669 Network Upgrade Higgins Mountain Wind | 2026 ACE Plan (for Subsequent Approval) |  | 9496174 |  | 115696.62
Pending Submission | Transmission | C0070086 | 10H-T2 Transformer Replacement | 2026 ACE Plan (for Subsequent Approval) |  | 2878891 |  | 20581.52
Pending Submission | Transmission | C0070327 | IR 673 Network Upgrade Benjamins Mill Wind | 2026 ACE Plan (for Subsequent Approval) |  | 265000 |  | 7945.63
Pending Submission | Transmission | C0070367 | IR 618 Network Upgrade Goose Harbour Lake Wind | 2026 ACE Plan (for Subsequent Approval) |  | 11015684 |  | 9084.91
Pending Submission | Transmission | C0071888 | New Tidewater Substation | 2026 ACE Plan (for Subsequent Approval) |  | 4141223 |  | 73909.38
Pending Submission | Transmission | C0071889 | 77V-T1 Transformer Replacement | 2026 ACE Plan (for Subsequent Approval) |  | 3486796 |  | 8208.83
Pending Submission | Transmission | C0072808 | ECEI Synchronous Condensers | 2026 ACE Plan (for Subsequent Approval) |  | 364566804 |  | 553600.43
Pending Submission | Generation | C0073368 | HYD Malay Falls Rubber Dam | 2026 ACE Plan (for Subsequent Approval) |  | 2237339 |  | 42683.85
Pending Submission | Generation | C0076273 | Bear Head Ash Management Site - Life Extension | 2026 ACE Plan (for Subsequent Approval) |  | 10148108 |  | 18725.42
Pending Submission | Generation | C0076672 | ICP - RC SCR Bridge 10.10 Refurbishment | 2026 ACE Plan (for Subsequent Approval) |  | 1353592 |  | 0
Pending Submission | Distribution | C0080101 | 539N-210 Big Island Sub-Sea Cable Replacement | 2026 ACE Plan (for Subsequent Approval) |  | 3539067 |  | 0
Pending Submission | Distribution | C0080102 | 92H-331 Double Circuit Peggys Cove Rd | 2026 ACE Plan (for Subsequent Approval) |  | 1882573 |  | 0
Pending Submission | Transmission | C0080107 | L-5532 Reliability Upgrade - 91W Middle Field Substation | 2026 ACE Plan (for Subsequent Approval) |  | 3053526 |  | 0
Pending Submission | Transmission | C0080108 | L-5532 Replacements and Upgrades Phase 1 | 2026 ACE Plan (for Subsequent Approval) |  | 2490532 |  | 0
Pending Submission | Generation | C0080219 | HYD Deep Brook Spillway & Intake Refurbishment | 2026 ACE Plan (for Subsequent Approval) |  | 3142201 |  | 4249.76
Pending Submission | Generation | C0080671 | LIN1 HIP Turbine Refurbishment 2026 | 2026 ACE Plan (for Subsequent Approval) |  | 3244992 |  | 0
Pending Submission | Generation | C0080691 | LIN3 DCS Migration 2026 | 2026 ACE Plan (for Subsequent Approval) |  | 1359218 |  | 0
Pending Submission | Generation | C0080732 | POA Ash Cell Capping/ Cell Development 2026 | 2026 ACE Plan (for Subsequent Approval) |  | 2420358 |  | 0
Pending Submission | Generation | C0080768 | POT - CW Pump & Motor Replacement | 2026 ACE Plan (for Subsequent Approval) |  | 2872183 |  | 0
Pending Submission | Transmission | C0081985 | Michelin DVR Phase 2 | 2026 ACE Plan (for Subsequent Approval) |  | 13000000 |  | 2875292
Pending Submission | General Plant | C0082133 | IT - Renew Microsoft Enterprise Agreement | 2026 ACE Plan (for Subsequent Approval) |  | 1800000 |  | 0
Pending Submission | Generation | C0082195 | LIN2 2025/26 Capacity Requirement | 2026 ACE Plan (for Subsequent Approval) |  | 3162203 |  | 0
* Maritime Link Transmission capital work orders were filed as part of the Company's General Rate Application. They were not approved at the time of the GRA Decision.

## R3 - Deferred or Cancelled
NS Power 2025 ACE Plan Items – Deferred or Cancelled
3rd Quarter Overview - as of September 30, 2025
This report includes any deferred or cancelled projects that were included in the 2025 ACE Plan.
CI | Project Title | 2025 ACE Amount | 2025 ACE Project Total | Cancelled / Deferred | Deferred To | Prior Approval | 2025 ACE Plan Reference | Commentary
Generation
48913 | HYD - Tusket Facility Refurbishment | 1093904.18 | 12972226.16 | Deferred | 2027 |  | Subsequent Submittal | As condition assessments related to the Powerhouse continue, it has been determined that additional engineering is required to prepare the capital filing. Curent assessment indicates that this can safety be deferred to 2027.
C0020329 | TRE5 Stack Expansion Joint Replacement | 362990.64 | 395290.64 | Deferred | 2026 |  | Less than $1M | Through further scoping it was determined the risk could be mitigated in 2025 with additional monitoring and detection.
C0020331 | TRE5 Air Heater Expansion Joint Replacement | 354574.99 | 385221.99 | Deferred | 2026 |  | Less than $1M | Through further scoping it was determined the risk could be mitigated in 2025 with additional monitoring and detection.
C0061366 | TRE6 - Caustic Heater Heat Exchanger | 84017.17 | 91767.17 | Cancelled |  |  | Less than $1M | This project has been cancelled. Leak test on existing heat exchange bundle and gasket replacements mitigated risk and need for project.
C0068660 | TRE5 - Boiler Refurbishment 2025 | 825181.91 | 896931.91 | Cancelled |  |  | Less than $1M | This project has been cancelled as the scope of work will not be completed under C0073965 TRE5 U&U Burner Nest Waterwall Tube Replacement
C0030122 | LIN4 HIP Insulation Replacement | 106894.37 | 126233.95 | Deferred | 2026 |  | Less than $1M | Additional scoping found the condition of the insulation allows for this project to be deferred to 2026.
C0067945 | POA Pond Transfer Pumps | 367194.18 | 417194.18 | Cancelled |  |  | Pt. Aconi | This project has been cancelled, as updated condition assessment revealed the risk does not need immediate mitigation.
C0060572 | TUC1 Secondary Air & Recirculation Damper Replacement | 77423.62 | 77423.62 | Cancelled |  |  | Less than $1M | This project has been cancelled, as the risk can be managed through 2026 and will also be completed as part of a major boiler upgrade on TUC1 which will begin in 2027.
C0068894 | TUC1 Gas Block Valve Upgrades | 607737.24 | 607737.24 | Cancelled |  |  | Less than $1M | This project has been cancelled, as the risk can be managed through 2026 and will also be completed as part of a major boiler upgrade on TUC1 which will begin in 2027.
C0069047 | TUC2 FD Fan Duct Refurbishment | 99940.12 | 99940.12 | Deferred | 2027 |  | Less than $1M | Further scoping showed that engineering was required to determine the final project requirements and that the risks could be managed through to 2027.
C0069567 | TUC1 - Boiler Cyclone Tube Replacements | 859647.29 | 859647.29 | Cancelled |  |  | Less than $1M | This project has been cancelled, as the risk can be managed through 2026 and will also be completed as part of a major boiler upgrade on TUC1 which will begin in 2027.
C0068303 | LIN Wastewater Lagoon Algae Control 2025 | 102074.1 | 111164.19 | Cancelled |  |  | Less than $1M | Monitoring has shown that recent algae levels are being managed through current risk mitigation practices.
C0068236 | LIN4 North Water Wall Replacement 2025 | 446612.36 | 526274.88 | Deferred | 2026 |  | Less than $1M | This project is being deferred to the 2026 outage. The existing approach to management of this asset is expected to address near-term risks.
C0068228 | LIN3 Air Preheater Seal Refurbishment | 102249.46 | 110788.23 | Deferred | 2026 |  | Less than $1M | As part of an updated condition assessment during this year's planned outage, the condiiton of the air preheater seals allows for this project to be deferred to 2026.
40023 | TRE - Sewage Lift Station Upgrades | 158492.98 | 158492.98 | Cancelled |  |  | Less than $1M | This project has been cancelled, as updated condition assessment revealed the risk does not need immediate mitigation.
C0020367 | TRE5 Main Oil Pump & Gearbox Refurbishment | 195311.55 | 212311.55 | Deferred | 2026 |  | Less than $1M | This project is being deferred to 2026 outage. The existing approach to management of this asset is expected to address near-term risks.
C0061363 | TRE5 - Screenwash Pump Replacement | 129988.79 | 151106.64 | Deferred | 2026 |  | Less than $1M | Updated condition assessment determined the condition of the asset allows the project to be deferred to 2026.
C0068624 | TRE - Overhead / Person Door Refurbishments | 92755.93 | 100556.08 | Cancelled |  |  | Less than $1M | This project is cancelled as the necessary scope to mitigate these risks will be completed through CI C0061356 TRE Overhead/Person Door Refurbishments
C0068627 | TRE - Rotating Equipment Guards 2025 | 131614.17 | 143314.17 | Cancelled |  |  | Less than $1M | This project has been cancelled, as further scoping revealed the risk can be managed without need for proactive replacement.
C0068658 | TRE6 - Battery Charger Replacement | 80589.07 | 87789.07 | Deferred | 2026 |  | Less than $1M | Further scoping determined the condition of the asset allows the project to be deferred to 2026.
C0068675 | TRE6 Parallel Slide HP heater isolations | 494861.06 | 540411.06 | Deferred | 2026 |  | Less than $1M | Deferred due to U&U capital work utilizing available resources. The existing approach to management of this asset is expected to address near-term risks.
C0068691 | TRE6 - Boiler Main Stop Valve | 148838.62 | 162538.62 | Deferred | 2026 |  | Less than $1M | Deferred due to U&U capital work utilizing available resources. The existing approach to management of this asset is expected to address near-term risks.
C0068692 | TRE6 - 6A BFP Discharge Valve Refurbishment | 149278.92 | 159778.92 | Deferred | 2026 |  | Less than $1M | Deferred due to U&U capital work utilizing available resources. The existing approach to management of this asset is expected to address near-term risks.
C0068693 | TRE6 Instrument Air Dry Replacement | 81210.21 | 88310.21 | Deferred | 2026 |  | Less than $1M | Deferred due to U&U capital work utilizing available resources. The existing approach to management of this asset is expected to address near-term risks.
C0070850 | TRE Shaker House Hoist Replacement | 83853.76 | 91353.76 | Deferred | 2026 |  | Less than $1M | Deferred to better define project scope. The exisiting approach to management of this asset is expected to address near-term risks.
C0060610 | TUC Cable Spreading Room Fire Protection | 250108.15 | 250108.15 | Cancelled |  |  | Less than $1M | This project has been cancelled. Project scope will be completed as part of CI C0069829 TUC - Relay Room Fire Suppression System.
C0068906 | TUC6 Boiler Feed Pump Refurbishment 2025 | 302097.12 | 302097.12 | Deferred | 2026 |  | Less than $1M | This project is deferred until the 2026 TUC6 outage. The existing approach to management of this asset is expected to address near-term risks.
C0057361 | HYD - ANN Facility Isolation | 210688.77 | 2899094.29 | Deferred | 2026 |  | Subsequent Submittal | Deferred to better define project scope. The exisiting approach to management of this asset is expected to address near-term risks.
C0051932 | HYD - Avon 2 Penstock Recoating | 152346.24 | 688897.33 | Deferred | 2027 |  | Less than $1M | Deferred due to reprioritization. The existing approach to management of this asset is expected to address near-term risks.
C0067383 | HYD HMS Electrical Replacement | 135289.83 | 156002.82 | Cancelled |  |  | Less than $1M | This project has been cancelled as further scoping needed before proceeding, and near-term risks being managed by current asset management approach.
C0068703 | HYD COW Battery Bank Replacement | 78186.77 | 90747.36 | Deferred | 2027 |  | Less than $1M | Deferred due to reprioritization. The existing approach to asset management of this asset is expected to address near-term risks.
C0039046 | LIN Ash Silo Refurbishment 2024 | 197598.96 | 214456.09 | Cancelled |  |  | Less than $1M | This project has been cancelled, as updated condition assessment revealed the risk does not need immediate mitigation.
C0061340 | LIN12 Diesel Generator Room Refurbishment | 336843.09 | 365588.87 | Cancelled |  |  | Less than $1M | This project has been cancelled, as updated condition assessment revealed the risk does not need immediate mitigation.
C0068144 | LIN Coal Amenities Trailer Replacement | 302813.1 | 331363.08 | Cancelled |  |  | Less than $1M | This project has been cancelled, as updated condition assessment revealed the risk does not need immediate mitigation.
C0068150 | LIN Coal Stacker Refurbishment 2025 | 135428.15 | 147338.25 | Cancelled |  |  | Less than $1M | This project has been cancelled, as updated condition assessment revealed the risk does not need immediate mitigation.
C0068184 | LIN HFO/LFO Line Refurbishment 2025 | 195187.05 | 212426.82 | Cancelled |  |  | Less than $1M | This project has been cancelled. Project scope will be completed as part of CI C0060819 LIN HFO/LFO Line Refurbishment 2024.
C0068186 | LIN Kubota Replacement 2025 | 36673.92 | 43971.91 | Cancelled |  |  | Less than $1M | Cancelled due to U&U capital work utilizing available resources. Kubota will not be replaced.
C0068226 | LIN1 SoER Installation 2025 | 227364.16 | 246717.16 | Cancelled |  |  | Less than $1M | Cancelled due to U&U capital work utilizing available resources. The exisiting approach is sufficient to address near-term risks.
C0052536 | POA Demin Tank Heater | 86962.76 | 98962.76 | Cancelled |  |  | Pt. Aconi | Cancelled due to U&U capital work utilizing available resources. The exisiting approach is sufficient to address near-term risks.
C0068039 | POA Sootblower Refurb 2025 | 102854.41 | 117854.41 | Deferred | 2027 |  | Pt. Aconi | Deferred due to U&U capital work utilizing available resources. The existing approach to management of this asset is expected to address near-term risks.
C0068687 | TRE6 "A" and "B" CW Screens Refurb | 177892.12 | 192892.12 | Deferred | 2026 |  | Less than $1M | Deferred due to U&U capital work utilizing available resources. The existing approach to management of this asset is expected to address near-term risks.
C0059533 | WIN - DIG Gearbox Replacement WTG19 | 716489 | 761741 | Deferred | 2026 |  | Less than $1M | Deferred due to reprioritization. The existing approach to asset management of this asset is expected to address near-term risks.
C0059602 | WIN - DIG Gearbox Replacement WTG10 | 714917 | 782510 | Deferred | 2026 |  | Less than $1M | Deferred due to reprioritization. The existing approach to asset management of this asset is expected to address near-term risks.
Transmission
C0041822 | WRC Spare Cable Replacement & Storage System | 50000 | 189341.81 | Deferred | 2027 |  | Less than $1M | Additional engineering is required before project can progress to construction.
C0011358 | New Bridgewater Substation | 1385538.11 | 18173046.53 | Deferred | 2027 |  | Subsequent Submittal | Additional engineering is required before project can progress to construction.
C0032382 | Susie Lake Substation Addition | 5149415.34 | 13954518.14 | Deferred | 2026 |  | Subsequent Submittal | Additional engineering is required before project can progress to construction.
C0053214 | 76W-T1 Transformer Replacement | 1938848.22 | 2279294.98 | Deferred | 2026 |  | Subsequent Submittal | Project now forecasted for 2026 ACE request approval. Project had been deferred as additional engineering was required before project could progress to construction.
C0072808 | Synchronous Condensers (ECEI) | 27197774.37 | 243807241.41 | Deferred | 2026 |  | Subsequent Submittal | Project now forecasted for filing in 2026, as preliminary engineering and planning work continues throughout 2025 and is required prior to submission.
C0061552 | L6043 Replacements and Upgrades | 796676.93 | 1346808.78 | Deferred | 2027 |  | Subsequent Submittal | Deferred to better define project scope.
Distribution
C0071410 | 25W-301 Welshtown Phase Addition | 322773.58 | 594945.14 | Deferred | 2026 |  | Less than $1M | Deferred due to reprioritization of projects in the West. The existing approach to asset management of this asset is expected to address near-term risks.
General Plant
C0071652 | IT - ZTN Security and Restrictive Network Controls | 725124.01 | 869124.01 | Cancelled |  |  | Less than $1M | Scope of this project included in C0061289 - IT - Network Next Generation Security Design.
C0032202 | Sydney T&D Depot Consolidation | 1578174.34 | 1879855.12 | Deferred | 2026 |  | Subsequent Submittal | Deferred to better define project scope.
C0021835 | IT - CIS Replacement | 2243592.31 | 77890770.6 | Deferred | 2026 |  | Subsequent Submittal | This project is delayed due to the cyber event. Resources were required for priority restoration.
C0047278 | IT - Oracle MDM Upgrade | 912788.84 | 3010689.35 | Deferred | 2026 |  | Subsequent Submittal | This project is delayed due to the cyber event. Resources were required for priority restoration.
C0061285 | IT - Enterprise Governance, Risk, and Compliance | 664055.55 | 1179857.28 | Deferred | 2026 |  | Subsequent Submittal | This project is delayed due to the cyber event. Resources were required for priority restoration.
C0061347 | IT - Wireless Video Solution | 56424.26 | 72924.26 | Deferred | 2026 |  | Less than $1M | This project is delayed due to the cyber event. Resources were required for priority restoration.
C0068719 | IT - Distributed Intelligence Apps | 2086439.96 | 4353461.11 | Deferred | 2026 |  | Subsequent Submittal | This project is delayed due to the cyber event. Resources were required for priority restoration.
C0068718 | IT - DERMS Solution Project | 1950046.61 | 2993199.75 | Deferred | 2026 |  | Subsequent Submittal | Deferred to better define project scope through the Distributed Energy Resource Integration Roadmap.
C0068714 | IT - Identity and Access Management | 963267.04 | 1275524.12 | Deferred | 2026 |  | Subsequent Submittal | This project is delayed due to the cyber event. Resources were required for priority restoration.
C0067863 | IT - Managed Detect & Respond | 668280.04 | 1126412.56 | Deferred | 2026 |  | Subsequent Submittal | This project is delayed due to the cyber event. Resources were required for priority restoration.

## R4 - FIN Report
NS Power Final Cost Report
3rd Quarter Overview - as of September 30, 2025
This report includes a list of all FIN capital work orders that have fallen outside the timelines under the CEJC. (Within six months of in-service.)
These projects have either been completed and are outside the FIN tolerances or forecast to be outside of the FIN tolerances. (The greater of +/- 5% or +/- $250,000.)
Projects that have been in-service for 6 months, but have a project forecast within the allowed FIN tolerance, are not included on this list.
Project # | Project | In-service Date | NSEB Approval | Spend to September 30, 2025 | Comment
C0031145 | 2021 Padmount Replacement Program | 2021-03-31 | 1636152.76 | 1176603.75 | This project is now complete and a Final Cost Application is planned for submission in 2026.
51956 | 6P Mobile Substation Rewind | 2019-01-31 | 1516120.57 | 635776 | FIN CWO submitted to NSEB on December 1, 2025
52314 | 1C-GT1/UT1 Replacement | 2020-11-30 | 2032393 | 1678006 | FIN CWO submitted to NSEB on December 1, 2025
C0042166 | IT - Data Loss Prevention (DLP) Platform | 2023-11-30 | 4261239.1945 | 3944010 | This project is now complete; however, the final cost application is being held until the functionality of the asset has been confirmed, pending findings relating to the Cyber Incident investigation.
C0043010 | 2022/2023 Wood Pole Retreatment Program | 2022-09-30 | 1300037.21 | 791054 | FIN CWO submitted to NSEB on October 6, 2025
C0010778 | Smart Grid Nova Scotia Project | 2020-05-31 | 7053622 | 6409669.6 | This project is now complete, however, final costs are dependent on final asset disposition treatment under the SGNS Asset Disposition proceeding (M12178).