## Sheet1
CI# | Project Long Title | (i)Approval Mechanism | (ii)Approved Budget (no Contingency) | (iii)Approved Contingency | (iv)Actual Cost | (v)
C0031069 | L6020 Replacements and Upgrades | ACE 2021 | 1681215.29 | 144084.99 | 1520928.86 | Under budget. FIN approved by NSEB
C0031085 | L6516 Line Replacement and Upgrades | ACE 2021 | 2513759.81 | 216832 | 2542897.02 | Over budget by < 5%
C0041789 | L5550 Replacements and Upgrades Phase 2 | ACE 2022 | 2392219.06 | 306295.75 | 2094295.07 | Under budget. FIN approved by NSEB
C0041793 | L7002 Replacements and Upgrades Phase 2 | ACE 2022 | 3640960 | 417551 | 3856784.58 | Over budget. Increased costs are due to more difficult access to the strucures.
C0041796 | L6020 Replacements and Upgrades Phase 2 | ACE 2022 | 2232472.86 | 285770.11 | 3281196.14 | Over budget. Additional structure replacements were required. FIN/ATO filed and approved by NSEB
C0041800 | L5537 Replacements and Upgrades | ACE 2022 | 1126404.16 | 144294.25 | 648216.14 | Under budget. FIN approved by NSEB
C0041805 | L7005 Replacements and Upgrades Phase 2 | ACE 2022 | 2818776.64 | 363741.47 | 2910505.47 | Over budget by < 5%
C0041810 | L5022 Replacements and Upgrades | ACE 2022 | 1927706.53 | 244493.65 | 1618002.65 | Under budget. FIN approved by NSEB
C0011339 | L6549 Replacements and Upgrades Phase 2 | ACE 2019 | 2041364 | 168543 | 3904481.05 | Over budget. ATO filed and approved by NSEB
C0043010 | 2022-2023 Wood Pole Retreatment Program | ACE 2022 | 1300037.21 | 98320.1 | 791054 | Under budget. FIN filed with NSEB

## Sheet4 (hidden)
Cc Cpc | Fp Number | Funding Project Descr | Proj To Date Actuals
| 28111-T518 | 81S RESERVE ST ADD ONE 69KV BREAKER | 566525.86
| 25184-T514 | REPLACE BREAKER 50W-515 | 164182.71
| 27769-T519 | POLE RETREATMENT PROGRAM 2006 | 588552.53
| 27773-T529 | 2006 STEEL TOWER LIFE EXTENSION | 30102.42
| 28172-T522 | ESTIMATE REPLACE BATTERY 120H-D42 A | 47211.33
| 28870-T563 | CAPE PORCUPINE 100C LOW VOLTAGE REP | -1531.88
| 28295-T564 | CONSTRUCT 137H-HAMMONDS PLAINS RD. | 4003879.33
| 28481-T546 | L8004 RELAY PROTECTION REPLACEMENT | 143191.88
| CONV-T424 | T424-REPLACE FAILED 95H-T1 AT MALAY | 71377.73
| 24003-T470 | 64V-T1 REWIND FAILED POWER TRANSFOR | 380815.34
| 26021-T486 | REPAIR 138KV SF6 BREAKER 88S-711 AN | 194926.17
| CONV-T490 | T490-Replace 91H-514 & 529 Switches | 109400.04
| CONV-T503 | T503-L6012 Replace Tower Peaks | 48199.76
| 39195-T636 | Statia Wind Project | -3888.59
| 27266-T500 | ONSLOW REPLACE 67N-R311 REACTOR | 21501.06
| 28463-T536 | RELOCATE L-5535 RAYNARD LAKE RESERV | 113269.9
| 28468-T538 | RAISE L5017 OVER HWY 101 | 11367.2
| 28218-T531 | REPLACE RADS 81S-T1 | 54805
| 36412-T607 | Relocate L6511 | -376.78
| 29016-T577 | INSTALL CIRCUIT SWITCHER 100C-CAPE | 163275.98
| 29562-T576 | 15S Replace Rads and Bushings | 147126.3
| 37043-T614 | 2009 Upgrade L7011 | 1373133.73
| 38122-T684 | 2010 PCB Equip. Removal/Destruction | 1638107.45
| 37067-T612 | 2009 Upgrade L6518 | 199876.91
| 40867-T697 | 59C-T61 Transformer Refurbishment | 898807.94
| 42566-T714 | Upgrade L7001 | 196398.67
Transmission Line | 41391-T728 | L6025 Spar Arm Reinforcement | 834833.52
Substation Operations | 41426-T733 | 2012 Transmission Switch & Breaker | 2122459.57
Trans - Replace / Refurb | 42636-T723 | L6539 Upgrade | 225376.74
Substation Operations | 41437-T739 | 104H-T62 Kempt Rd Transf Rewind | 1151315.99
Substation Operations | 41390-T744 | 7V Methals Hydro Transformer Replac | 382465.8
Transmission Line | 44314-T769 | L5003 Upgrade | 91619.98
Substation Operations | 44974-T799 | 2014 PCB Equipment Removals | 1262145.86
Substation Operations | 44973-T803 | 2014 Subst Recloser Replacement | 442020.17
Transmission Line | 45651-T792 | L8004 Upgrade | 125986.98
Capital Projects Group - Transmission | 46591-T828 | 88S Lingan Replace 230kV GIS | 14858073.85
Capital Projects Group - Transmission | 46513-T827 | 3C Port Hastings BPS Upgrade | 3315242.44
Transmission Line | 46335-T838 | L5511 Replacements | 569221.84
Transmission Line | 46337-T840 | L6535/L6551 Insulator Replacements | 377198.53
Transmission Line | 47221-T852 | L5015 Avon to Three Mile Plains | 40267.97
Substation Operations | 48066-T880 | 2016 PCB Removal - Substation | 3526302.04
Transmission Line | 48116-T883 | 2016 Sacrificial Anode Installation | 1198819.71
Transmission Line | 48597-T897 | L5530A Replacements and Upgrades | 215817.67
Substation Operations | 49253-T910 | U&U 20V-T1 Transformer Replacement | 953531.29
Transmission Line | 49378-T916 | L6517 Replacements and Upgrades | 379099.55
Transmission Line | 49381-T919 | L7014 Replacements and Upgrades | 304954.38
Substation Operations | 48057-T965 | Replace 69kV cables between 2S& 83S | 598079.14
Transmission Line | 51916-T973 | L-5003 2017R Replacements and Upgr. | 178482.68
Transmission Line | 51111-T950 | L5037 Replacements and Upgrades | 369170.98
Substation Operations | 52241 | 16V-T2 Weymouth Hydro Transformer R | 674829.15
Transmission Line | 49788 | L5564 Replacements and Upgrades | 791941.86
Transmission Line | 52320 | L6549 2018 Replacements & Upgrades | 1452522.7
Substation Operations | 52238 | 2018/2019 Capacitor Bank Breaker Re | 300507.77
Transmission Line | C0010949 | T - 2019/2020 Steel Tower Life Ext | 2178231.16
Substation Operations | C0011261 | 101W Port Mersey Expansion | 4455715.54
Transmission Line | C0024724 | Feb 6, 2020 L3 Storm Transmission | 256683.38
Substation Operations | C0024862 | 2020 Unplanned Failures (T003) | 518032.19
Transmission Line | C0011321 | T-L5031-Replacements and Upgrades | 367756.27
Transmission Line | C0021107 | L8001 Replacements and Upgrades PH1 | 2517260.08
Substation Operations | C0032745 | 89H Oil Spill Remediation | 815531.61
AMO - Customer Operations | C0037146 | AMO Transmission Damage Model_ | 43596.94
AMO - Customer Operations | C0031268 | AMO Critical Equipment Online Mon. | 398322.03
Transmission Line | C0042206 | L6002 Michelin Line Relocation | 48749.9
Transmission Line | C0045353 | L5027 Unplanned Repl & Upgr | 778313.14
Transmission Line | C0044590 | L5510 Pioneer Coal Line Relocation | 20049.34
Substation Operations | C0031050 | New Spare Large Autotransformer | 2373032.9
Substation Operations | C0046373 | Jan 14, 2022 Storm - Substation | 39961.59
Substation Operations | C0045510 | 20V-T52 Transformer Replacement | 1425712.63
Transmission Line | C0041804 | 2022 Line Retirement Program | 160541.63
Transmission Line | C0063273 | L6024 Replacements and Upgrades | 535695.03
Transmission Line | C0063384 | L5535 Replacements and Upgrades | 342064.26
Transmission Line | C0064511 | Jan 10, 2024 Level 3 Storm-Transm | 378255.32
Substation Operations | C0061883 | 129H - Kearney Lake Substation Rebu | 14786.87
Substation Operations | C0031047 | 85S New Generator Breakers | 244241.26
Transmission Line | C0061550 | L5031 - Hubbards to East Chester | 212808.69
Transmission Line | C0067111 | L5023 Rebuild | 644851
Substation Operations | 23121-T004-820 | PROVINCIAL- SUBSTATION ADDITIONS & | 11675888.45
| 28077-T517 | 2006 KD RELAY REPLACEMENT | 367461.24
| 27772-T530 | 2006 TRANSMISSION GROUND LINE CLEAR | 902352.83
| 28450-T537 | RELOCATION OF L-5012 TO IMPERIAL OI | 183656.01
| 28802-T559 | WRIGHT AVE LINE EXTENSION | 25743.18
| 24924-T499 | REPLACE BREAKERS 30N-635 AND 1N-619 | 333842.36
| 28472-T556 | 2007 TRANSMISSION LINE CLEARANCE | 641612.95
Transmission Line | 28649-T548 | TRANSMISSION REPLACEMENT ENGINEERIN | 440607.92
| 28477-T552 | UPGRADE 90H 138KV BREAKERS | 57616.79
| 12138-T259 | L6517 AND L6518 PT. HASTINGS TO PT. | 120796.09
| 28243-T532 | REWIND TRANSFORMER 5W-GT1Y DEEP BRO | 246899.34
| 28480-T543 | L5017 UPGRADE LINE CLEARANCES | 136476.87
| 28363-T583 | 55V-WATERVILLE: ADD 7.5/10/12.5 MVA | 699384.7
| 28469-T586 | L6503 RE-INSULATE | 1932151.63
| 29482-T575 | L-5011 Extension of Woodroofe Ave | -0.36
| 34262-T599 | Amherst Wind Farm | 67521.09
| 29622-T571 | L-5033 - Broken Ties/Pole/Aerial ID | 46561.33
| 29842-T601 | Move Line Pt. Tupper Dust Mitigate | 154204.19
| 33563-T604 | 2009 Pole Retreatment | 243884.42
| 38858-T641 | L6002 Deteriorated Replacements | 438688.14
| 38860-T638 | 2010 Pole Retreatment | 387616.75
| 39723-T652 | 104H-T63 Transformer Refurbishment | 759692.52
| 36942-T649 | 1H-B62 Bus Replacement Water St U&U | 1052046.04
| 25391-T683 | 25 kV Bus Keltic Dr | 775762.01
Substation Operations | 41589-T740 | 22N-Church St Replace 25 kV Bus | 803923.54
Trans - New | 41517-T741 | L6535, 6536 & 6514 Upgrades | 2340820.35
Substation Operations | 43226-T762 | 2013 Trans Switch & Breaker Replace | 1774354.07
Trans - Replace / Refurb | 43750-T760 | U&U 22W Barrington Passage | 455031.48
Transmission Line | 43606-T759 | L5549 Upgrade | 577375.68
Transmission Line | 44206-T766 | L5535 Upgrade - Part Of T011 | 182612.01
Trans - Replace / Refurb | 44363-T774 | U&U Replace 58H-T3 Transformer | 293325.22
Substation Operations | 43487-T785 | Add Breaker Backup at 81V and 12V | 119223.28
Transmission Line | 44975-T806 | Sacrificial Anode Installation Ph 1 | 784409.1
Transmission Line | 43205-T808 | L5510 Insulator Replacements | 2908944.23
Substation Operations | 44982-T797 | New Spare Transformer Replac 20W-T1 | 291873.68
Transmission Line | 45033-T812 | L7001 Replacements | 699595.97
Substation Operations | 44977-T813 | 3W Breaker, Switch & Cable Rplacmen | 645757.56
Transmission Line | 46211-T816 | Upgrade L5502 | 141721.13
Substation Operations | 46339-T825 | 120H Replace SVC Controls | 10027941.28
Transmission Line | 47219-T851 | L7005 67N Onslow to 3C Port Hasting | 194841.38
Transmission Line | 47222-T853 | L5521 1N Onslow to 15N Willow Lane | 114739.16
Transmission Line | 45795-T862 | L6503 Replacements | 825251.14
Substation Operations | 43266-T887 | 89S Point Aconi ST2 Replacement | 1524240.2
Substation Operations | 48067-T892 | 2016 Oil Containment Program | 351498.95
Transmission Line | 48604-T909 | L5538 Replacements and Upgrades | 175269.23
Transmission Line | 48599-T899 | L5054 Replacements and Upgrades | 53176.18
Transmission Line | 49505-T920 | L5011 Line Relocation | 17060.42
Transmission Line | 49380-T918 | L6545 Replacements and Upgrades | 56670.85
Transmission Line | 49775-T927 | L5004 Replacements and Upgrades | 1008751.6
Transmission Line | 49813-T926 | 2017 Sacrificial Anode Installation | 1749976.89
MDRR Transmission | 48026-T921 | L-6033/L-6035 CT Ratio Changes 1H | 9098.09
Substation Operations | 49818-T923 | 2017/2018 Tx Switch & Breaker Rplmt | 1096990.7
Transmission Line | 49793-T946 | L7011 Replacements and Upgrades | 4591706.24
Transmission Line | 47956-T932 | L7004 Replacements and Upgrades | 481722.61
Transmission Line | 51404-T970 | 2018/2019 Steel Tower Life Extensio | 2992783.11
Substation Operations | 51974-T971 | Remote Substation Video/Thermal Mon | 427850.88
Substation Operations | 49798-T935 | 2017 Capacitor Bank Breaker Replace | 209820.49
Substation Operations | 51956 | 6P Mobile Substation Rewind | 1056955.81
Transmission Line | 52102 | L5014-2018 Replacements and Upgr | 1038850.04
Substation Operations | 51797 | 2018 Oil Containment Program | 345673.91
Transmission Line | 49779 | T-L6537 Replacements and Upgrades | 2284615.84
Substation Operations | 51318-T961 | L-5055 - 98W-Rio Algom Tin Mine | 12793.63
Substation Operations | C0010978 | T-2019/2020 Tran Switch & Breaker R | 1029498.49
Transmission Line | C0008461 | 2019 Transmission Inspection Prog | -195.93
Substation Operations | C0011850 | T - 2019 Substation Insulator Repla | 52895.17
Substation Operations | C0024486 | 2S-T1 Transformer Replacement | 2821133.52
Customer Reliability | C0024242 | Arc Flash Program Development | 110661.82
Transmission Line | C0023802 | L6515 Replacements and Upgrades | 251682.25
Substation Operations | C0021136 | 6P New High Side Circuit Switcher | 65623.61
Transmission Line | 52317 | 2020 Line Retirement Program | 581079.4
Substation Operations | C0031042 | 5P-MS Rewind | 83017.52
Transmission Line | C0033645 | 2021-2022 Steel Tower Refurbishment | 2181080.64
Substation Operations | C0031283 | 2021 Substation Theft Prevention | 465517.71
Substation Operations | C0027362 | 2020 Petroleum Storage Tank Replace | 556210.89
Transmission Line | C0046375 | Jan 14, 2022 Storm - Transmission | 554405.75
Transmission Line | C0046873 | Jan 29, 2022 Storm - Transmission | 235693.48
Substation Operations | C0043571 | 2022-2023 Transmission Switch & B | 1663051.11
Substation Operations | C0044431 | 2022 - 2023 Capacitor Bank Breaker | 305380.47
Substation Operations | C0048114 | 88S-301 Switchgear Replacement | 923529.2
Transmission Line | C0049652 | 2022 Transmission Inspection Progra | 289955.06
Substation Operations | C0053995 | Sept 23, 2022 Storm Fiona - Subst | 56738.36
Transmission Line | C0041793 | L7002 Replacements and Upgrades Ph2 | 3856784.58
Substation Operations | C0055539 | 10H-T1 Transformer Replacement | 36445.16
Substation Operations | C0058103 | 2023 Merlin Gerin Breaker Replaceme | 510598.1
Transmission Line | C0052299 | 2023 2024 Steel Tower Life Extensio | 705665.6
Transmission Line | C0052634 | L5016 Replacements and Upgrades | 2944568.36
Transmission Line | C0063268 | L5058 Replacements and Upgrades | 285087.75
Transmission Line | C0063272 | L5546 Replacements and Upgrades | 336320.99
Substation Operations | C0064128 | Dec 18, 2023 Level 3 Storm Subs | 2147.76
Substation Operations | C0058902 | Substation Engineering Standards Up | 424181.15
Substation Operations | C0061046 | 2024 Merlin Gerin Breaker Replaceme | 172682.55
Substation Operations | C0050834 | Spare EHV Breaker Replacements | 153.68
Substation Operations | C0069446 | IR 668 - Weavers Mountain Wind | -0.07
Transmission Line | C0061743 | L6038 Realignment | 42029.68
Substation Operations | C0070328 | IR 673 TPIF - Benjamins Mill Wind | -0.02
Substation Operations | C0073188 | Replacement of 87S GT1 H3 Bushing | 486541.88
| 27265-T501 | REFURBISH TRANSFORMER AT 40H-T1 WOO | 564780.97
Substation Operations | 27337-T498 | OVERHAUL 1H-635 & 1H-633 BREAKERS W | 374683.58
| 28169-T525 | REPLACE TWO INTERRUPTERS ON BREAKER | 4265.75
| 28661-T551 | L6536 NB/NS TIE LINE | 234844.53
| 28483-T544 | L6511 UPGRADE LINE CLEARANCES | 201734.53
| 29099-T565 | L7011 PT HASTINGS 3C TO LINGAN 88S | 2420842.71
| CONV-T300 | T300-L6013 CANAAN RD.TO TREMONT | 102267.67
Substation Operations | CONV-T016-610 | T016-PROTECTION MOD ContCent | 2116.33
| 37942-T623 | Nuttby Mountain Wind Project Substa | 2939879.34
| CONV-T492 | T492-Replace Conical Insulators at | 108035.93
| CONV-T509 | T509-L6002 Pine Grove Rd. Raise Cle | 21333.55
| 28619-T541 | L6001 & L6535 GUSSET PLATES REPLACE | 123153.16
| 37065-T610 | 2009 Upgrade L6516 | 654931.48
| 37062-T615 | 2009 Upgrade L6004 | 285960.48
Trans - Replace / Refurb | 38732-T650 | 1H Water St Replace 138 kV GIS | 8584762.19
| 40281-T668 | 2011 Tx Line Insulator Replacement | 3986553.24
| 11004-T669 | Canaan Rd Circuit Breaker Additions | 2129493.04
| 39627-T693 | Digby Wind Project Trans Line | 4174697.88
| 42006-T702 | 7N Remote Grnd Electrode Connection | -41.86
Transmission Line | 41536-T699 | 2012 Reliability Technology Trans. | 627061.69
Substation Operations | 41430-T707 | 2012 Subst. Recloser Replacement | 1913554.62
Transmission Line | 42633-T720 | L6005B Upgrade | 304292.14
Trans - New | 43293-T755 | Brushy Hill Protect Upgrade (138KV) | 2650781.44
Transmission Line | 43323-T756 | Tuft's Cove Line Swap | 281415.91
Substation Operations | 43231-T758 | 2013 Substation PCB Equip Removal | 797063.07
Transmission Line | 43786-T768 | 2013 L8002 Tower Refurbishments | 2480929.31
Substation Operations | 43726-T778 | Replace 3N-T51 Transformer | 825135.97
Wind Generation - South Canoe | 43683-T789 | South Canoe Wind Project Tx Line | 5179766.65
Substation Operations | 43489-T773 | 8H Substation Retirement | 42507.92
Capital Projects Group | 43291-T786 | 67N-Onslow BPS Upgrades 230KV | 3362634.16
Wind Generation - Sable | 46771-T823 | Sable Wind Collector System | 1085295.48
Substation Operations | 46340-T833 | 2015 Switch & Breaker Replacements | 1505923.87
Substation Operations | 46353-T834 | 2015 Substation Recloser Replacemen | 387388.87
Transmission Line | 47214-T845 | L5551 79W Lunenburg to 80W Indian P | 87764.58
Capital Projects Group - Transmission | 46587-T856 | Metro Voltage Support Add Capacitor | 3234346.57
Transmission Line | 46331-T837 | L7001 Replacements - Phase 2 | 822290.77
Capital Projects Group - Transmission | 46757-T867 | 88S Lingan 230kV BPS Upgrades | 3296759.76
Transmission Line | 46362-T843 | L5560 Reconductor | 799126.5
Transmission Line | 48113-T882 | 2016 Steel Tower Refurbishment | 1940802
Substation Operations | 48062-T878 | 2016 Reactor Breaker Replacements | 572352.34
MDRR Transmission | 48022-T888 | Spider Lake Substation Addition | 9066397.53
Transmission Line | 47935-T875 | L5040 Replacements | 1107608.74
Substation Operations | 48112-T906 | 11W King Street Substation Ret | 72516.42
Substation Operations | 49795-T941 | 100C Cape Porcupine Switch Addition | 248377.98
Substation Operations | 49821-T940 | Mersey River Hydro Spare Transformr | 439279.61
Transmission Line | 51901-T972 | L-6010 2017R Replacements and Upg | 139181.78
Transmission Line | 49790-T959 | L5505 Replacements and Upgrades | 816588.04
Transmission Line | 51405 | 2018 Wood Pole Retreatment Program | 924520.55
Transmission Line | C0011243 | T-L5551 -Replacements and Upgrades | 1115386.39
Substation Operations | C0013938 | Lingan SF6 Bus Refurbishment | 249072.59
Transmission Line | C0010948 | T-2019/2020 Sacrificial Anode Inst | 3244208.44
Substation Operations | C0022283 | 58C-T1 Margaree Failed Transformer | 778806.88
Substation Operations | C0026102 | 2020 Substation Theft Prevention | -22100.19
Substation Operations | C0025384 | 9W-517 & 529 Capbank Civil Work | 87472.21
Substation Operations | C0021026 | Replace Willow Lane Power Transform | 1179586.14
Substation Operations | C0022247 | 1N-Onslow 138 kV Add Second 42 MVA | 1462694.5
Transmission Line | C0021106 | L7005 Replacements and Upgrades PH1 | 3136430.06
Substation Operations | C0032829 | 1C-GT2 LV Enclosure Cooling System | 1092.7
Transmission Line | C0035846 | 2021 Transmission Inspection Progra | 1944.13
Substation Operations | C0031273 | Substation Ground Grid Replacements | 19288.21
Substation Operations | C0040566 | 69kV System Assessment | 83523.72
Substation Operations | C0061931 | Sept 16 2023 - Hurricane Lee Substa | 82183.83
Transmission Line | C0041807 | L5534 Replacements and Upgrades | 1555748.02
Transmission Line | C0061703 | L5028 LaFarge Transmission Tap Rebu | -32625.32
Substation Operations | C0062447 | Dec 11, 2023 Level 3 Storm - Substa | 1495.74
Transmission Line | C0063271 | L8001 Ice Damage Replacements | 322134.48
Substation Operations | C0050852 | 10V-T1 Transformer Replacement | 15303.12
Transmission Line | C0061403 | 2024 2025 Sacrificial Anode Install | 1693672.68
Transmission Line | C0061529 | L6001 Replacements and Upgrades | 274360.91
Substation Operations | C0064903 | IR 664 - 99W Bridgewater BESS TPIF | 25749.91
Substation Operations | C0070327 | IR 673 NU - Benjamins Mill Wind | -0.01
Substation Operations | C0070386 | IR 618 TPIF - Goose Harbour Lake Wi | -0.01
Substation Operations | C0068969 | 2026 Pennsylvania Breaker Replaceme | 813.23
| 27524-T502 | LND TERMINAL @ BEAR HEAD ENVIRONMEN | -22675.33
Capital Projects Group | 28164-T516 | CBPL WIND FARM LINGAN | -225370.14
| 25116-T515 | RETIRE 13N-WALKER ST SUBSTATION | 49400.2
| CONV-T504 | T504-Replace Tower Peaks | 164678.37
Substation Operations | CONV-T016-820 | T016-PROTECTION MOD.CC820 | 475693.84
| 28789-T558 | INSTALLATION OF SUBSTATION SECURITY | 319831.46
| 28471-T554 | TOWER INSTALLATION L7001 BEAVER NAR | 570224.82
| 28478-T549 | L6033 & L6035 Tower Footing Restora | 141560.13
Substation Operations | 20916-T004-743 | TRANSMISSION SUBSTATION ADDITION/MO | 155785.64
Substation Operations | 29013-T592 | 82V Elmsdale Transformer Addition | 2919966.94
| 18990-T489 | RETIRE 1S SEABOARD SUBSTATION | 237656.05
Transmission Line | 25425-T493 | RETIRE 100S AND L-7016 | 90560.87
| CONV-T494 | T494-Retire 9S Sysco North & Portio | 1550.12
| 28476-T555 | 2007 TRANSMISSION LINE LIDAR SURVEY | 6268.87
| 29001-T582 | 2008 POLE RETREATMENT PROGRAM | 465809.14
| 28702-T588 | REPLACE BRIDGEWATER TRANSFORMER 89W | 1773083.98
| 37068-T616 | 2009 Upgrade L7002 | 201884.25
Transmission Line | 33542-T617 | Upgrade L-8002 2009 | 1188672.88
| 35202-T621 | St. Croix to Avon - Reconductor 69 | 662099.45
| 39812-T640 | L5563 Re-conductor | 149448.69
| 40185-T653 | 104H-T61 Transformer Refurbishment | 882423.59
| 40726-T659 | L6513 Upgrade | 273421.82
| 40862-T696 | 101H-T61 Transformer Refurbishment | 913124.52
Capital Projects Group - Transmission | 40327-T695 | Glen Dhu 138 kV Substation | 3406923.82
Transmission Line | 42628-T717 | L5031 Upgrade | 151090.6
Capital Projects Group | 41348-T726 | 2012 Protection Upgrades Onslow | 2363221.76
Trans - Replace / Refurb | 42627-T716 | L5004 Upgrade | 254635.77
Substation Operations | 41550-T704 | Spare 30MVA 69KV 25/12KV Trans. | 523868.4
Transmission Line | 42635-T722 | L7012 Upgrade | 250065.5
Substation Operations | 41399-T729 | 2012 Subst Insulator & Cutout Repla | 431154.1
| 43187-T742 | U&U L8002 Tower Refurbishment | 276635.35
Substation Operations | CONV-T003-800 | T003-TRANSMISSION SUBSTATION REPLAC | -18276.78
Trans - New | 41422-T736 | Onslow Spares Storage Upgrades | 379545.36
Substation Operations | 44092-T765 | 91W Transformer Replacement | 327396.23
Transmission Line | 44316-T771 | L6015 Upgrade | 124419.42
Substation Operations | 45182-T784 | U&U - 40H Install 25kV Transformer | 119931.01
Maritime Link Transmission | 43678-T800 | Separate L8004/L7005 | 20387277.51
Transmission Line | 45797-T817 | L7004 Upgrade | 523137.52
Substation Operations | 44990-T796 | 104S Switch Replacement & Addition | 115602.71
Transmission Line | 45794-T814 | L5040 Upgrade | 655354.98
Transmission Line | 47220-T861 | L5027A 9W, 20W and 22W | 68982.09
Transmission Line | 47131-T858 | L8001 Structure 58 Replacement | 830603.41
Substation Operations | 48061-T884 | New Mobile Substation 7.5MVA | 2535247.21
Substation Operations | 46811-T872 | 2H Armdale Transformer Addition | 2816042.97
Transmission Line | 48114-T893 | 2016 Steel Tower Life Extension | 1519276.91
Telecom | 46366-T854 | 65V Middleton Substation RTU Add | 190198.91
Transmission Line | 49052-T908 | L5506 Pictou Roundabout Line | 88052.53
Transmission Line | 49373-T912 | L5544 Replacements and Upgrades | 92319.48
Transmission Line | 49376-T915 | L6011 Replacements and Upgrades | 75385.34
Transmission Line | 49789-T925 | L6515 Replacements and Upgrades | 2590653.46
Transmission Line | 49815-T929 | 2017 Steel Tower Refurbishment | 1937432.56
Substation Operations | 49838-T924 | 2017 Substation PCB Equip Rplcmnt | 4334511.53
Transmission Line | 49776-T933 | L7008 Replacements and Upgrades | 733883.93
Substation Operations | 49929-T945 | Tap Changer Replacements | 518589
Transmission Line | 49782-T958 | L5027B Replacements and Upgrades | 1532095.81
Capital Projects Group - Transmission | 51098-T952 | L-6014 Shannon Park Trans Towers | 1043035.15
Vegetation Management | 51969 | 2018 Transmission ROW Widening 69kV | 5542106.33
Substation Operations | 51406 | 2018/2019 Transmission Switch & Bre | 1136172.52
Transmission Line | 52119 | L5054 2018 Replacements and Upgra | 784720.25
Substation Operations | C0005040 | T-2V-T41 Refurb and Support Str Rep | 165302.99
Substation Operations | 48131 | 48H-T1 Replacement | 1517266.05
Substation Operations | C0013920 | 2019 Substation Storm Replacements | 8963.64
Vegetation Management | C0010042 | 2019 Transmission ROW Widening 69kV | 5633875.15
Substation Operations | C0014040 | 89S-ST1-Neutral Grounding Resistor | 11151.36
Substation Operations | C0021123 | 2020/2021 Substation PCB Equipment | 5365128.57
Substation Operations | C0020743 | Ragged Lake UPS Replacement | 197464.17
Substation Operations | C0021122 | 2020-21 Transmission Switch and Br | 1502538.05
Transmission Line | C0021105 | L7002 Replacements and Upgrades PH1 | 3320026.92
Substation Operations | C0024867 | 67N Leaking CT Replacement (T003) | 30026.37
Substation Operations | C0022744 | 2020 Oil Containment Program | 154274.97
Substation Operations | C0027162 | 129H Kearney Lake Substation Relo | 253928.76
Substation Operations | C0028464 | 12V-T2 Tapchanger Replacement | 180159.88
Substation Operations | C0024870 | 50N-GT5 Regasket and Radiator Repla | 20314.56
Transmission Line | C0035611 | Jan 8th 2021 Ice Storm-Transmission | 70568.12
Substation Operations | C0031263 | 2021/2022 Substation Polychlorinate | 7000003.03
Substation Operations | C0036231 | 88S-704 Switch Repairs | 700.5
Transmission Line | C0031069 | L6020 Replacements and Upgrades | 1520928.86
Vegetation Management | C0031089 | 2021/2022 Trans ROW Widening 69kV | 5512846.46
Transmission Line | C0031064 | L5054 Line Replacements and Upgrade | 1003259.08
Substation Operations | C0024869 | 24C Grounding Transformer Bank Repl | 2572.69
Transmission Line | C0047573 | Feb 18, 2022 Storm - Transmission | 311444.84
Substation Operations | C0047050 | Feb 4, 2022 Storm - Substation | 5971.16
ECEI | C0045132 | ECEI - Energy Storage | 46164467.16
Transmission Line | C0043010 | 2022 2023 Wood Pole Retreatment Prg | 791054.43
Transmission Line | C0055696 | L5031 Replacement & Upgrade R.C Tap | 990465.13
Transmission Line | C0056721 | 2023 Transmission Inspection Progra | 2112590.4
Substation Operations | C0050842 | 2024 Bulk Oil Breaker Replacement | 563382.35
Transmission Line | C0053295 | L5004 Kearney Lake Structure Replac | 235921.04
Transmission Line | C0063274 | L7008 Replacements and Upgrades | 304377.55
Substation Operations | C0053158 | 77V-T52 Transformer Replacement | 16475.7
Substation Operations | C0065024 | IR 662 - 132H Spider Lake BESS TPIF | 35938.61
Transmission Line | C0061546 | L6514 Replacements and Upgrades | 1252889.45
Transmission Line | C0072115 | L5511 Replacements and Upgrades | 706925.19
Substation Operations | C0072609 | 2024 Substation Fence Upgrades | 884152.75
Transmission Line | C0073388 | L8002 Replacements and Upgrades U&U | 457460.99
| 28091-T511 | L-7014 SPECIAL PROTECTION SCHEME | 109263.53
Transmission Line | 23118-T011-820 | PROVINCIAL - PLANNED TRANS LINE REP | 58626646.1
| 27770-T520 | 2006 SURVEY TRANSMISSION LINES | 360866.63
| 27768-T512 | CAPACITOR BANK 36 MVAR AT 99W | 849372.38
Substation Operations | 28609-T560 | 91H-GT3 TRANSFORMER REFURBISHMENT - | 2521980.25
Substation Operations | 14973-T018-820 | PRIMARY EQUIPMENT SPARES | 2840486.25
| CONV-T506 | T506-Replace CP Insulators in Onslo | 36920.32
Trans - New | 28083-T540 | 81W LUNENBURG - INSTALL DIRECT CONN | 31844.16
| 28482-T542 | L5053 UPGRADE LINE CLEARANCES | 100322.05
| 28474-T574 | ST CROIX INSTALL NEW TRANSFORMER & | 4070458.21
| 29643-T572 | L5572-Repair Deficiencies | 75024.59
| 29012-T595 | UPGRADE L6537 | 2234559.37
| 29582-T573 | Replace Breaker 120H-715 | 65496.63
| 29542-T579 | Michilin Tap | 362220
Transmission Line | 29522-T567 | Relocation of L5032 | -0.41
| 34022-T593 | Nuttby Mountain Wind Farm | -2347.69
| 29644-T580 | L5564-Poles/Insulators VJ to Keltic | 117159.11
| 37063-T609 | 2009 Upgrade L6013 | 58198.9
| 40279-T663 | 2011 Pole Retreatment | 508208.1
| 40724-T657 | L5532 Upgrade | 137471.73
| 40728-T661 | L6515 Upgrade | 494165.46
| 40790-T667 | Relocate L6511 and Feeder 4C-430 | -13069.37
Trans - Replace / Refurb | 40285-T677 | 2011 Trans Subst Insulator & Cutout | 878370.09
| 38857-T685 | L7004 Deteriorated Replacements | 2447746.17
Transmission Line | 40266-T671 | L6002 Deteriorated Replacement 2012 | 1102189.41
| 42637-T724 | L6552 Upgrade | 284908.7
Transmission Line | 41432-T713 | L7009 Lidar Upgrades & Maintenance | 3770099.38
| 41592-T732 | 88W New Recloser & Relocate 88W-322 | 135638.07
Substation Operations | 41551-T748 | Glentosh Subst. Footing Remediation | 455177.83
Substation Operations | 40310-T747 | 15N Willow Ln Circuit Switcher Add | 529153.95
Transmission Line | 42634-T721 | L7003 Upgrade | 91653.76
Trans - New | 43292-T754 | 120H-Brushy Hill BPS Upgrades 230KV | 1680583.65
Trans - Replace / Refurb | 44317-T772 | L7019 Upgrade | 135410.37
Substation Operations | 43369-T783 | New Mobile Transformer 15MVA | 1840076.53
Substation Operations | 44980-T798 | 2014 Trans. Switch & Breaker Rplcmn | 1322173.32
Transmission Line | 45792-T810 | L5012 Upgrade | 71268.14
Transmission Line | 46583-T826 | L6511 Upgrade | 783892.35
Transmission Line | 44979-T836 | L5527 Structure Replacements | 756962.24
Transmission Line | 47212-T844 | L5506 55N Pictou to 54N Abercrombie | 339770.86
Transmission Line | 47215-T846 | L6008 90H Sackville to 103H Lakesi | 375923.24
Substation Operations | 43261-T831 | 6V-GT1 Hollow Bridge Hydro Replace | 533267.75
Transmission Line | 47191-T859 | L5536A 9W Tusket to 88W Pleasant St | 253888.4
Substation Operations | 46397-T855 | Substation Telemetry | 204833.29
Substation Operations | 47631-T865 | U&U Capacitor Bank Breaker Rpcmnts | 273736.64
Transmission Line | 47949-T876 | L5028 Replacements and Upgrades | 943265.07
Substation Operations | 44981-T871 | 2C Port Hastings Tx Replacement | 2006133.93
Transmission Line | 48593-T895 | L5016 Replacements and Upgrades | 165791.63
Transmission Line | 47912-T873 | L6552 Replacements and Upgrades | 947929.95
Substation Operations | 49879-T928 | 77V-T52 Replacement | 866855.77
Substation Operations | 49928-T949 | 3S Gannon Rd. Bus Reconfiguration | 835571.74
Transmission Line | 51696-T964 | L7015 Replacements and Upgrades | 400214.81
Transmission Line | 51932-T975 | L6533 2017R Replc and Upgrades | 88204.48
Transmission Line | 51935-T976 | L-5555 2017R Replacements and Upg. | 451121.65
Substation Operations | 52328 | 56N-T1 Transformer Upgrades | 1307910.2
Transmission Line | 51398 | 2018/2019 Steel Tower Refurb | 2054802.01
Gas Turbine Generation | C0013458 | 10W Tusket 69kV Bus Bypass | 189379.32
Substation Operations | C0010952 | 2019/20 Substation PCB Equip Replac | 2686536.39
Substation Operations | C0020162 | Substation Replacement of Grounds | 2747001.16
Transmission Line | C0010950 | T - 2019/2020 Steel Tower Refurb | 2168600.5
Vegetation Management | C0020627 | 2020 Transmission ROW Widening 69kV | 5617281.86
Substation Operations | C0024868 | Battery Bank and Charger Replacemen | 348803.88
Transmission Line | C0024602 | L6537 River Inhabitants Crossing | 437755.73
Substation Operations | C0023182 | 101S Woodbine Reactor Replacement | 456895.09
Substation Operations | C0025382 | 2020 Unknown Additions (T004) | 62295.89
Transmission Line | C0021104 | L5550 Replacements and Upgrades Ph1 | 1818407.89
Substation Operations | C0032382 | Susie Lake Substation Addition | 415322.5
Substation Operations | C0030142 | L6515, L6516 Structures Replacement | 329402.88
Substation Operations | C0022742 | Retire 6S-Terrace Street | 110.93
Transmission Line | C0033644 | 2021-2022 Steel Tower Life Extensio | 1830410.86
Transmission Line | C0041789 | L5550 Replacements and Upgrades Ph2 | 2094295.07
Transmission Line | C0036392 | L6001-366A Highway 102 Aerotech Con | 7879.5
Transmission Line | C0041800 | L5537 Replacements and Upgrades | 648216.14
Substation Operations | C0021140 | 98N-Stellarton Substation | 2670052
Substation Operations | C0041833 | 2022 2023 Bulk Oil Breaker Replace | 1042450.35
Substation Operations | C0041837 | 2022 2023 Substation PCB Equip Remo | 3114753.03
Transmission Line | C0049212 | L8001 Replacements and Upgrades Ph3 | 1208027.05
Transmission Line | C0053976 | Sept 23, 2022 Level 4 Storm Fiona | 1263233.03
Substation Operations | C0055796 | 2023 EHV Breaker Replacements | 62663.93
Substation Operations | C0055557 | 76V-T1 Transformer Replacement | 219311.19
Transmission Line | C0050835 | 2023/2024 Steel Tower Refurbishment | 1295942.47
Substation Operations | C0059403 | 62H Low Voltage Switchgear Replacem | 1517568.37
Vegetation Management | C0052055 | 2023/2024 Trans ROW Widening 69kV | 4947437.85
Transmission Line | C0063275 | L5033 Replacements and Upgrades | 660732.14
Transmission Line | C0064126 | Dec 18, 2023 Level 3 Storm Transmis | 93099.74
Substation Operations | C0062123 | 143H-Mount Uniacke Substation | 1354624.36
Substation Operations | C0011358 | New Bridgewater Substation | 36065.68
Transmission Line | C0061551 | L7009 Replacements and Upgrades Pha | 2091.91
Substation Operations | C0053234 | 96H-T1 Transformer Replacement | 235.8
| 24922-T513 | REPLACE BREAKER 81V-501 | 154264.52
Substation Operations | 23120-T003-820 | PROVINCIAL-TRANS SUBSTATION PRIMARY | 36190126.38
Substation Operations | 14841-T016-630 | PROTECTION MODIFICATIONS AND REPLAC | 8939078.4
| CONV-T465 | T465-StoraEnso 138kV Service Connec | 843352.42
| 24262-T473 | PURCHASE OF SPARE 15/20/25 MVA, 69- | 424564.41
Trans - New | 25185-T479 | CONNECTION OF PUBNICO WIND FARM TO | -4662.67
| 25221-T488 | ADD A 12KV FEEDER CIRCUIT AT BRIDGE | 75903.55
| 28713-T557 | L7003/L7004 TOWER BASE REPLACEMENT | 115914.05
| 28621-T585 | 2008 L5027 INSULATOR REPLACEMENT | 987381.93
| 31662-T587 | L6515-Repair Concrete Foundations | 161891.5
| 29008-T602 | Construct 139H Dartmouth Crossing S | 4680935.77
| 33464-T606 | 2009 Tx Line Insulator Replacement | 685293.2
| 39043-T620 | Relocate L5575 | 225.07
Capital Projects Group | 40430-T648 | PH Biomass Tx Interconnection | 1342899.03
| 40425-T647 | Kempt Road Transformer | 1050733.39
| 40788-T665 | L6538 Upgrade | 177130.08
Trans - Replace / Refurb | 38819-T675 | 51V Tremont Circuit Breaker & Bus | 7437554.33
| 40725-T658 | L5011 Upgrade | 154998.29
| 40233-T662 | 2011 Protection Upgrades TUC | 4173842.31
Substation Operations | 38878-T686 | 2010 Subs Cutout and Insul. Replace | 484669.73
Transmission Line | 38856-T681 | L7011 Deteriorated Replacements | 1756235.87
Substation Operations | 43672-T779 | 82V-T1 Transformer Rewind | 1756776.09
Trans - New | 40323-T679 | Canaan Road Line Terminal | 979179.69
Trans - New | 40321-T687 | Canaan Rd to Highbury Trans Line | 2044742.03
Substation Operations | 38027-T700 | 2010 Trans Switch & Breaker Upgrade | 2059889.68
Substation Operations | 41429-T730 | 2012 Subst PCB Equipment Removal | 1282336.85
Transmission Line | 42629-T718 | L5575 Upgrade | 95751.95
| 41386-T735 | 2012 Pole Retreatment | 540418.94
| 39590-T725 | Upgrade L5547 | 93096.55
Substation Operations | 41555-T738 | Spare Wind Farm Gen. Transformer | 776283.2
Transmission Line | 43260-T746 | 2013 Trans Line Insulator Replace | 303626.16
Transmission Line | 44228-T767 | L5026 Upgrade Pole & Arm Replacmnt | 101697.51
Substation Operations | 43427-T776 | 62N-510 Breaker & Control Replace | 515620.29
Trans - Replace / Refurb | 44315-T770 | L6002 Upgrade | 725241.78
Wind Generation - South Canoe | 43681-T788 | South Canoe Subs. Network Upgrades | 4270257.6
Wind Generation - Sable | 43674-T793 | Sable Wind Network Upgrades | 835040.36
Maritime Link Transmission | 45066-T802 | Upgrade L6511 and L7019 | 2691016.62
Substation Operations | 44985-T807 | Replace 230kV Kearney Disconnect Sw | 352433.75
Transmission Line | 45793-T811 | L5028 Upgrade 2014 | 195188.76
Substation Operations | 44976-T832 | 10H 25kV Breaker Rplcmnt & Reconfig | 1157139.93
Transmission Line | 47218-T848 | L5563 2S VJ to 4STownsend St | 216079.99
Transmission Line | 46333-T864 | L6538 Replacements | 911299.45
Substation Operations | 48059-T877 | 2016 Switch and Breaker Replacement | 1178775.49
Transmission Line | 49374-T913 | L6002 Replacements and Upgrades | 96089.92
Transmission Line | 47950-T881 | L-5017 Replacements & Upgrades | 3012632.2
Vegetation Management | 49992-T938 | 2017 Transmission ROW Widening 69kV | 5494422.68
Substation Operations | 49922-T939 | Western Switching Upgrades | 650673.92
Transmission Line | 51092-T947 | L5011 Replacements and Upgrades | 351271.54
Substation Operations | 52305 | 2018 Substation Insulator Replc | 323830.05
Substation Operations | 51403 | T-2018 PCB Removal Program | 3518852.44
Substation Operations | C0007538 | 87S-GT3 Pipe Replacements | 33291.22
Transmission Line | 49371-T911 | L5039 Replacements and Upgrades | 192565.52
Transmission Line | 52059 | L5039 - 2018 Replacements and Upgr | 795229.29
Substation Operations | 51863 | 2018 Tap Changer Replacements | 417340.3
Transmission Line | 52258 | 2018/2019 Isolated Structure Replac | 294849.4
Transmission Line | C0011240 | T-L5511 -Replacements and Upgrades | 1485115.59
Transmission Line | C0017198 | 2019 Transmission LiDAR | 69720.15
Substation Operations | C0011918 | T-2019 Oil Containment Program | 585411.58
Substation Operations | 52261 | 83V-503 & 83V-504 - Bring Switches | 185723.32
Transmission Line | C0022322 | Sep 2019 - Hurricane Dorian - Trans | 504851.84
Transmission Line | 52285 | L5524 Replacements & Upgrades | 2274544.83
Substation Operations | C0024875 | 30W Deteriorated Bus Structure Repl | 227159.53
AMO - Customer Operations | C0026342 | AMO Substation Test Equipment | 262271.76
Substation Operations | C0021130 | 48H Metalclad Switchgear Replacemen | 1391009.19
Substation Operations | C0034209 | 1C-GT2 Transformer Failure | 168496.98
Substation Operations | C0024872 | Lingan New Coolers (T003) | 17813.32
Substation Operations | C0035647 | 2021 Unplanned Failures (T003) | 1165239.83
Substation Operations | C0035651 | 2021 Battery Bank & Charger Replace | 175339.68
Substation Operations | C0036187 | 3C-T71 Transformer Refurbishment | 45517.25
Transmission Line | C0031122 | L6539-2021 Replacements and Upgrade | 1247483.77
Substation Operations | C0031298 | 88S-T72 New Radiators | 93551.87
Substation Operations | C0041830 | Spare Power Prod Unit Transformer | 6799.27
Substation Operations | C0059046 | 101S and 79N Reactor Replacements | 802549.11
Substation Operations | C0056240 | 2024-2025 Transmission Switch & Bre | 2526854.37
Substation Operations | C0057882 | 2024 Pennsylvania Breaker Replace | 380841.42
Corporate Initiatives | C0060866 | Everwind 230kV Transmission Line | 90570.65
Transmission Line | C0041812 | L6040 Replacements and Upgrades | 9131.65
Transmission Line | C0063264 | L5573 Replacements and Upgrades | 275493.31
Transmission Line | C0063270 | L8002 Replacements and Upgrades | 261785.37
Transmission Line | C0061543 | L5048 Replacements and Upgrades | 911821.95
Substation Operations | C0053214 | 76W-T1 Transformer Replacement | 40927.15
AMO - Customer Operations | C0058703 | AMO 69kV Lightning Arrester Assessm | 94919.07
Transmission Line | C0067112 | L5012 Replacements and Upgrades | 1213248.97
Transmission Line | C0061545 | L6006 Replacements and Upgrades | 3107442.41
Substation Operations | C0069535 | IR 669 TPIF - Higgins Mountain Wind | -0.01
Substation Operations | C0068868 | Fall River Substation Addition | 14622.23
Substation Operations | C0070086 | 10H-T2 Transformer Replacement | 16217.1
Substation Operations | C0070586 | 22N-603 and 604 Switch Repl L6536 | 963.41
| 26330-T496 | INSTALLATION OF ON-LINE GAS MONITOR | 136706.05
Transmission Line | 23115-T001-820 | PROVINCIAL TRANSMISSION LINE REPLAC | 29670610.8
| 28375-T533 | L6001 - REINSULATE; REPLACE DAMPERS | 516923.05
| 28167-T527 | REPLACE TAPCHANGER PARTS AT 124H AK | 167670.14
| 29098-T566 | L6002 REINSULATE | 1073542.95
Capital Projects Group | 38818-T637 | Valley Protection Upgrades | 247804.02
| CONV-T016-810 | T016-PROTECTION MOD.Elec Insp | 5962.62
Substation Operations | 16103-T405 | FARRELL ST. - CONSTRUCT 69-12KV SUB | 595250.08
| 22131-T447 | REWIND 4P-MS MOBILE TRANSFORMER | 407325.51
Transmission Line | 25918-T507 | LM6000 TUC #5 TRANSMISSION | 670476.32
| CONV-T510 | T510-Replacement of L6003/L6007 Tow | 845544.58
| 28186-T528 | L7011 2006 MISCELLANEOUS UPGRADES | 490035.24
| 37944-T624 | Nuttby Mountain Wind Project Trans | 562863.98
Substation Operations | 29010-T596 | Install 138-25KV Transformer At 22C | 2338356.15
| 30845-T581 | L5004 Move Structures for HRM | 2069.75
| 29623-T570 | L-5534 - Bad poles and Insulators | 83291.89
| 29642-T569 | L-5550 - Poles/X Braces/Rusted Guy | 53564.47
| 37064-T613 | 2009 Upgrade Line 6515 | 41895.96
| 37042-T608 | 2009 Upgrade L5510 | 109385.8
| 37066-T611 | 2009 Upgrade L6517 | 82412.39
| 35862-T622 | 2009 Transmission Switching Improve | 804676.01
Substation Operations | 33624-T639 | Spare Generator Transformer | 3520466.49
| 39647-T644 | L5500 - Widening East River Rd | -6.85
| 40722-T655 | L5028 Upgrade | 283944.99
Transmission Line | 40787-T664 | L5546 Upgrade | 85512.51
Transmission Line | 40260-T689 | L7012 Upgrades | 1099112.2
Transmission Line | 40270-T672 | Upgrade 69 kV Circuit to Bridge Ave | 718294.04
Capital Projects Group - Transmission | 41537-T706 | Amherst 138kV Substation | 2718541.73
Substation Operations | 40288-T690 | 2011 PCB Equipment Removals | 1805617.49
Capital Projects Group - Transmission | 39628-T694 | Digby Wind Project Interconnect | 3958086.01
Capital Projects Group | 39626-T692 | Digby Wind Project Substation | 4332406.3
Substation Operations | 40868-T698 | 64V-T1 Transformer Replacement | 679938.19
Capital Projects Group | 40317-T703 | 1H Transformer & Breaker Addition | 4330201
Transmission Line | 38110-T701 | 2010 Tx Line Insulator Replacement | 1490348.72
Transmission Line | 42526-T711 | L6004 Replacements | 179250.98
Substation Operations | 41439-T712 | 5P & 6P Mobile Substation Upgrades | 468640.28
| 42632-T719 | L5530A Upgrade | 135746.11
| 42758-T734 | 9W Tusket B52 Structure Replacement | 273013.32
Substation Operations | 41434-T737 | Purchase New 42 MVA Spare Transform | 716220.74
Transmission Line | 41535-T745 | 2012 Steel Tower Painting | 1701690.56
| 43351-T743 | L5535 Upgrade | 101271.27
Transmission Line | 44166-T764 | L6531 Upgrade | 108685.76
Maritime Link Transmission | 43324-T782 | Replace L6513 / Upgrade Line Termin | 18625081.5
Wind Generation - South Canoe | 43684-T790 | Interconection Substation South Can | 7981090.01
Wind Generation - Sable | 43676-T795 | Interconnection Substation Sable | 1208366.32
Wind Generation - Sable | 43675-T794 | Transmission Interconnection Sable | 478660.11
Substation Operations | 44983-T809 | Reactor Bank Breaker Replacements | 415813.52
Trans - Replace / Refurb | 45796-T815 | L6516 Upgrade | 493256.93
Substation Operations | 45882-T819 | 103H-T63 Transformer Replacement | 1402349.23
Transmission Line | 46872-T829 | L6518 Replacement | 296981.06
Substation Operations | 45306-T822 | Prime Brook Substation Addition | 3691720.16
Substation Operations | 43267-T835 | 13V Gulch Replace 13V-GT1 & 13V-VR1 | 1011993.16
Transmission Line | 47217-T847 | L6012 17V St. Croix to 43V Cannan | 352174.89
Transmission Line | 46332-T863 | L6539 Replacements | 705259.85
Transmission Line | 46360-T850 | L5545B Reconductor | 808274
Transmission Line | 46582-T842 | L5569 Upgrade | 149514.3
Substation Operations | 48194-T868 | 88S-713 Replacement | 4467074.72
Transmission Line | 47952-T869 | L7001 Replacements (Phase 3 & 4) | 1509306.56
Substation Operations | 48063-T879 | 2016 Capacitor Bank Breaker Repl. | 253153.88
Transmission Line | 48598-T898 | L5530B Replacements and Upgrades | 167327.48
Transmission Line | 48602-T901 | L5047 Replacements and Upgrades | 81451.52
Substation Operations | 48111-T905 | East Switch Upgrades 15S | 290264.84
Transmission Line | 49379-T917 | L6527 Replacements and Upgrades | 84560.4
Transmission Line | 47914-T874 | L6537 Replacements and Upgrades | 1551391.27
Transmission Line | 48595-T896 | L5548 Replacements and Upgrades | 242889.91
Substation Operations | 49878-T937 | 2017 Substation Insulator Replace | 353314.79
Transmission Line | 47954-T963 | L7012 Replacements and Upgrades | 4392085.97
Transmission Line | 47915-T931 | L5053 Replacements and Upgrades | 423948.72
Transmission Line | 49774-T956 | L5527 Replacements and Upgrades | 1784759.13
Transmission Line | 49778-T957 | L5535 Replacements and Upgrades | 2837177.2
Substation Operations | 49833-T936 | 2017 Oil Containment Program | 339359.52
Transmission Line | 51096-T942 | L-5019 Replacements and Upgrades | 159521.62
Substation Operations | 43268 | 9W-B53 Tusket Replace Structure | 14587.88
Transmission Line | 51117-T944 | L5502 Replacements and Upgrades | 49214.45
Substation Operations | 52314 | 1C-GT1/UT1 Replacement | 1678006.2
Transmission Line | 49777 | L7002 Replacements and Upgrades | 1141256.42
Substation Operations | C0001900 | Mount Hope 69-25kV Substation | 2997775.64
Transmission Line | 51112-T951 | L5042 Replacements and Upgrades | 2343.19
Transmission Line | C0014158 | T-L5548 Emergency Repairs | 966751.37
Transmission Line | C0011339 | T-L6549-Replacements and Upgr Ph2 | 3910364.31
Transmission Line | C0011300 | T-L7005 -Replacements and Upgrades | 1571512.32
Transmission Line | C0022202 | 2020 Transmission LiDAR | 93786.16
Substation Operations | C0011039 | 5V-GT1 Generating Transformer | 747421.61
Substation Operations | C0021323 | 50N-Trenton Replace 50N-T13 | 1336009
Transmission Line | C0030263 | L7003 & L7004 - Hwy 104 Twinning | -16.21
Substation Operations | C0022783 | 2020/2021 Gen Power Trans Refurb | 23083.43
Substation Operations | C0021142 | 19W-T51 Transformer Replacement | 1473278.51
Substation Operations | C0021145 | Mobile Substation Low Voltage Cable | 300302.38
Substation Operations | C0031262 | 2021-22 Transmission Switch & Break | 1465591.26
Transmission Line | C0031053 | L5506 Line Replacements and Upgrade | 716595.92
Substation Operations | C0031274 | 2021 Cap Bank Breaker Replacements | 342932.55
Transmission Line | C0044591 | Hwy 103 Exit 12 Public Works Line | 32620.99
Transmission Line | C0045332 | L6020/21 Unplanned Rep & Upg | 832809
Transmission Line | C0031085 | L6516 Line Replacement and Upgrades | 2542897.02
Transmission Line | C0041790 | L8001 Replacements and Upgrades Ph2 | 1169771.83
Substation Operations | C0031051 | Pennsylvania Breaker Replacements | 279044.82
Substation Operations | C0037907 | 5V-501 Switch & Structure Replace | 783031.12
Transmission Line | C0021102 | L5029 Replacements and Upgrades | 275361.57
Transmission Line | C0041805 | L7005 Replacements and Upgrades Ph2 | 2910505.47
Substation Operations | C0041828 | Auto-Regen Breather Retrofit Progra | 102494.24
Transmission Line | C0044172 | L7005 Canso Crossing Vibration Miti | 367176.28
Substation Operations | C0060963 | IR 597 - Mersey Wind Phase 1 | 37385.66
Substation Operations | C0057682 | Spare Transformer Replacement | 41397.4
Substation Operations | C0031048 | 91H-T11 Transformer Replacement | 25330.2
Transmission Line | C0067110 | L5532 Replacements and Upgrades | 330103.17
Substation Operations | C0069534 | IR 669 NU - Higgins Mountain Wind | 5233.88
Substation Operations | C0069394 | 16N-T1 Transformer Replacement | 825.94
Transmission Line | C0061387 | 2024 2025 Wood Pole Retreatment Pro | 252790.73
Substation Operations | C0070367 | IR 618 NU - Goose Harbour Lake Wind | -0.03
| 28181-T521 | RELOCATE L-5501 HIGHLAND SQUARE MAL | 117.62
| 28171-T523 | REPLACE BATTERY 1H-D41 AT WATER STR | 59034.24
| 28168-T526 | REPLACE SWITCHES 90H-602A, 602B & 6 | 46595.48
| 28657-T550 | L8003/L7003/L7004 REPLACEMENTS | 140770.15
| 28486-T553 | ADD MOD'S LAKESIDE SUBSTATION | 181408.69
| 24662-T485 | REPLACE JOSLYN RECLOSERS | 78364.98
| 28170-T524 | REPLACE THREE RADIATORS ON TRANSFOR | 33381.29
| 28473-T547 | 2007 POLE RETREATMENT | 543843.66
| 32402-T589 | L5011 INSTALL 69KV STRUCTURE | 349.59
Trans - Replace / Refurb | 40287-T654 | Substation Recloser Replacement | 4114179.9
| 40727-T660 | L7002 Upgrade | 271226.79
| 40723-T656 | L6536 Upgrade | 191812.66
Trans - Replace / Refurb | 40789-T666 | Upgrade L7005 | 305021.65
Capital Projects Group | 33525-T674 | Canaan Rd 43V to Tremont 51V Line | 7197372.76
Trans - Replace / Refurb | 34622-T670 | Upgrade L-8002 | 2377229.22
Trans - New | 40280-T676 | 2011 Trans Switch & Breaker Upgrade | 3275924.7
Capital Projects Group | 38266-T682 | 2010 Protection Upgrades | 419577.29
Transmission Line | 40322-T678 | Highbury Road Substation | 3066205.32
Capital Projects Group | 40883-T680 | NS-NB Interconnection | 250983.84
Transmission Line | 40307-T673 | L6033 and L6035 Transmission Tower | 837486.95
Trans - New | 40231-T688 | 2011 Protection Upgrades LAK | 1845085.77
Capital Projects Group | 41005-T691 | Parrsboro Tidal Interconnection | 1728098.86
Trans - New | 41552-T705 | 131H Lucasville Transformer Additio | 1848858.71
Trans - Replace / Refurb | 41387-T710 | 2012 Transmission Line Insulator Re | 3623427.83
Transmission Line | 41844-T708 | L8004 & L7005 Reinsulate | 1016937.04
Transmission Line | 42626-T715 | Upgrade L7009 | 585387.34
Substation Operations | 43222-T761 | 2013 Subst. Insulator and Cut-Outs | 235583.46
Substation Operations | 43237-T763 | 2013 Substation Recloser Replace | 1126614.24
Vegetation Management | 43827-T010-840 | Transmission ROW Widening Routine | 11842133.77
Substation Operations | 43488-T775 | 7H Substation Retirement | 73861.56
Substation Operations | 43428-T787 | Remove 6S 4kV Switchgear Breakers | 193091.94
Maritime Link Transmission | 45067-T801 | 67N Onslow 345 KV Node Swap | 2982585.13
Transmission Line | 44987-T820 | L7003 Lidar Upgrades | 10905773.86
Transmission Line | 44984-T821 | 9C Aberdeen Line Tap | 831031.91
Transmission Line | 45053-T818 | 69Kv Structure Replacements West | 225494.35
Transmission Line | 46356-T841 | 2015 Sacrificial Anode Install Prog | 2378745.97
Substation Operations | 46354-T839 | 2015 Reactor Breaker Replacements | 522124.01
Substation Operations | 46586-T857 | 2015 PCB Removal - Substation | 1476013.58
Transmission Line | 43490-T860 | Steel Tower Life Ext - Hali Harbour | 833760.61
Substation Operations | 41438-T866 | 85S Cable Termination Replacement | 427630.1
Transmission Line | 48047-T870 | Trans Inspection Programs | 1401718.25
Transmission Line | 48591-T894 | L5003 Replacements and Upgrades | 103296.81
Substation Operations | 48156-T904 | East Switch Upgrades 58C | 63436.08
Substation Operations | 48151-T903 | 2016 Insulator Replacement Program | 150611.68
Transmission Line | 49375-T914 | L6003 Replacements and Upgrades | 254587.16
Transmission Line | 49792-T934 | 2017 Line Retirement Program | 544381.87
Transmission Line | 49814-T948 | 2017 Steel Tower Life Extension | 1643870.96
Transmission Line | 43200-T930 | 2017 Wood Pole Retreatment | -0.01
Transmission Line | 51118-T953 | L5549 Replacements and Upgrades | 279661.3
Transmission Line | 49948-T960 | 2017/2018 Isolated Structure Replac | 4814888.94
Transmission Line | 51119-T954 | L5550 Replacements and Upgrades | 187358.89
Transmission Line | 51917-T974 | L6515 2017R Replc and Upgrades | 51129.06
Substation Operations | 51742-T966 | 88S-302 Metal Clad Switchgear Repl. | 310725.88
Capital Projects Group - Transmission | 52323 | 2C Port Hastings Uprated to NPCC BP | 3997957.67
Transmission Line | 49783 | L5027A Replacements and Upgrades | 791304.92
Transmission Line | 51402-T969 | 2018/2019 Sacrificial Anode Install | 3073174.01
Substation Operations | 51975 | 5P Mobile Substation Replacement | 2981512.75
Substation Operations | C0009598 | 100C-T61 Transformer Repair | 84789.32
Transmission Line | C0014320 | Nov 28, 2018 L3 Storm -Transmission | 584914.05
Transmission Line | C0011241 | T-L5026 -Replacements and Upgrades | 1379562.67
Transmission Line | C0015480 | Jan 20,2019 L3 Storm-Transmission | 2228.99
Transmission Line | C0011338 | T-L5548- Replacements and Upgrades | 1796576.36
Transmission Line | C0015640 | Jan 24,2019 L3 Storm-Transmission | 32147.64
Transmission Line | C0011242 | T-L5541 -Replacements and Upgrades | 1822760.95
Substation Operations | C0022342 | Sep 2019 Hurricane Dorian - Substai | 71675.37
Substation Operations | C0011851 | T - 2019 Tap Changer Replacement | 446693.28
Substation Operations | C0010956 | 78W-Martins Brook Substation Reloc | 4065937.45
Transmission Line | C0026504 | 2020 Transmission Inspection Progra | 172.19
Transmission Line | C0010955 | 2020/2021 Wood Pole Retreatment | 912015
Substation Operations | C0025383 | 2020 Transformer Refurbishment | 79440.57
Substation Operations | C0030785 | Wreck Cove oil reconditioning | -65148.11
Transmission Line | 52303 | L7019 2020 Replacements & Upgrades | 1383195.98
Transmission Line | C0045072 | Nov 23, 2021 Storm - Transmission | 24350.35
Transmission Line | C0045352 | L7009 Unplanned Repl and Upg | 316248.79
Transmission Line | C0041810 | L5022 Replacements and Upgrades | 1618002.65
Substation Operations | C0031052 | Replenish Spare used at 58C | 1071232.74
Transmission Line | C0046111 | Jan 7, 2022 Storm - Transmission | 185455.16
Transmission Line | C0047035 | Feb 4th, 2022 Storm - Transmission | 568218.58
Large Industrial Reliability | C0044110 | 138kv Line Tap to 92V Substation | 4419262.27
Substation Operations | C0031267 | 2022 Oil Containment Program | 33712.39
Transmission Line | C0041796 | L6020 Replacements and Upgrades Ph2 | 3281196.14
Transmission Line | C0041989 | 2022 2023 Sacrificial Anode Inst Pr | 2773422.66
Vegetation Management | C0041893 | 2022/2023 Trans ROW Widening 69kV | 5186446.8
ECEI | C0044391 | ECEI - Transmission | 11689045.52
Substation Operations | C0031044 | 67N-713 230 kV Breaker Replacem | 622.05
Large Industrial Reliability | C0053316 | Michelin Waterville Dynamic Voltage | 29752743.19
Transmission Line | C0056061 | Dec 24, 2022 Storm - Transmission | 166011.55
Transmission Line | C0056843 | July 22, 2023 Level 3 Storm Transm | 61143.17
Transmission Line | C0041788 | L6516 Replacements and Upgrades Ph2 | 4211236.34
Transmission Line | C0061930 | Sept 16 2023 - Hurricane Lee Transm | 961919.27
Substation Operations | C0064512 | Jan 10, 2024 Level 3 Storm-Substa | 1332.84
Substation Operations | C0063266 | Porter’s Lake Feeder Addition | 302837.29
Substation Operations | C0059483 | Rebuild L5046 Tap | 85588.36
Substation Operations | C0064883 | IR 697 - 105V White Rock BESS TPIF | 5299.53
Transmission Line | C0061547 | L7022 Replacements and Upgrades | 13890.91
Transmission Line | C0041791 | L6551 Replacements and Upgrades | 214865.12

## Sheet3 (hidden)
Cc Cpc | Fp Number | Fp Description | Est Charge Type | Span Estimates 1
Substation Operations | 14973-T018-820 | PRIMARY EQUIPMENT SPARES | 535100 Other Goods and Services | 471.1
Substation Operations | 14841-T016-630 | PROTECTION MODIFICATIONS AND REPLAC | 533450 iExpenses-Tips | 107.33
Substation Operations | 14841-T016-630 | PROTECTION MODIFICATIONS AND REPLAC | 535700 Admin Overheads | 154293.48
Substation Operations | 14841-T016-630 | PROTECTION MODIFICATIONS AND REPLAC | 530050 Regular Labour | 243060.09
Transmission Line | 23118-T011-820 | PROVINCIAL - PLANNED TRANS LINE REP | 530050 Regular Labour | 442104.99
Substation Operations | 23120-T003-820 | PROVINCIAL-TRANS SUBSTATION PRIMARY | 532900 Comp Hardware & Op Software | -10.85
Substation Operations | 23120-T003-820 | PROVINCIAL-TRANS SUBSTATION PRIMARY | 535700 Admin Overheads | 440994.37
Substation Operations | 23120-T003-820 | PROVINCIAL-TRANS SUBSTATION PRIMARY | 534750 Personal Equipment | -6330.69
Substation Operations | C0010956 | 78W-Martins Brook Substation Reloc | 535100 Other Goods and Services | 2
Substation Operations | C0022743 | Retire 9H-Yale Street Substation | 535700 Admin Overheads | 12005.41
Substation Operations | C0031286 | Spare Padmounted Substation | 535705 Contractor Admin Overhead | 1960.91
Substation Operations | C0032382 | Susie Lake Substation Addition | 530050 Regular Labour | 36001
Substation Operations | C0041822 | WRC Spare Cable Repl & Storage Syst | 530050 Regular Labour | 8867.79
Substation Operations | C0041830 | Spare Power Prod Unit Transformer | 535705 Contractor Admin Overhead | 2892.39
Substation Operations | C0041840 | Legacy Oil Containment Refurbish | 530050 Regular Labour | -0.02
Substation Operations | C0043571 | 2022-2023 Transmission Switch & B | 530050 Regular Labour | 39532.34
ECEI | C0044391 | ECEI - Transmission | 532100 Telephones | 17748
ECEI | C0045132 | ECEI - Energy Storage | 532100 Telephones | 28840.05
Substation Operations | C0050834 | Spare EHV Breaker Replacements | 530050 Regular Labour | 12501.2
Substation Operations | C0050842 | 2024 Bulk Oil Breaker Replacement | 535650 Vehicle Allocated Costs | 134114.42
Transmission Line | C0052654 | L5541 Water Crossing Upgrades | 531400 Materials | 420500
Substation Operations | C0053195 | 47C-T1 and T2 PHP Transformer Repl | 530950 Travel Expense | 3069.96
Substation Operations | C0053214 | 76W-T1 Transformer Replacement | 535705 Contractor Admin Overhead | 1164.19
Substation Operations | C0053214 | 76W-T1 Transformer Replacement | 530050 Regular Labour | 33418.54
Large Industrial Reliability | C0053316 | Michelin Waterville Dynamic Voltage | 535700 Admin Overheads | 57192.26
Substation Operations | C0055557 | 76V-T1 Transformer Replacement | 530200 Overtime Labour | 9076
Substation Operations | C0055796 | 2023 EHV Breaker Replacements | 535700 Admin Overheads | 141056.38
Substation Operations | C0057682 | Spare Transformer Replacement | 530050 Regular Labour | 23558.74
Substation Operations | C0057682 | Spare Transformer Replacement | 533400 Meals and Entertainment | 249.99
Substation Operations | C0057882 | 2024 Pennsylvania Breaker Replace | 531400 Materials | 1164360.24
Substation Operations | C0059483 | Rebuild L5046 Tap | 535650 Vehicle Allocated Costs | 26441.64
Corporate Initiatives | C0060866 | Everwind 230kV Transmission Line | 536750 Capital Contributions | -2943040.75
Transmission Line | C0061387 | 2024 2025 Wood Pole Retreatment Pro | 530200 Overtime Labour | 3250
Transmission Line | C0061547 | L7022 Replacements and Upgrades | 535700 Admin Overheads | 53229.02
Transmission Line | C0061550 | L5031 - Hubbards to East Chester | 531550 Contracts | 3518000
Transmission Line | C0061551 | L7009 Replacements and Upgrades Pha | 531400 Materials | 440000
Substation Operations | C0061883 | 129H - Kearney Lake Substation Rebu | 535705 Contractor Admin Overhead | 89490.15
Substation Operations | C0062123 | 143H-Mount Uniacke Substation | 531400 Materials | 1600000
Substation Operations | C0063266 | Porter’s Lake Feeder Addition | 535650 Vehicle Allocated Costs | 0.01
Substation Operations | C0064903 | IR 664 - 99W Bridgewater BESS TPIF | 535700 Admin Overheads | 4866.1
Substation Operations | C0064903 | IR 664 - 99W Bridgewater BESS TPIF | 536750 Capital Contributions | -222151.56
Substation Operations | C0065024 | IR 662 - 132H Spider Lake BESS TPIF | 536750 Capital Contributions | -222151.56
Transmission Line | C0065294 | L5561 Reroute - CBU Expansion | 535650 Vehicle Allocated Costs | 24800.72
AMO - Power Production | C0068452 | AMO Transmission Spares Strategy | 535700 Admin Overheads | 5489.6
AMO - Power Production | C0068452 | AMO Transmission Spares Strategy | 535650 Vehicle Allocated Costs | 4924.92
Substation Operations | C0068961 | 2025 PCB Substation Sampling and Re | 531300 iExpenses-KMs (milage) | 15000
Substation Operations | C0068961 | 2025 PCB Substation Sampling and Re | 535705 Contractor Admin Overhead | 145487.72
Substation Operations | C0068961 | 2025 PCB Substation Sampling and Re | 530200 Overtime Labour | 413000
Transmission Line | C0069227 | L6516 Replacements and Upgrades Ph3 | 535700 Admin Overheads | 72599.61
Transmission Line | C0069227 | L6516 Replacements and Upgrades Ph3 | 531550 Contracts | 1695512.39
Substation Operations | C0069392 | 12V-T1 Transformer Replacement | 530950 Travel Expense | 518.98
Substation Operations | C0069446 | IR 668 - Weavers Mountain Wind | 530200 Overtime Labour | 30792.92
Transmission Line | C0070048 | L5027B Replacements and Upgrades Ph | 530050 Regular Labour | 86129
Transmission Line | C0070048 | L5027B Replacements and Upgrades Ph | 531550 Contracts | 1653094.25
Substation Operations | C0070327 | IR 673 NU - Benjamins Mill Wind | 535700 Admin Overheads | 23125
Substation Operations | C0070328 | IR 673 TPIF - Benjamins Mill Wind | 530950 Travel Expense | 1252.5
Substation Operations | C0070386 | IR 618 TPIF - Goose Harbour Lake Wi | 532500 Consulting | 16364
Substation Operations | C0070909 | 70W-T51 Transformer Replacement | 535700 Admin Overheads | 38937.24
Substation Operations | C0070909 | 70W-T51 Transformer Replacement | 531400 Materials | 2227479
Transmission Line | C0071771 | 2024 Non-NERC Trans LIDAR Surveys | 530050 Regular Labour | 12399.99
Substation Operations | C0071888 | 92H-T61 Transformer Replacement | 533400 Meals and Entertainment | 170.36
Substation Operations | C0072089 | 2P Mobile Transformer Replacement | 535700 Admin Overheads | 25682.19
Substation Operations | C0072308 | Dartmouth Substation Addition | 530950 Travel Expense | 249.99
Substation Operations | 14973-T018-820 | PRIMARY EQUIPMENT SPARES | 535705 Contractor Admin Overhead | 3709.17
Substation Operations | 14841-T016-630 | PROTECTION MODIFICATIONS AND REPLAC | 533400 Meals and Entertainment | 623.96
Transmission Line | 23118-T011-820 | PROVINCIAL - PLANNED TRANS LINE REP | 535705 Contractor Admin Overhead | 443983.4
Substation Operations | 23120-T003-820 | PROVINCIAL-TRANS SUBSTATION PRIMARY | 536100 Rental/Maint of Equipment | 478.17
Substation Operations | 23121-T004-820 | PROVINCIAL- SUBSTATION ADDITIONS & | 533400 Meals and Entertainment | 727.03
Substation Operations | 23121-T004-820 | PROVINCIAL- SUBSTATION ADDITIONS & | 530320 Term Labour-Overtime | 5101.3
Substation Operations | C0011261 | 101W Port Mersey Expansion | 533400 Meals and Entertainment | 194.06
Substation Operations | C0031042 | 5P-MS Rewind | 535100 Other Goods and Services | 1
Substation Operations | C0031046 | 77V New Transformer | 535650 Vehicle Allocated Costs | 11195.64
Transmission Line | C0041791 | L6551 Replacements and Upgrades | 535700 Admin Overheads | 9927.83
Substation Operations | C0041837 | 2022 2023 Substation PCB Equip Remo | 530200 Overtime Labour | 33000
Substation Operations | C0041837 | 2022 2023 Substation PCB Equip Remo | 531800 Freight Postage Delivery | 2100
Substation Operations | C0043571 | 2022-2023 Transmission Switch & B | 531400 Materials | 30000
ECEI | C0044391 | ECEI - Transmission | 532900 Comp Hardware & Op Software | 12800
ECEI | C0044391 | ECEI - Transmission | 534650 Training and Development | 49841
ECEI | C0044391 | ECEI - Transmission | 532700 Fleet Fuel | 30600
ECEI | C0045132 | ECEI - Energy Storage | 532900 Comp Hardware & Op Software | 150000
Transmission Line | C0050835 | 2023/2024 Steel Tower Refurbishment | 530050 Regular Labour | 17501
Substation Operations | C0052994 | WRC 85S-GT1 85S-GT2 Transform Repl | 535705 Contractor Admin Overhead | 43168
Substation Operations | C0052994 | WRC 85S-GT1 85S-GT2 Transform Repl | 530950 Travel Expense | 2533.2
Substation Operations | C0053214 | 76W-T1 Transformer Replacement | 535700 Admin Overheads | 18923.57
Transmission Line | C0053295 | L5004 Kearney Lake Structure Replac | 535700 Admin Overheads | 39792.89
Transmission Line | C0053295 | L5004 Kearney Lake Structure Replac | 535705 Contractor Admin Overhead | 205678.56
Substation Operations | C0055539 | 10H-T1 Transformer Replacement | 532500 Consulting | 50000.06
Substation Operations | C0055539 | 10H-T1 Transformer Replacement | 530950 Travel Expense | 916.63
Substation Operations | C0055557 | 76V-T1 Transformer Replacement | 535650 Vehicle Allocated Costs | 13668.26
Substation Operations | C0056240 | 2024-2025 Transmission Switch & Bre | 530050 Regular Labour | 90715.73
Substation Operations | C0057682 | Spare Transformer Replacement | 535650 Vehicle Allocated Costs | 11752.94
AMO - Customer Operations | C0060003 | AMO 85S Thermal Camera Upgrade | 530050 Regular Labour | 35000
AMO - Customer Operations | C0060003 | AMO 85S Thermal Camera Upgrade | 605050 AFUDC Interest | 3602.89
Corporate Initiatives | C0060866 | Everwind 230kV Transmission Line | 532500 Consulting | 50000
Transmission Line | C0061545 | L6006 Replacements and Upgrades | 535650 Vehicle Allocated Costs | 14268.46
Transmission Line | C0061546 | L6514 Replacements and Upgrades | 531400 Materials | 145608.76
Transmission Line | C0061552 | L6043 Replacements and Upgrades | 530050 Regular Labour | 52784.58
Transmission Line | C0061552 | L6043 Replacements and Upgrades | 531400 Materials | 353037.1
Transmission Line | C0061552 | L6043 Replacements and Upgrades | 535705 Contractor Admin Overhead | 131161.53
Transmission Line | C0061743 | L6038 Realignment | 605050 AFUDC Interest | 706.72
Substation Operations | C0062123 | 143H-Mount Uniacke Substation | 533400 Meals and Entertainment | 572.72
Substation Operations | C0062123 | 143H-Mount Uniacke Substation | 531550 Contracts | 4340000
Substation Operations | C0062123 | 143H-Mount Uniacke Substation | 530200 Overtime Labour | 5515.33
Substation Operations | C0063266 | Porter’s Lake Feeder Addition | 535700 Admin Overheads | 0.01
Substation Operations | C0064903 | IR 664 - 99W Bridgewater BESS TPIF | 530050 Regular Labour | 8421.07
Substation Operations | C0064903 | IR 664 - 99W Bridgewater BESS TPIF | 533400 Meals and Entertainment | 210.48
AMO - Power Production | C0068452 | AMO Transmission Spares Strategy | 605050 AFUDC Interest | 560.35
Substation Operations | C0068961 | 2025 PCB Substation Sampling and Re | 535700 Admin Overheads | 572772.04
Transmission Line | C0069232 | L6021 Replacements and Upgrades Ph1 | 530200 Overtime Labour | 16000
Substation Operations | C0069234 | L5532 Reliability Improvements Phas | 535700 Admin Overheads | 65119.9
Transmission Line | C0069238 | 2025/2026 Steel Tower Refurbishment | 530050 Regular Labour | 32510.1
Substation Operations | C0069394 | 16N-T1 Transformer Replacement | 533400 Meals and Entertainment | 209.31
Transmission Line | C0070048 | L5027B Replacements and Upgrades Ph | 535100 Other Goods and Services | 330000
Substation Operations | C0070367 | IR 618 NU - Goose Harbour Lake Wind | 530050 Regular Labour | 166273.36
Substation Operations | C0070386 | IR 618 TPIF - Goose Harbour Lake Wi | 535705 Contractor Admin Overhead | 29363.97
Substation Operations | C0071889 | 77V-T1 Transformer Replacement | 531400 Materials | 2671776
Substation Operations | C0072089 | 2P Mobile Transformer Replacement | 530050 Regular Labour | 44444.45
Transmission Line | C0072115 | L5511 Replacements and Upgrades | 531400 Materials | 10000.01
Transmission Line | C0072115 | L5511 Replacements and Upgrades | 535705 Contractor Admin Overhead | 11569.6
Substation Operations | C0072308 | Dartmouth Substation Addition | 605050 AFUDC Interest | 216820.25
Transmission Line | C0073388 | L8002 Replacements and Upgrades U&U | 531550 Contracts | 120000
Substation Operations | C0073975 | IR 671 NU - Bear Lake Wind | 533410 Overtime Meals | 6250
Substation Operations | C0073975 | IR 671 NU - Bear Lake Wind | 533400 Meals and Entertainment | 19000
Substation Operations | 14973-T018-820 | PRIMARY EQUIPMENT SPARES | 535650 Vehicle Allocated Costs | 1919.14
Substation Operations | 14841-T016-630 | PROTECTION MODIFICATIONS AND REPLAC | 531400 Materials | 170729.56
Substation Operations | 14841-T016-630 | PROTECTION MODIFICATIONS AND REPLAC | 530300 Term Labour | 12631.32
Transmission Line | 23115-T001-820 | PROVINCIAL TRANSMISSION LINE REPLAC | 530320 Term Labour-Overtime | 9631.4
Transmission Line | 23118-T011-820 | PROVINCIAL - PLANNED TRANS LINE REP | 535100 Other Goods and Services | 1740
Substation Operations | 23120-T003-820 | PROVINCIAL-TRANS SUBSTATION PRIMARY | 530050 Regular Labour | 538586.89
Substation Operations | 23120-T003-820 | PROVINCIAL-TRANS SUBSTATION PRIMARY | 531550 Contracts | 621646.75
Substation Operations | 23120-T003-820 | PROVINCIAL-TRANS SUBSTATION PRIMARY | 455300 Other Income-Salvage | 2623.09
Substation Operations | 23121-T004-820 | PROVINCIAL- SUBSTATION ADDITIONS & | 531500 Materials-Corp Promo Items | 9358.27
Substation Operations | 23121-T004-820 | PROVINCIAL- SUBSTATION ADDITIONS & | 531300 iExpenses-KMs (milage) | 134.94
Capital Projects Group - Transmission | 51098-T952 | L-6014 Shannon Park Trans Towers | 531550 Contracts | 8856954.17
Capital Projects Group - Transmission | 51098-T952 | L-6014 Shannon Park Trans Towers | 535705 Contractor Admin Overhead | 1280892.78
Substation Operations | C0022743 | Retire 9H-Yale Street Substation | 531550 Contracts | 108860
Transmission Line | C0023802 | L6515 Replacements and Upgrades | 531550 Contracts | 135000
Transmission Line | C0031122 | L6539-2021 Replacements and Upgrade | 531400 Materials | 175000
AMO - Customer Operations | C0031268 | AMO Critical Equipment Online Mon. | 531400 Materials | 4000
AMO - Customer Operations | C0031268 | AMO Critical Equipment Online Mon. | 531550 Contracts | 7000
Transmission Line | C0033644 | 2021-2022 Steel Tower Life Extensio | 530050 Regular Labour | 1
Transmission Line | C0041804 | 2022 Line Retirement Program | 535700 Admin Overheads | 7941.43
Transmission Line | C0041807 | L5534 Replacements and Upgrades | 535700 Admin Overheads | 7135.43
Substation Operations | C0041822 | WRC Spare Cable Repl & Storage Syst | 530950 Travel Expense | 681.99
Substation Operations | C0041830 | Spare Power Prod Unit Transformer | 531400 Materials | 1200000
Substation Operations | C0041830 | Spare Power Prod Unit Transformer | 530200 Overtime Labour | 5000.01
Substation Operations | C0041830 | Spare Power Prod Unit Transformer | 605050 AFUDC Interest | 43560.69
Substation Operations | C0041837 | 2022 2023 Substation PCB Equip Remo | 530320 Term Labour-Overtime | 750
Substation Operations | C0041837 | 2022 2023 Substation PCB Equip Remo | 535705 Contractor Admin Overhead | 8677.2
ECEI | C0044391 | ECEI - Transmission | 530900 Office Supplies | 7824
ECEI | C0045132 | ECEI - Energy Storage | 530300 Term Labour | 188976
Substation Operations | C0050834 | Spare EHV Breaker Replacements | 605050 AFUDC Interest | 4308.82
Substation Operations | C0050842 | 2024 Bulk Oil Breaker Replacement | 530050 Regular Labour | 268831.24
Substation Operations | C0050852 | 10V-T1 Transformer Replacement | 532500 Consulting | 20257.13
Substation Operations | C0053234 | 96H-T1 Transformer Replacement | 605050 AFUDC Interest | 80834.19
Transmission Line | C0053295 | L5004 Kearney Lake Structure Replac | 530050 Regular Labour | 70273.12
Large Industrial Reliability | C0053316 | Michelin Waterville Dynamic Voltage | 530200 Overtime Labour | 12000
Substation Operations | C0061023 | 2024 EHV Breaker Replacements | 535650 Vehicle Allocated Costs | 116713.8
Substation Operations | C0061046 | 2024 Merlin Gerin Breaker Replaceme | 535705 Contractor Admin Overhead | 5098.59
Transmission Line | C0061403 | 2024 2025 Sacrificial Anode Install | 533400 Meals and Entertainment | 600
Transmission Line | C0061403 | 2024 2025 Sacrificial Anode Install | 535650 Vehicle Allocated Costs | 5363.46
Transmission Line | C0061544 | L6536 Replacements and Upgrades | 535650 Vehicle Allocated Costs | 23946.74
Transmission Line | C0061551 | L7009 Replacements and Upgrades Pha | 535100 Other Goods and Services | 150000
Transmission Line | C0061551 | L7009 Replacements and Upgrades Pha | 535650 Vehicle Allocated Costs | 59610.49
Substation Operations | C0061883 | 129H - Kearney Lake Substation Rebu | 531400 Materials | 186674.01
Substation Operations | C0064883 | IR 697 - 105V White Rock BESS TPIF | 535700 Admin Overheads | 6667.51
Substation Operations | C0064883 | IR 697 - 105V White Rock BESS TPIF | 530950 Travel Expense | 576.94
Substation Operations | C0065024 | IR 662 - 132H Spider Lake BESS TPIF | 533400 Meals and Entertainment | 210.48
Substation Operations | C0065024 | IR 662 - 132H Spider Lake BESS TPIF | 535650 Vehicle Allocated Costs | 4365.54
Transmission Line | C0065294 | L5561 Reroute - CBU Expansion | 535700 Admin Overheads | 27644.26
Transmission Line | C0065294 | L5561 Reroute - CBU Expansion | 536750 Capital Contributions | -134780.96
Transmission Line | C0067110 | L5532 Replacements and Upgrades | 535700 Admin Overheads | 0.57
Transmission Line | C0067111 | L5023 Rebuild | 535650 Vehicle Allocated Costs | 2744.34
AMO - Power Production | C0068467 | AMO Transmission Risk Profiling | 535700 Admin Overheads | 6645.29
Substation Operations | C0068868 | Fall River Substation Addition | 533400 Meals and Entertainment | 500
Transmission Line | C0069231 | L8002 Replacements and Upgrades Ph1 | 530050 Regular Labour | 98770.38
Transmission Line | C0069231 | L8002 Replacements and Upgrades Ph1 | 531400 Materials | 596247.38
Transmission Line | C0069231 | L8002 Replacements and Upgrades Ph1 | 531550 Contracts | 1650430.03
Transmission Line | C0069231 | L8002 Replacements and Upgrades Ph1 | 535700 Admin Overheads | 55929.75
Transmission Line | C0069232 | L6021 Replacements and Upgrades Ph1 | 535100 Other Goods and Services | 370559.08
Substation Operations | C0069234 | L5532 Reliability Improvements Phas | 535650 Vehicle Allocated Costs | 57371.2
Transmission Line | C0069238 | 2025/2026 Steel Tower Refurbishment | 535650 Vehicle Allocated Costs | 16218.52
Substation Operations | C0069392 | 12V-T1 Transformer Replacement | 605050 AFUDC Interest | 50482.37
Substation Operations | C0069394 | 16N-T1 Transformer Replacement | 530950 Travel Expense | 502.64
Substation Operations | C0069534 | IR 669 NU - Higgins Mountain Wind | 535100 Other Goods and Services | 275326.43
Substation Operations | C0069535 | IR 669 TPIF - Higgins Mountain Wind | 530050 Regular Labour | 89975.36
Substation Operations | C0069535 | IR 669 TPIF - Higgins Mountain Wind | 535650 Vehicle Allocated Costs | 47000.69
Transmission Line | C0072115 | L5511 Replacements and Upgrades | 535700 Admin Overheads | 849.96
Substation Operations | C0072308 | Dartmouth Substation Addition | 535650 Vehicle Allocated Costs | 15165.47
Substation Operations | C0072308 | Dartmouth Substation Addition | 531400 Materials | 3226661
ECEI | C0072808 | Synchronous Condensers | 531510 Materials-Ash Disposal | 67031940.16
Substation Operations | C0073308 | IR 677 TPIF - Wedgeport Wind | 533400 Meals and Entertainment | 478.26
Substation Operations | C0073309 | IR 677 NU - Wedgeport Wind | 536750 Capital Contributions | -22302749.02
Substation Operations | C0073309 | IR 677 NU - Wedgeport Wind | 532500 Consulting | 288000
Transmission Line | C0073388 | L8002 Replacements and Upgrades U&U | 530050 Regular Labour | 4000.99
Substation Operations | C0073975 | IR 671 NU - Bear Lake Wind | 536750 Capital Contributions | -5066105.58
Substation Operations | 14973-T018-820 | PRIMARY EQUIPMENT SPARES | 535700 Admin Overheads | 2139.16
Substation Operations | 14841-T016-630 | PROTECTION MODIFICATIONS AND REPLAC | 533410 Overtime Meals | 699.3
Transmission Line | 23115-T001-820 | PROVINCIAL TRANSMISSION LINE REPLAC | 455300 Other Income-Salvage | -10002.61
Transmission Line | 23115-T001-820 | PROVINCIAL TRANSMISSION LINE REPLAC | 530900 Office Supplies | 101.49
Transmission Line | 23118-T011-820 | PROVINCIAL - PLANNED TRANS LINE REP | 531400 Materials | 1402554
Substation Operations | 23120-T003-820 | PROVINCIAL-TRANS SUBSTATION PRIMARY | 530200 Overtime Labour | 300789.48
Substation Operations | 23121-T004-820 | PROVINCIAL- SUBSTATION ADDITIONS & | 530300 Term Labour | 4807.58
Substation Operations | 23121-T004-820 | PROVINCIAL- SUBSTATION ADDITIONS & | 531400 Materials | 192453.59
Substation Operations | 23121-T004-820 | PROVINCIAL- SUBSTATION ADDITIONS & | 532500 Consulting | 815.92
Substation Operations | C0011261 | 101W Port Mersey Expansion | 531550 Contracts | 370
Substation Operations | C0011358 | New Bridgewater Substation | 605050 AFUDC Interest | 901.89
Substation Operations | C0021140 | 98N-Stellarton Substation | 531550 Contracts | 3417000
Substation Operations | C0031048 | 91H-T11 Transformer Replacement | 535100 Other Goods and Services | 1059799.2
Substation Operations | C0041830 | Spare Power Prod Unit Transformer | 530950 Travel Expense | 1000.01
Substation Operations | C0041837 | 2022 2023 Substation PCB Equip Remo | 535650 Vehicle Allocated Costs | 50636.83
Substation Operations | C0041837 | 2022 2023 Substation PCB Equip Remo | 531200 iExpenses-Accommodations | 700
Substation Operations | C0041840 | Legacy Oil Containment Refurbish | 531400 Materials | 0.03
ECEI | C0044391 | ECEI - Transmission | 531400 Materials | 1614148
ECEI | C0044391 | ECEI - Transmission | 533100 External Legal and Audit | 3457176
ECEI | C0045132 | ECEI - Energy Storage | 530050 Regular Labour | 5061092.03
ECEI | C0045132 | ECEI - Energy Storage | 536750 Capital Contributions | -73397270
ECEI | C0045132 | ECEI - Energy Storage | 531350 iExpenses-Airfare | 239000
ECEI | C0045132 | ECEI - Energy Storage | 536450 First Nation Commitments | 337128
Substation Operations | C0050852 | 10V-T1 Transformer Replacement | 535700 Admin Overheads | 63850.98
Transmission Line | C0052299 | 2023 2024 Steel Tower Life Extensio | 535700 Admin Overheads | 14440.2
Transmission Line | C0052299 | 2023 2024 Steel Tower Life Extensio | 530200 Overtime Labour | 19000
Substation Operations | C0052994 | WRC 85S-GT1 85S-GT2 Transform Repl | 535650 Vehicle Allocated Costs | 65247.74
Transmission Line | C0053295 | L5004 Kearney Lake Structure Replac | 535650 Vehicle Allocated Costs | 35057.81
Large Industrial Reliability | C0053316 | Michelin Waterville Dynamic Voltage | 535705 Contractor Admin Overhead | 108453.22
Substation Operations | C0055557 | 76V-T1 Transformer Replacement | 533400 Meals and Entertainment | 1507.92
Substation Operations | C0055557 | 76V-T1 Transformer Replacement | 535700 Admin Overheads | 15514.41
Substation Operations | C0055796 | 2023 EHV Breaker Replacements | 531400 Materials | 1958868.75
Substation Operations | C0056240 | 2024-2025 Transmission Switch & Bre | 530950 Travel Expense | 414
Substation Operations | C0059483 | Rebuild L5046 Tap | 605050 AFUDC Interest | 1874.78
AMO - Customer Operations | C0060003 | AMO 85S Thermal Camera Upgrade | 535705 Contractor Admin Overhead | 2290.8
AMO - Customer Operations | C0060003 | AMO 85S Thermal Camera Upgrade | 535650 Vehicle Allocated Costs | 18144.36
Corporate Initiatives | C0060866 | Everwind 230kV Transmission Line | 531400 Materials | 1500000
Transmission Line | C0061543 | L5048 Replacements and Upgrades | 531550 Contracts | -0.16
Transmission Line | C0061544 | L6536 Replacements and Upgrades | 530050 Regular Labour | 48001
Transmission Line | C0061547 | L7022 Replacements and Upgrades | 530200 Overtime Labour | 16000
Transmission Line | C0061550 | L5031 - Hubbards to East Chester | 535705 Contractor Admin Overhead | 508773.16
Transmission Line | C0061552 | L6043 Replacements and Upgrades | 535650 Vehicle Allocated Costs | 26333.17
Transmission Line | C0061743 | L6038 Realignment | 535650 Vehicle Allocated Costs | 14593.52
Substation Operations | C0061883 | 129H - Kearney Lake Substation Rebu | 530050 Regular Labour | 65799.04
Substation Operations | C0062123 | 143H-Mount Uniacke Substation | 605050 AFUDC Interest | 697882.64
Substation Operations | C0068868 | Fall River Substation Addition | 535700 Admin Overheads | 11892.03
Substation Operations | C0068961 | 2025 PCB Substation Sampling and Re | 532500 Consulting | 98674.24
Transmission Line | C0069238 | 2025/2026 Steel Tower Refurbishment | 531400 Materials | 403700
Substation Operations | C0069392 | 12V-T1 Transformer Replacement | 535650 Vehicle Allocated Costs | 25776.57
Substation Operations | C0069534 | IR 669 NU - Higgins Mountain Wind | 530050 Regular Labour | 175160.62
Substation Operations | C0070086 | 10H-T2 Transformer Replacement | 532500 Consulting | 50000.06
Substation Operations | C0070327 | IR 673 NU - Benjamins Mill Wind | 530050 Regular Labour | 38730
Substation Operations | C0070328 | IR 673 TPIF - Benjamins Mill Wind | 535705 Contractor Admin Overhead | 34209.3
Substation Operations | C0070367 | IR 618 NU - Goose Harbour Lake Wind | 536750 Capital Contributions | -1861477.36
Substation Operations | C0070386 | IR 618 TPIF - Goose Harbour Lake Wi | 535650 Vehicle Allocated Costs | 74832.5
Substation Operations | C0070451 | 2026 Switch and Breaker Replacement | 530050 Regular Labour | 78454.28
Substation Operations | C0070586 | 22N-603 and 604 Switch Repl L6536 | 531550 Contracts | 57710.98
Substation Operations | C0070586 | 22N-603 and 604 Switch Repl L6536 | 535950 Royalty, Easement, Appraisal | 2705.21
Substation Operations | C0070909 | 70W-T51 Transformer Replacement | 530950 Travel Expense | 410.7
Substation Operations | C0071888 | 92H-T61 Transformer Replacement | 530950 Travel Expense | 425.92
Substation Operations | C0072308 | Dartmouth Substation Addition | 533400 Meals and Entertainment | 500
Substation Operations | C0073308 | IR 677 TPIF - Wedgeport Wind | 531400 Materials | 231478.26
Substation Operations | C0073309 | IR 677 NU - Wedgeport Wind | 535700 Admin Overheads | 450622.21
Substation Operations | C0073975 | IR 671 NU - Bear Lake Wind | 530950 Travel Expense | 18550
Substation Operations | C0073975 | IR 671 NU - Bear Lake Wind | 535100 Other Goods and Services | 385106.7
Substation Operations | 14973-T018-820 | PRIMARY EQUIPMENT SPARES | 531400 Materials | 169483.14
Substation Operations | 14841-T016-630 | PROTECTION MODIFICATIONS AND REPLAC | 530950 Travel Expense | 611.1
Transmission Line | 23115-T001-820 | PROVINCIAL TRANSMISSION LINE REPLAC | 532500 Consulting | 2254.06
Substation Operations | 23121-T004-820 | PROVINCIAL- SUBSTATION ADDITIONS & | 531550 Contracts | 253849.07
Substation Operations | 23121-T004-820 | PROVINCIAL- SUBSTATION ADDITIONS & | 533450 iExpenses-Tips | 92.17
Capital Projects Group - Transmission | 51098-T952 | L-6014 Shannon Park Trans Towers | 532500 Consulting | 918529.02
Substation Operations | C0011358 | New Bridgewater Substation | 530050 Regular Labour | 24001
Substation Operations | C0022247 | 1N-Onslow 138 kV Add Second 42 MVA | 535650 Vehicle Allocated Costs | 18916.33
Transmission Line | C0031122 | L6539-2021 Replacements and Upgrade | 531550 Contracts | 630000
Transmission Line | C0041791 | L6551 Replacements and Upgrades | 530050 Regular Labour | 17532.35
Transmission Line | C0041807 | L5534 Replacements and Upgrades | 535650 Vehicle Allocated Costs | 6286.39
Substation Operations | C0041830 | Spare Power Prod Unit Transformer | 533400 Meals and Entertainment | 249.92
Substation Operations | C0041840 | Legacy Oil Containment Refurbish | 535700 Admin Overheads | -0.02
Substation Operations | C0043571 | 2022-2023 Transmission Switch & B | 531550 Contracts | 7500
ECEI | C0044391 | ECEI - Transmission | 535950 Royalty, Easement, Appraisal | 3175000
ECEI | C0044391 | ECEI - Transmission | 536750 Capital Contributions | -28271107
ECEI | C0044391 | ECEI - Transmission | 534750 Personal Equipment | 12654
ECEI | C0045132 | ECEI - Energy Storage | 531550 Contracts | 36834513.33
ECEI | C0045132 | ECEI - Energy Storage | 532850 Application Software | 2340720.16
ECEI | C0045132 | ECEI - Energy Storage | 533100 External Legal and Audit | 129507
Transmission Line | C0050835 | 2023/2024 Steel Tower Refurbishment | 531400 Materials | 75000
Transmission Line | C0050835 | 2023/2024 Steel Tower Refurbishment | 530200 Overtime Labour | 3500
Substation Operations | C0050852 | 10V-T1 Transformer Replacement | 605050 AFUDC Interest | 38466.87
Transmission Line | C0052654 | L5541 Water Crossing Upgrades | 531550 Contracts | 466000
Substation Operations | C0052994 | WRC 85S-GT1 85S-GT2 Transform Repl | 530050 Regular Labour | 125861.2
Substation Operations | C0052994 | WRC 85S-GT1 85S-GT2 Transform Repl | 531400 Materials | 2915533.3
Substation Operations | C0053195 | 47C-T1 and T2 PHP Transformer Repl | 531400 Materials | 2409312.6
Substation Operations | C0055539 | 10H-T1 Transformer Replacement | 535650 Vehicle Allocated Costs | 52483.56
Substation Operations | C0055796 | 2023 EHV Breaker Replacements | 535705 Contractor Admin Overhead | 115945.41
Substation Operations | C0061023 | 2024 EHV Breaker Replacements | 530050 Regular Labour | 225138.04
Transmission Line | C0061387 | 2024 2025 Wood Pole Retreatment Pro | 533400 Meals and Entertainment | 1372
Transmission Line | C0061403 | 2024 2025 Sacrificial Anode Install | 530050 Regular Labour | 10501
Transmission Line | C0061545 | L6006 Replacements and Upgrades | 531550 Contracts | 1252258.88
Transmission Line | C0061546 | L6514 Replacements and Upgrades | 535700 Admin Overheads | 18733.12
Transmission Line | C0061546 | L6514 Replacements and Upgrades | 535705 Contractor Admin Overhead | 70874.48
Transmission Line | C0061743 | L6038 Realignment | 530200 Overtime Labour | 9500.33
Substation Operations | C0065024 | IR 662 - 132H Spider Lake BESS TPIF | 605050 AFUDC Interest | 12471.78
AMO - Power Production | C0068452 | AMO Transmission Spares Strategy | 530050 Regular Labour | 9500
AMO - Power Production | C0068467 | AMO Transmission Risk Profiling | 535650 Vehicle Allocated Costs | 5961.73
Substation Operations | C0068961 | 2025 PCB Substation Sampling and Re | 531200 iExpenses-Accommodations | 3000
Substation Operations | C0068961 | 2025 PCB Substation Sampling and Re | 533400 Meals and Entertainment | 3000
Substation Operations | C0068969 | 2026 Pennsylvania Breaker Replaceme | 531400 Materials | 419301.53
Transmission Line | C0069232 | L6021 Replacements and Upgrades Ph1 | 535950 Royalty, Easement, Appraisal | 15000
Transmission Line | C0069232 | L6021 Replacements and Upgrades Ph1 | 535700 Admin Overheads | 71985.76
Substation Operations | C0069234 | L5532 Reliability Improvements Phas | 530050 Regular Labour | 115000
Substation Operations | C0069234 | L5532 Reliability Improvements Phas | 605050 AFUDC Interest | 13209.38
Substation Operations | C0069394 | 16N-T1 Transformer Replacement | 531400 Materials | 1848033
Substation Operations | C0069446 | IR 668 - Weavers Mountain Wind | 530950 Travel Expense | 30171.12
Substation Operations | C0069446 | IR 668 - Weavers Mountain Wind | 535650 Vehicle Allocated Costs | 326445.65
Substation Operations | C0069535 | IR 669 TPIF - Higgins Mountain Wind | 535705 Contractor Admin Overhead | 14253.83
Substation Operations | C0070367 | IR 618 NU - Goose Harbour Lake Wind | 531550 Contracts | 658636.36
Substation Operations | C0070451 | 2026 Switch and Breaker Replacement | 531400 Materials | 1000492.04
Substation Operations | C0070451 | 2026 Switch and Breaker Replacement | 535700 Admin Overheads | 44425.51
Substation Operations | C0070909 | 70W-T51 Transformer Replacement | 533400 Meals and Entertainment | 164.3
Substation Operations | C0072308 | Dartmouth Substation Addition | 530050 Regular Labour | 30399
ECEI | C0072808 | Synchronous Condensers | 531550 Contracts | 113321580.81
ECEI | C0072808 | Synchronous Condensers | 532500 Consulting | 1001150
Substation Operations | C0073309 | IR 677 NU - Wedgeport Wind | 530950 Travel Expense | 45042
Substation Operations | C0073975 | IR 671 NU - Bear Lake Wind | 531550 Contracts | 1987360
Transmission Line | 23115-T001-820 | PROVINCIAL TRANSMISSION LINE REPLAC | 535100 Other Goods and Services | 303.47
Transmission Line | 23115-T001-820 | PROVINCIAL TRANSMISSION LINE REPLAC | 531400 Materials | 290000
Transmission Line | 23118-T011-820 | PROVINCIAL - PLANNED TRANS LINE REP | 532500 Consulting | 45936
Substation Operations | 23120-T003-820 | PROVINCIAL-TRANS SUBSTATION PRIMARY | 532100 Telephones | 48.76
Vegetation Management | 43827-T010-840 | Transmission ROW Widening Routine | 535650 Vehicle Allocated Costs | 20953.46
Vegetation Management | 43827-T010-840 | Transmission ROW Widening Routine | 535705 Contractor Admin Overhead | 357847.69
Substation Operations | C0011261 | 101W Port Mersey Expansion | 531300 iExpenses-KMs (milage) | 126.17
Substation Operations | C0011261 | 101W Port Mersey Expansion | 530300 Term Labour | 349.13
Substation Operations | C0011358 | New Bridgewater Substation | 531400 Materials | 1624000
Substation Operations | C0011358 | New Bridgewater Substation | 530950 Travel Expense | 300
Substation Operations | C0022247 | 1N-Onslow 138 kV Add Second 42 MVA | 531550 Contracts | 350000.01
AMO - Customer Operations | C0031268 | AMO Critical Equipment Online Mon. | 535700 Admin Overheads | 4530.08
Substation Operations | C0032382 | Susie Lake Substation Addition | 531400 Materials | 1660000
Transmission Line | C0041791 | L6551 Replacements and Upgrades | 535705 Contractor Admin Overhead | 144981.58
Transmission Line | C0041804 | 2022 Line Retirement Program | 535650 Vehicle Allocated Costs | 6996.48
Substation Operations | C0041822 | WRC Spare Cable Repl & Storage Syst | 535705 Contractor Admin Overhead | 295.87
Substation Operations | C0041830 | Spare Power Prod Unit Transformer | 535650 Vehicle Allocated Costs | 15632.09
Substation Operations | C0041837 | 2022 2023 Substation PCB Equip Remo | 531300 iExpenses-KMs (milage) | 3500
Substation Operations | C0043571 | 2022-2023 Transmission Switch & B | 535700 Admin Overheads | 22843.77
ECEI | C0044391 | ECEI - Transmission | 530950 Travel Expense | 430244
ECEI | C0045132 | ECEI - Energy Storage | 531800 Freight Postage Delivery | 14640316
ECEI | C0045132 | ECEI - Energy Storage | 533400 Meals and Entertainment | 14420.07
Transmission Line | C0050835 | 2023/2024 Steel Tower Refurbishment | 535650 Vehicle Allocated Costs | 9603.94
Transmission Line | C0052299 | 2023 2024 Steel Tower Life Extensio | 530950 Travel Expense | 500
Transmission Line | C0052299 | 2023 2024 Steel Tower Life Extensio | 535650 Vehicle Allocated Costs | 12721.93
Substation Operations | C0052994 | WRC 85S-GT1 85S-GT2 Transform Repl | 531550 Contracts | 282661.1
Substation Operations | C0053195 | 47C-T1 and T2 PHP Transformer Repl | 531550 Contracts | 401662.6
Substation Operations | C0053214 | 76W-T1 Transformer Replacement | 532500 Consulting | 119999.99
Substation Operations | C0053234 | 96H-T1 Transformer Replacement | 531400 Materials | 1641354.32
Large Industrial Reliability | C0053316 | Michelin Waterville Dynamic Voltage | 605050 AFUDC Interest | 339290.65
Substation Operations | C0055539 | 10H-T1 Transformer Replacement | 530050 Regular Labour | 101077.68
Substation Operations | C0056240 | 2024-2025 Transmission Switch & Bre | 535700 Admin Overheads | 51368.73
Substation Operations | C0057682 | Spare Transformer Replacement | 530950 Travel Expense | 999.99
Substation Operations | C0057882 | 2024 Pennsylvania Breaker Replace | 535100 Other Goods and Services | 148896.9
AMO - Customer Operations | C0060003 | AMO 85S Thermal Camera Upgrade | 535700 Admin Overheads | 20224.76
Substation Operations | C0061023 | 2024 EHV Breaker Replacements | 531550 Contracts | 772560
Substation Operations | C0061023 | 2024 EHV Breaker Replacements | 535100 Other Goods and Services | 290346
Substation Operations | C0061046 | 2024 Merlin Gerin Breaker Replaceme | 535700 Admin Overheads | 16568.11
Substation Operations | C0061046 | 2024 Merlin Gerin Breaker Replaceme | 531550 Contracts | 33385.26
Transmission Line | C0061387 | 2024 2025 Wood Pole Retreatment Pro | 535650 Vehicle Allocated Costs | 12035.98
Transmission Line | C0061552 | L6043 Replacements and Upgrades | 531550 Contracts | 906939.17
Substation Operations | C0061883 | 129H - Kearney Lake Substation Rebu | 531550 Contracts | 618795.28
Substation Operations | C0064883 | IR 697 - 105V White Rock BESS TPIF | 536750 Capital Contributions | -319739.67
Substation Operations | C0064883 | IR 697 - 105V White Rock BESS TPIF | 531400 Materials | 216858.47
Transmission Line | C0067111 | L5023 Rebuild | 535705 Contractor Admin Overhead | 17354.4
Substation Operations | C0068868 | Fall River Substation Addition | 605050 AFUDC Interest | 327607.22
Substation Operations | C0068969 | 2026 Pennsylvania Breaker Replaceme | 533400 Meals and Entertainment | 500.04
Transmission Line | C0069227 | L6516 Replacements and Upgrades Ph3 | 535705 Contractor Admin Overhead | 245205.07
Transmission Line | C0069232 | L6021 Replacements and Upgrades Ph1 | 530050 Regular Labour | 119124.8
Substation Operations | C0069446 | IR 668 - Weavers Mountain Wind | 530050 Regular Labour | 614309.02
Substation Operations | C0069446 | IR 668 - Weavers Mountain Wind | 531400 Materials | 3376685.74
Substation Operations | C0069534 | IR 669 NU - Higgins Mountain Wind | 532500 Consulting | 13333.34
Substation Operations | C0069535 | IR 669 TPIF - Higgins Mountain Wind | 535700 Admin Overheads | 52389.54
Substation Operations | C0069535 | IR 669 TPIF - Higgins Mountain Wind | 536750 Capital Contributions | -588234.5
Substation Operations | C0070327 | IR 673 NU - Benjamins Mill Wind | 532500 Consulting | 3375
Substation Operations | C0070327 | IR 673 NU - Benjamins Mill Wind | 536750 Capital Contributions | -140648.85
Substation Operations | C0070367 | IR 618 NU - Goose Harbour Lake Wind | 530200 Overtime Labour | 14345.16
Substation Operations | C0070586 | 22N-603 and 604 Switch Repl L6536 | 535700 Admin Overheads | 23522.65
Substation Operations | C0071888 | 92H-T61 Transformer Replacement | 531400 Materials | 2978695
Substation Operations | C0071889 | 77V-T1 Transformer Replacement | 535650 Vehicle Allocated Costs | 34700.03
Substation Operations | C0071889 | 77V-T1 Transformer Replacement | 535700 Admin Overheads | 39386.73
Transmission Line | C0072115 | L5511 Replacements and Upgrades | 530050 Regular Labour | 1501.01
Transmission Line | C0072115 | L5511 Replacements and Upgrades | 535100 Other Goods and Services | 50000
ECEI | C0072808 | Synchronous Condensers | 605050 AFUDC Interest | 16135829.21
Substation Operations | C0073308 | IR 677 TPIF - Wedgeport Wind | 530200 Overtime Labour | 5918.96
Substation Operations | C0073308 | IR 677 TPIF - Wedgeport Wind | 530950 Travel Expense | 2396.08
Substation Operations | 14973-T018-820 | PRIMARY EQUIPMENT SPARES | 533410 Overtime Meals | 34.28
Substation Operations | 14841-T016-630 | PROTECTION MODIFICATIONS AND REPLAC | 535650 Vehicle Allocated Costs | 131622.24
Transmission Line | 23118-T011-820 | PROVINCIAL - PLANNED TRANS LINE REP | 533400 Meals and Entertainment | 1740
Transmission Line | 23118-T011-820 | PROVINCIAL - PLANNED TRANS LINE REP | 530900 Office Supplies | 60
Substation Operations | C0021140 | 98N-Stellarton Substation | 535705 Contractor Admin Overhead | 494166.53
Substation Operations | C0021140 | 98N-Stellarton Substation | 531400 Materials | 2051000
Transmission Line | C0023802 | L6515 Replacements and Upgrades | 530050 Regular Labour | 64791.01
Transmission Line | C0023802 | L6515 Replacements and Upgrades | 532500 Consulting | 60000
Substation Operations | C0031046 | 77V New Transformer | 531550 Contracts | 21596.16
Substation Operations | C0032382 | Susie Lake Substation Addition | 532500 Consulting | 100000
Transmission Line | C0041788 | L6516 Replacements and Upgrades Ph2 | 535705 Contractor Admin Overhead | 111694.83
Transmission Line | C0041791 | L6551 Replacements and Upgrades | 531550 Contracts | 1002500
Transmission Line | C0041807 | L5534 Replacements and Upgrades | 530050 Regular Labour | 12600.99
Transmission Line | C0041812 | L6040 Replacements and Upgrades | 531400 Materials | 137647
Substation Operations | C0041822 | WRC Spare Cable Repl & Storage Syst | 531550 Contracts | 2046
Large Industrial Reliability | C0044110 | 138kv Line Tap to 92V Substation | 532500 Consulting | 230000
ECEI | C0044391 | ECEI - Transmission | 532850 Application Software | 470000
ECEI | C0044391 | ECEI - Transmission | 605050 AFUDC Interest | 4050712.67
ECEI | C0045132 | ECEI - Energy Storage | 605050 AFUDC Interest | 10803356.73
Substation Operations | C0050852 | 10V-T1 Transformer Replacement | 531400 Materials | 1334472.37
Transmission Line | C0052299 | 2023 2024 Steel Tower Life Extensio | 535705 Contractor Admin Overhead | 132327.3
Transmission Line | C0052654 | L5541 Water Crossing Upgrades | 535705 Contractor Admin Overhead | 67392.92
Substation Operations | C0053234 | 96H-T1 Transformer Replacement | 531550 Contracts | 418869.45
Transmission Line | C0053295 | L5004 Kearney Lake Structure Replac | 531400 Materials | 864661
Substation Operations | C0055539 | 10H-T1 Transformer Replacement | 530200 Overtime Labour | 8250
Substation Operations | C0055539 | 10H-T1 Transformer Replacement | 531400 Materials | 1530000
Substation Operations | C0055557 | 76V-T1 Transformer Replacement | 530050 Regular Labour | 22860.04
Substation Operations | C0055557 | 76V-T1 Transformer Replacement | 531550 Contracts | 868165.04
Substation Operations | C0056240 | 2024-2025 Transmission Switch & Bre | 531400 Materials | 307981.56
Substation Operations | C0057682 | Spare Transformer Replacement | 535705 Contractor Admin Overhead | 2892.39
Substation Operations | C0057882 | 2024 Pennsylvania Breaker Replace | 535700 Admin Overheads | 143112.09
Substation Operations | C0059483 | Rebuild L5046 Tap | 531550 Contracts | 600000
Substation Operations | C0059483 | Rebuild L5046 Tap | 531400 Materials | 258000
Transmission Line | C0061403 | 2024 2025 Sacrificial Anode Install | 531550 Contracts | 387000
Transmission Line | C0061545 | L6006 Replacements and Upgrades | 535705 Contractor Admin Overhead | 181101.68
Transmission Line | C0061547 | L7022 Replacements and Upgrades | 531550 Contracts | 1130000
Transmission Line | C0061551 | L7009 Replacements and Upgrades Pha | 531550 Contracts | 1957839.77
Transmission Line | C0061743 | L6038 Realignment | 531550 Contracts | 528333.33
Substation Operations | C0063266 | Porter’s Lake Feeder Addition | 530050 Regular Labour | 0.01
Substation Operations | C0065024 | IR 662 - 132H Spider Lake BESS TPIF | 530050 Regular Labour | 8421.07
Substation Operations | C0065024 | IR 662 - 132H Spider Lake BESS TPIF | 531400 Materials | 144504.45
Substation Operations | C0065024 | IR 662 - 132H Spider Lake BESS TPIF | 532500 Consulting | 8421.07
Transmission Line | C0065294 | L5561 Reroute - CBU Expansion | 535100 Other Goods and Services | 12051.09
Transmission Line | C0067110 | L5532 Replacements and Upgrades | 535100 Other Goods and Services | 50000
Transmission Line | C0067111 | L5023 Rebuild | 531550 Contracts | 120000
Transmission Line | C0067112 | L5012 Replacements and Upgrades | 531550 Contracts | 0.03
Transmission Line | C0069231 | L8002 Replacements and Upgrades Ph1 | 535705 Contractor Admin Overhead | 238685.08
Transmission Line | C0069231 | L8002 Replacements and Upgrades Ph1 | 535650 Vehicle Allocated Costs | 49274.63
Substation Operations | C0069392 | 12V-T1 Transformer Replacement | 531400 Materials | 1406406
Substation Operations | C0069446 | IR 668 - Weavers Mountain Wind | 535705 Contractor Admin Overhead | 438891.36
Substation Operations | C0069535 | IR 669 TPIF - Higgins Mountain Wind | 532500 Consulting | 11333.3
Substation Operations | C0070086 | 10H-T2 Transformer Replacement | 531400 Materials | 1548399.96
Substation Operations | C0070086 | 10H-T2 Transformer Replacement | 531550 Contracts | 75000
Substation Operations | C0070328 | IR 673 TPIF - Benjamins Mill Wind | 536750 Capital Contributions | -720276.95
Substation Operations | C0070367 | IR 618 NU - Goose Harbour Lake Wind | 533400 Meals and Entertainment | 1636.36
Substation Operations | C0070586 | 22N-603 and 604 Switch Repl L6536 | 535650 Vehicle Allocated Costs | 20723.71
Substation Operations | C0070909 | 70W-T51 Transformer Replacement | 530050 Regular Labour | 68762.01
Substation Operations | C0072089 | 2P Mobile Transformer Replacement | 605050 AFUDC Interest | 20909.23
Transmission Line | C0072115 | L5511 Replacements and Upgrades | 531550 Contracts | 80000
Substation Operations | C0073308 | IR 677 TPIF - Wedgeport Wind | 605050 AFUDC Interest | 49044.01
Substation Operations | C0073308 | IR 677 TPIF - Wedgeport Wind | 530050 Regular Labour | 131245.3
Substation Operations | C0073309 | IR 677 NU - Wedgeport Wind | 535650 Vehicle Allocated Costs | 397002.03
Substation Operations | C0073975 | IR 671 NU - Bear Lake Wind | 530050 Regular Labour | 480980
Substation Operations | 14973-T018-820 | PRIMARY EQUIPMENT SPARES | 531550 Contracts | 24287.46
Substation Operations | 14841-T016-630 | PROTECTION MODIFICATIONS AND REPLAC | 531800 Freight Postage Delivery | 863.39
Transmission Line | 23115-T001-820 | PROVINCIAL TRANSMISSION LINE REPLAC | 535650 Vehicle Allocated Costs | 109554.5
Transmission Line | 23115-T001-820 | PROVINCIAL TRANSMISSION LINE REPLAC | 535950 Royalty, Easement, Appraisal | 1088.05
Transmission Line | 23115-T001-820 | PROVINCIAL TRANSMISSION LINE REPLAC | 531800 Freight Postage Delivery | 4735.22
Transmission Line | 23118-T011-820 | PROVINCIAL - PLANNED TRANS LINE REP | 535650 Vehicle Allocated Costs | 241040.3
Transmission Line | 23118-T011-820 | PROVINCIAL - PLANNED TRANS LINE REP | 535700 Admin Overheads | 276636.68
Substation Operations | 23120-T003-820 | PROVINCIAL-TRANS SUBSTATION PRIMARY | 530300 Term Labour | 67036.42
Substation Operations | 23120-T003-820 | PROVINCIAL-TRANS SUBSTATION PRIMARY | 530950 Travel Expense | 5977.39
Substation Operations | 23120-T003-820 | PROVINCIAL-TRANS SUBSTATION PRIMARY | 532200 Tools and Equipment | 33144.85
Substation Operations | 23121-T004-820 | PROVINCIAL- SUBSTATION ADDITIONS & | 534750 Personal Equipment | 2358.62
Vegetation Management | 43827-T010-840 | Transmission ROW Widening Routine | 535700 Admin Overheads | 23783.49
Substation Operations | C0011261 | 101W Port Mersey Expansion | 605050 AFUDC Interest | 217.03
Substation Operations | C0021140 | 98N-Stellarton Substation | 535700 Admin Overheads | 20385.93
Substation Operations | C0022247 | 1N-Onslow 138 kV Add Second 42 MVA | 531400 Materials | 247944.61
Substation Operations | C0022783 | 2020/2021 Gen Power Trans Refurb | 535100 Other Goods and Services | 1
Substation Operations | C0027162 | 129H Kearney Lake Substation Relo | 535100 Other Goods and Services | 1
Substation Operations | C0031048 | 91H-T11 Transformer Replacement | 531400 Materials | 4762399.94
AMO - Customer Operations | C0031268 | AMO Critical Equipment Online Mon. | 605050 AFUDC Interest | 659.94
Substation Operations | C0031286 | Spare Padmounted Substation | 532500 Consulting | 2282.65
Transmission Line | C0041791 | L6551 Replacements and Upgrades | 535650 Vehicle Allocated Costs | 8746.52
Transmission Line | C0041804 | 2022 Line Retirement Program | 531550 Contracts | 895000
Transmission Line | C0041812 | L6040 Replacements and Upgrades | 530050 Regular Labour | 7470.99
Substation Operations | C0041837 | 2022 2023 Substation PCB Equip Remo | 530050 Regular Labour | 85001.02
Substation Operations | C0041837 | 2022 2023 Substation PCB Equip Remo | 531400 Materials | 356000
Substation Operations | C0041837 | 2022 2023 Substation PCB Equip Remo | 535700 Admin Overheads | 61935.28
Transmission Line | C0043010 | 2022 2023 Wood Pole Retreatment Prg | 535100 Other Goods and Services | 50000
ECEI | C0044391 | ECEI - Transmission | 533400 Meals and Entertainment | 16308
Substation Operations | C0050834 | Spare EHV Breaker Replacements | 532500 Consulting | 0.12
Substation Operations | C0052994 | WRC 85S-GT1 85S-GT2 Transform Repl | 535700 Admin Overheads | 72728.98
Substation Operations | C0053195 | 47C-T1 and T2 PHP Transformer Repl | 530050 Regular Labour | 145206.32
Substation Operations | C0053195 | 47C-T1 and T2 PHP Transformer Repl | 535705 Contractor Admin Overhead | 61341.9
Substation Operations | C0055539 | 10H-T1 Transformer Replacement | 535100 Other Goods and Services | 248239.81
Substation Operations | C0055557 | 76V-T1 Transformer Replacement | 531800 Freight Postage Delivery | 72700
Substation Operations | C0055796 | 2023 EHV Breaker Replacements | 535650 Vehicle Allocated Costs | 124271.85
Substation Operations | C0056240 | 2024-2025 Transmission Switch & Bre | 531550 Contracts | 249999.96
Substation Operations | C0057882 | 2024 Pennsylvania Breaker Replace | 530950 Travel Expense | 740.14
Corporate Initiatives | C0060866 | Everwind 230kV Transmission Line | 535705 Contractor Admin Overhead | 108465
Transmission Line | C0061546 | L6514 Replacements and Upgrades | 530050 Regular Labour | 33082.2
Transmission Line | C0061550 | L5031 - Hubbards to East Chester | 535650 Vehicle Allocated Costs | 48572.72
Substation Operations | C0061883 | 129H - Kearney Lake Substation Rebu | 535700 Admin Overheads | 37259.48
Substation Operations | C0061883 | 129H - Kearney Lake Substation Rebu | 605050 AFUDC Interest | 3810.35
Substation Operations | C0062123 | 143H-Mount Uniacke Substation | 535950 Royalty, Easement, Appraisal | 812104.02
Substation Operations | C0062123 | 143H-Mount Uniacke Substation | 535705 Contractor Admin Overhead | 627650.8
Substation Operations | C0064903 | IR 664 - 99W Bridgewater BESS TPIF | 605050 AFUDC Interest | 12471.78
Substation Operations | C0068868 | Fall River Substation Addition | 531400 Materials | 3226661
Transmission Line | C0069231 | L8002 Replacements and Upgrades Ph1 | 535100 Other Goods and Services | 330000
Substation Operations | C0069234 | L5532 Reliability Improvements Phas | 531550 Contracts | 1310015.34
Transmission Line | C0069238 | 2025/2026 Steel Tower Refurbishment | 533400 Meals and Entertainment | 4000
Substation Operations | C0069394 | 16N-T1 Transformer Replacement | 530050 Regular Labour | 51668.98
Transmission Line | C0070048 | L5027B Replacements and Upgrades Ph | 535650 Vehicle Allocated Costs | 42968
Transmission Line | C0070048 | L5027B Replacements and Upgrades Ph | 535700 Admin Overheads | 48771.48
Substation Operations | C0070086 | 10H-T2 Transformer Replacement | 530950 Travel Expense | 1413.77
Substation Operations | C0070086 | 10H-T2 Transformer Replacement | 535700 Admin Overheads | 50234.45
Substation Operations | C0070328 | IR 673 TPIF - Benjamins Mill Wind | 532500 Consulting | 8500
Substation Operations | C0070328 | IR 673 TPIF - Benjamins Mill Wind | 530050 Regular Labour | 68572
Substation Operations | C0070328 | IR 673 TPIF - Benjamins Mill Wind | 530200 Overtime Labour | 2062.5
Substation Operations | C0070367 | IR 618 NU - Goose Harbour Lake Wind | 530950 Travel Expense | 4876.36
Substation Operations | C0070367 | IR 618 NU - Goose Harbour Lake Wind | 535650 Vehicle Allocated Costs | 89916.26
Substation Operations | C0070586 | 22N-603 and 604 Switch Repl L6536 | 530050 Regular Labour | 41540.37
Substation Operations | C0071888 | 92H-T61 Transformer Replacement | 530050 Regular Labour | 69555.75
Transmission Line | C0072115 | L5511 Replacements and Upgrades | 535650 Vehicle Allocated Costs | 748.82
Substation Operations | C0073308 | IR 677 TPIF - Wedgeport Wind | 535705 Contractor Admin Overhead | 24899.78
Transmission Line | C0073388 | L8002 Replacements and Upgrades U&U | 535650 Vehicle Allocated Costs | 1996.01
Transmission Line | C0073388 | L8002 Replacements and Upgrades U&U | 535700 Admin Overheads | 2265.6
Transmission Line | C0073388 | L8002 Replacements and Upgrades U&U | 531400 Materials | 12764.6
Substation Operations | C0073975 | IR 671 NU - Bear Lake Wind | 531400 Materials | 1182204
Transmission Line | 23118-T011-820 | PROVINCIAL - PLANNED TRANS LINE REP | 535950 Royalty, Easement, Appraisal | 24996
Transmission Line | 23118-T011-820 | PROVINCIAL - PLANNED TRANS LINE REP | 531550 Contracts | 3070000
Substation Operations | 23121-T004-820 | PROVINCIAL- SUBSTATION ADDITIONS & | 530900 Office Supplies | 153.19
Capital Projects Group - Transmission | 51098-T952 | L-6014 Shannon Park Trans Towers | 536450 First Nation Commitments | 220212.24
Substation Operations | C0011261 | 101W Port Mersey Expansion | 535650 Vehicle Allocated Costs | 18317.76
Substation Operations | C0011261 | 101W Port Mersey Expansion | 535100 Other Goods and Services | 234.8
Substation Operations | C0011358 | New Bridgewater Substation | 535650 Vehicle Allocated Costs | 11973.62
Substation Operations | C0011358 | New Bridgewater Substation | 535700 Admin Overheads | 13590.81
Substation Operations | C0022247 | 1N-Onslow 138 kV Add Second 42 MVA | 530050 Regular Labour | 37917.63
Substation Operations | C0031044 | 67N-713 230 kV Breaker Replacem | 531400 Materials | 430000
Substation Operations | C0031046 | 77V New Transformer | 535700 Admin Overheads | 12479.4
Substation Operations | C0031048 | 91H-T11 Transformer Replacement | 530950 Travel Expense | 3535
Substation Operations | C0031048 | 91H-T11 Transformer Replacement | 530200 Overtime Labour | 8250
Transmission Line | C0031122 | L6539-2021 Replacements and Upgrade | 535700 Admin Overheads | 4813.77
AMO - Customer Operations | C0031268 | AMO Critical Equipment Online Mon. | 530050 Regular Labour | 8000
Substation Operations | C0032382 | Susie Lake Substation Addition | 535650 Vehicle Allocated Costs | 17960.18
Substation Operations | C0032382 | Susie Lake Substation Addition | 531550 Contracts | 1000000
Transmission Line | C0041788 | L6516 Replacements and Upgrades Ph2 | 531550 Contracts | 772333.14
Transmission Line | C0041788 | L6516 Replacements and Upgrades Ph2 | 535950 Royalty, Easement, Appraisal | 7800
Transmission Line | C0041807 | L5534 Replacements and Upgrades | 531400 Materials | 16164
Transmission Line | C0041812 | L6040 Replacements and Upgrades | 535705 Contractor Admin Overhead | 65079
Substation Operations | C0041822 | WRC Spare Cable Repl & Storage Syst | 535700 Admin Overheads | 5021.49
Substation Operations | C0041837 | 2022 2023 Substation PCB Equip Remo | 533400 Meals and Entertainment | 700
Substation Operations | C0043571 | 2022-2023 Transmission Switch & B | 535650 Vehicle Allocated Costs | 20493.95
Transmission Line | C0044172 | L7005 Canso Crossing Vibration Miti | 535650 Vehicle Allocated Costs | 4989.3
ECEI | C0044391 | ECEI - Transmission | 532600 Membership Dues | 28800
ECEI | C0045132 | ECEI - Energy Storage | 532600 Membership Dues | 232289.73
Substation Operations | C0050852 | 10V-T1 Transformer Replacement | 531550 Contracts | 147689.74
Substation Operations | C0053214 | 76W-T1 Transformer Replacement | 531400 Materials | 2190789
Substation Operations | C0053234 | 96H-T1 Transformer Replacement | 535700 Admin Overheads | 82936.86
Substation Operations | C0053234 | 96H-T1 Transformer Replacement | 530200 Overtime Labour | 7660.56
Substation Operations | C0053234 | 96H-T1 Transformer Replacement | 535100 Other Goods and Services | 220757.64
Large Industrial Reliability | C0053316 | Michelin Waterville Dynamic Voltage | 530950 Travel Expense | 10000
Large Industrial Reliability | C0053316 | Michelin Waterville Dynamic Voltage | 531550 Contracts | 749918.57
Large Industrial Reliability | C0053316 | Michelin Waterville Dynamic Voltage | 536750 Capital Contributions | -686857.7
Substation Operations | C0055539 | 10H-T1 Transformer Replacement | 531550 Contracts | 547399.97
Substation Operations | C0055557 | 76V-T1 Transformer Replacement | 531300 iExpenses-KMs (milage) | 2023.92
Transmission Line | C0055696 | L5031 Replacement & Upgrade R.C Tap | 535650 Vehicle Allocated Costs | 1497.14
Transmission Line | C0056721 | 2023 Transmission Inspection Progra | 535100 Other Goods and Services | 1
Substation Operations | C0057882 | 2024 Pennsylvania Breaker Replace | 530050 Regular Labour | 252732.28
AMO - Customer Operations | C0060003 | AMO 85S Thermal Camera Upgrade | 531550 Contracts | 15000
Transmission Line | C0061387 | 2024 2025 Wood Pole Retreatment Pro | 530050 Regular Labour | 22501
Transmission Line | C0061387 | 2024 2025 Wood Pole Retreatment Pro | 535705 Contractor Admin Overhead | 105861.84
Transmission Line | C0061403 | 2024 2025 Sacrificial Anode Install | 530200 Overtime Labour | 500
Transmission Line | C0061403 | 2024 2025 Sacrificial Anode Install | 531400 Materials | 82000
Transmission Line | C0061543 | L5048 Replacements and Upgrades | 531400 Materials | -0.03
Transmission Line | C0061544 | L6536 Replacements and Upgrades | 535700 Admin Overheads | 27181.06
Transmission Line | C0061545 | L6006 Replacements and Upgrades | 535700 Admin Overheads | 16195.61
Transmission Line | C0061551 | L7009 Replacements and Upgrades Pha | 535700 Admin Overheads | 67661.63
Substation Operations | C0062123 | 143H-Mount Uniacke Substation | 530050 Regular Labour | 310000.98
Substation Operations | C0064903 | IR 664 - 99W Bridgewater BESS TPIF | 532500 Consulting | 8421.07
Transmission Line | C0067111 | L5023 Rebuild | 531400 Materials | 20500
Transmission Line | C0067112 | L5012 Replacements and Upgrades | 531400 Materials | -0.03
Substation Operations | C0068868 | Fall River Substation Addition | 530050 Regular Labour | 21001
Substation Operations | C0068961 | 2025 PCB Substation Sampling and Re | 535100 Other Goods and Services | 550000
Substation Operations | C0068969 | 2026 Pennsylvania Breaker Replaceme | 530950 Travel Expense | 2000.04
Transmission Line | C0069227 | L6516 Replacements and Upgrades Ph3 | 530050 Regular Labour | 128208.98
Transmission Line | C0069227 | L6516 Replacements and Upgrades Ph3 | 535100 Other Goods and Services | 355194.85
Substation Operations | C0069234 | L5532 Reliability Improvements Phas | 535705 Contractor Admin Overhead | 189454.42
Substation Operations | C0069534 | IR 669 NU - Higgins Mountain Wind | 533400 Meals and Entertainment | 2500.02
Substation Operations | C0069534 | IR 669 NU - Higgins Mountain Wind | 535700 Admin Overheads | 106779.06
Substation Operations | C0069535 | IR 669 TPIF - Higgins Mountain Wind | 533400 Meals and Entertainment | 333.32
Substation Operations | C0070586 | 22N-603 and 604 Switch Repl L6536 | 535100 Other Goods and Services | 22875.3
Substation Operations | C0070909 | 70W-T51 Transformer Replacement | 605050 AFUDC Interest | 80448.47
Substation Operations | C0071888 | 92H-T61 Transformer Replacement | 605050 AFUDC Interest | 104138.66
Substation Operations | C0071889 | 77V-T1 Transformer Replacement | 605050 AFUDC Interest | 94596.87
Substation Operations | C0072609 | 2024 Substation Fence Upgrades | 535100 Other Goods and Services | 65082.57
ECEI | C0072808 | Synchronous Condensers | 533400 Meals and Entertainment | 1000
Substation Operations | C0073309 | IR 677 NU - Wedgeport Wind | 531550 Contracts | 7072630
Substation Operations | C0073975 | IR 671 NU - Bear Lake Wind | 535705 Contractor Admin Overhead | 287411.95
Substation Operations | 14841-T016-630 | PROTECTION MODIFICATIONS AND REPLAC | 535705 Contractor Admin Overhead | 2255.81
Substation Operations | 14841-T016-630 | PROTECTION MODIFICATIONS AND REPLAC | 531200 iExpenses-Accommodations | 746.03
Substation Operations | 14841-T016-630 | PROTECTION MODIFICATIONS AND REPLAC | 535100 Other Goods and Services | 1067.72
Substation Operations | 23120-T003-820 | PROVINCIAL-TRANS SUBSTATION PRIMARY | 535650 Vehicle Allocated Costs | 357176.47
Substation Operations | 23120-T003-820 | PROVINCIAL-TRANS SUBSTATION PRIMARY | 530320 Term Labour-Overtime | 14286.81
Substation Operations | 23121-T004-820 | PROVINCIAL- SUBSTATION ADDITIONS & | 535700 Admin Overheads | 107603.2
Substation Operations | 23121-T004-820 | PROVINCIAL- SUBSTATION ADDITIONS & | 535705 Contractor Admin Overhead | 38767.8
Vegetation Management | 43827-T010-840 | Transmission ROW Widening Routine | 533400 Meals and Entertainment | 3600
Capital Projects Group - Transmission | 51098-T952 | L-6014 Shannon Park Trans Towers | 533400 Meals and Entertainment | 11450
Substation Operations | C0011261 | 101W Port Mersey Expansion | 535705 Contractor Admin Overhead | 53.5
Substation Operations | C0022247 | 1N-Onslow 138 kV Add Second 42 MVA | 535705 Contractor Admin Overhead | 50616.99
Substation Operations | C0022743 | Retire 9H-Yale Street Substation | 530050 Regular Labour | 20776.02
AMO - Customer Operations | C0031268 | AMO Critical Equipment Online Mon. | 535705 Contractor Admin Overhead | 1012.34
AMO - Customer Operations | C0031268 | AMO Critical Equipment Online Mon. | 532500 Consulting | 10000
Substation Operations | C0032382 | Susie Lake Substation Addition | 605050 AFUDC Interest | 45961.64
Large Industrial Reliability | C0044110 | 138kv Line Tap to 92V Substation | 535705 Contractor Admin Overhead | 21693
ECEI | C0044391 | ECEI - Transmission | 531550 Contracts | 20077498
ECEI | C0044391 | ECEI - Transmission | 536450 First Nation Commitments | 254025
ECEI | C0045132 | ECEI - Energy Storage | 530900 Office Supplies | 11532.72
ECEI | C0045132 | ECEI - Energy Storage | 531200 iExpenses-Accommodations | 18000
Substation Operations | C0050834 | Spare EHV Breaker Replacements | 535700 Admin Overheads | 7078.98
Substation Operations | C0050842 | 2024 Bulk Oil Breaker Replacement | 531400 Materials | 1815058.8
Substation Operations | C0050852 | 10V-T1 Transformer Replacement | 533400 Meals and Entertainment | 350.04
Transmission Line | C0052299 | 2023 2024 Steel Tower Life Extensio | 531550 Contracts | 915000
Substation Operations | C0053214 | 76W-T1 Transformer Replacement | 531550 Contracts | 8050
Substation Operations | C0053234 | 96H-T1 Transformer Replacement | 535705 Contractor Admin Overhead | 63969.72
Substation Operations | C0053234 | 96H-T1 Transformer Replacement | 530950 Travel Expense | 8349.52
Transmission Line | C0053295 | L5004 Kearney Lake Structure Replac | 535100 Other Goods and Services | 293447.95
Substation Operations | C0055557 | 76V-T1 Transformer Replacement | 531400 Materials | 1441013.92
Substation Operations | C0055557 | 76V-T1 Transformer Replacement | 535100 Other Goods and Services | 374647
Transmission Line | C0055696 | L5031 Replacement & Upgrade R.C Tap | 531550 Contracts | 250000
Transmission Line | C0055696 | L5031 Replacement & Upgrade R.C Tap | 531400 Materials | 25000
Substation Operations | C0057682 | Spare Transformer Replacement | 605050 AFUDC Interest | 68.32
Substation Operations | C0057882 | 2024 Pennsylvania Breaker Replace | 535650 Vehicle Allocated Costs | 126083.29
Transmission Line | C0061547 | L7022 Replacements and Upgrades | 535705 Contractor Admin Overhead | 163420.6
Transmission Line | C0061551 | L7009 Replacements and Upgrades Pha | 535705 Contractor Admin Overhead | 283142.79
Transmission Line | C0061743 | L6038 Realignment | 535705 Contractor Admin Overhead | 76407.57
Substation Operations | C0061883 | 129H - Kearney Lake Substation Rebu | 532500 Consulting | 72388.26
Substation Operations | C0062123 | 143H-Mount Uniacke Substation | 535650 Vehicle Allocated Costs | 156029.07
Substation Operations | C0064903 | IR 664 - 99W Bridgewater BESS TPIF | 530950 Travel Expense | 421.07
Substation Operations | C0064903 | IR 664 - 99W Bridgewater BESS TPIF | 535100 Other Goods and Services | 38470
Transmission Line | C0065294 | L5561 Reroute - CBU Expansion | 535705 Contractor Admin Overhead | 2296.3
AMO - Power Production | C0068467 | AMO Transmission Risk Profiling | 530050 Regular Labour | 11500
AMO - Power Production | C0068467 | AMO Transmission Risk Profiling | 605050 AFUDC Interest | 777.83
Substation Operations | C0068966 | 2025 Merlin Gerin Breaker Replaceme | 530050 Regular Labour | 50000.06
Transmission Line | C0069232 | L6021 Replacements and Upgrades Ph1 | 535650 Vehicle Allocated Costs | 63420.05
Transmission Line | C0069232 | L6021 Replacements and Upgrades Ph1 | 531550 Contracts | 1864647.32
Substation Operations | C0069234 | L5532 Reliability Improvements Phas | 531400 Materials | 1253430
Substation Operations | C0069394 | 16N-T1 Transformer Replacement | 535705 Contractor Admin Overhead | 11569.61
Substation Operations | C0069394 | 16N-T1 Transformer Replacement | 535700 Admin Overheads | 29258.14
Substation Operations | C0069534 | IR 669 NU - Higgins Mountain Wind | 536750 Capital Contributions | -2419295.88
Substation Operations | C0069534 | IR 669 NU - Higgins Mountain Wind | 530950 Travel Expense | 4713.32
Substation Operations | C0069535 | IR 669 TPIF - Higgins Mountain Wind | 531400 Materials | 214666.66
Transmission Line | C0070048 | L5027B Replacements and Upgrades Ph | 531400 Materials | 521573.52
Substation Operations | C0070086 | 10H-T2 Transformer Replacement | 533400 Meals and Entertainment | 415.04
Substation Operations | C0070327 | IR 673 NU - Benjamins Mill Wind | 535100 Other Goods and Services | 16129.6
Substation Operations | C0070328 | IR 673 TPIF - Benjamins Mill Wind | 535700 Admin Overheads | 40220.25
Substation Operations | C0070451 | 2026 Switch and Breaker Replacement | 535650 Vehicle Allocated Costs | 39139.27
Substation Operations | C0071889 | 77V-T1 Transformer Replacement | 535705 Contractor Admin Overhead | 14461.98
Substation Operations | C0073309 | IR 677 NU - Wedgeport Wind | 533400 Meals and Entertainment | 24000
Substation Operations | C0073309 | IR 677 NU - Wedgeport Wind | 531400 Materials | 10304584
Substation Operations | C0073309 | IR 677 NU - Wedgeport Wind | 533410 Overtime Meals | 5000
Substation Operations | 14973-T018-820 | PRIMARY EQUIPMENT SPARES | 531800 Freight Postage Delivery | 224.52
Transmission Line | 23115-T001-820 | PROVINCIAL TRANSMISSION LINE REPLAC | 535705 Contractor Admin Overhead | 296471
Transmission Line | 23115-T001-820 | PROVINCIAL TRANSMISSION LINE REPLAC | 532200 Tools and Equipment | 888.95
Transmission Line | 23115-T001-820 | PROVINCIAL TRANSMISSION LINE REPLAC | 530950 Travel Expense | 3887.64
Transmission Line | 23115-T001-820 | PROVINCIAL TRANSMISSION LINE REPLAC | 530050 Regular Labour | 102600.99
Substation Operations | 23120-T003-820 | PROVINCIAL-TRANS SUBSTATION PRIMARY | 535100 Other Goods and Services | 2611.68
Substation Operations | 23120-T003-820 | PROVINCIAL-TRANS SUBSTATION PRIMARY | 535705 Contractor Admin Overhead | 94937.89
Substation Operations | 23121-T004-820 | PROVINCIAL- SUBSTATION ADDITIONS & | 531800 Freight Postage Delivery | 2964.38
Substation Operations | 23121-T004-820 | PROVINCIAL- SUBSTATION ADDITIONS & | 455300 Other Income-Salvage | -308.92
Vegetation Management | 43827-T010-840 | Transmission ROW Widening Routine | 530050 Regular Labour | 42001
Capital Projects Group - Transmission | 51098-T952 | L-6014 Shannon Park Trans Towers | 530050 Regular Labour | 350500
Capital Projects Group - Transmission | 51098-T952 | L-6014 Shannon Park Trans Towers | 535100 Other Goods and Services | 10583974.37
Substation Operations | C0011261 | 101W Port Mersey Expansion | 530200 Overtime Labour | 668.4
Substation Operations | C0011358 | New Bridgewater Substation | 535100 Other Goods and Services | 111212
Substation Operations | C0021140 | 98N-Stellarton Substation | 530050 Regular Labour | 36001
Substation Operations | C0031046 | 77V New Transformer | 531400 Materials | 431924.9
Substation Operations | C0031048 | 91H-T11 Transformer Replacement | 605050 AFUDC Interest | 91052.99
Transmission Line | C0031122 | L6539-2021 Replacements and Upgrade | 535650 Vehicle Allocated Costs | 4240.97
Transmission Line | C0033644 | 2021-2022 Steel Tower Life Extensio | 535650 Vehicle Allocated Costs | 0.5
Transmission Line | C0033644 | 2021-2022 Steel Tower Life Extensio | 535700 Admin Overheads | 0.57
Transmission Line | C0041807 | L5534 Replacements and Upgrades | 531550 Contracts | 205500
Substation Operations | C0041822 | WRC Spare Cable Repl & Storage Syst | 531400 Materials | 81838.44
Substation Operations | C0041822 | WRC Spare Cable Repl & Storage Syst | 535650 Vehicle Allocated Costs | 4423.98
Substation Operations | C0041830 | Spare Power Prod Unit Transformer | 531550 Contracts | 20000.01
Substation Operations | C0041837 | 2022 2023 Substation PCB Equip Remo | 531550 Contracts | 60000
Large Industrial Reliability | C0044110 | 138kv Line Tap to 92V Substation | 605050 AFUDC Interest | 1247167.96
Large Industrial Reliability | C0044110 | 138kv Line Tap to 92V Substation | 535700 Admin Overheads | 169878
Transmission Line | C0044172 | L7005 Canso Crossing Vibration Miti | 535100 Other Goods and Services | 1
ECEI | C0044391 | ECEI - Transmission | 532500 Consulting | 2593218
Substation Operations | C0050842 | 2024 Bulk Oil Breaker Replacement | 531550 Contracts | 85821.84
Substation Operations | C0050842 | 2024 Bulk Oil Breaker Replacement | 535700 Admin Overheads | 152228.25
Substation Operations | C0050852 | 10V-T1 Transformer Replacement | 535705 Contractor Admin Overhead | 21358.86
Substation Operations | C0053158 | 77V-T52 Transformer Replacement | 530050 Regular Labour | -0.1
Substation Operations | C0053214 | 76W-T1 Transformer Replacement | 533400 Meals and Entertainment | 346.56
Substation Operations | C0053214 | 76W-T1 Transformer Replacement | 605050 AFUDC Interest | 61063.01
Large Industrial Reliability | C0053316 | Michelin Waterville Dynamic Voltage | 531400 Materials | 2154991
Substation Operations | C0055539 | 10H-T1 Transformer Replacement | 535705 Contractor Admin Overhead | 79164.98
Transmission Line | C0055696 | L5031 Replacement & Upgrade R.C Tap | 530050 Regular Labour | 3001
Substation Operations | C0056240 | 2024-2025 Transmission Switch & Bre | 535705 Contractor Admin Overhead | 36155.04
Corporate Initiatives | C0060866 | Everwind 230kV Transmission Line | 531550 Contracts | 750000
Substation Operations | C0061046 | 2024 Merlin Gerin Breaker Replaceme | 531400 Materials | 119394
Transmission Line | C0061387 | 2024 2025 Wood Pole Retreatment Pro | 531550 Contracts | 732000
Transmission Line | C0061387 | 2024 2025 Wood Pole Retreatment Pro | 530950 Travel Expense | 2972
Transmission Line | C0061387 | 2024 2025 Wood Pole Retreatment Pro | 535100 Other Goods and Services | 50000
Transmission Line | C0061387 | 2024 2025 Wood Pole Retreatment Pro | 535700 Admin Overheads | 13661.62
Transmission Line | C0061403 | 2024 2025 Sacrificial Anode Install | 535700 Admin Overheads | 6087.87
Transmission Line | C0061544 | L6536 Replacements and Upgrades | 535705 Contractor Admin Overhead | 23139.2
Transmission Line | C0061547 | L7022 Replacements and Upgrades | 530050 Regular Labour | 86001.01
Transmission Line | C0061547 | L7022 Replacements and Upgrades | 535100 Other Goods and Services | 250000
Transmission Line | C0061552 | L6043 Replacements and Upgrades | 535950 Royalty, Easement, Appraisal | 0.04
Transmission Line | C0061743 | L6038 Realignment | 535700 Admin Overheads | 16564.54
Substation Operations | C0064883 | IR 697 - 105V White Rock BESS TPIF | 535100 Other Goods and Services | 41739
Substation Operations | C0064883 | IR 697 - 105V White Rock BESS TPIF | 530050 Regular Labour | 11538.47
Substation Operations | C0064883 | IR 697 - 105V White Rock BESS TPIF | 533400 Meals and Entertainment | 288.47
Substation Operations | C0065024 | IR 662 - 132H Spider Lake BESS TPIF | 535100 Other Goods and Services | 38470
AMO - Power Production | C0068467 | AMO Transmission Risk Profiling | 532500 Consulting | 6000
Substation Operations | C0068969 | 2026 Pennsylvania Breaker Replaceme | 535700 Admin Overheads | 54262.96
Substation Operations | C0068969 | 2026 Pennsylvania Breaker Replaceme | 535650 Vehicle Allocated Costs | 47806.2
Transmission Line | C0069238 | 2025/2026 Steel Tower Refurbishment | 535700 Admin Overheads | 18409.23
Substation Operations | C0069392 | 12V-T1 Transformer Replacement | 535705 Contractor Admin Overhead | 11569.61
Substation Operations | C0069446 | IR 668 - Weavers Mountain Wind | 531550 Contracts | 2873829.72
Substation Operations | C0069534 | IR 669 NU - Higgins Mountain Wind | 531550 Contracts | 693333.32
Substation Operations | C0069535 | IR 669 TPIF - Higgins Mountain Wind | 531550 Contracts | 93333.32
Substation Operations | C0069535 | IR 669 TPIF - Higgins Mountain Wind | 535100 Other Goods and Services | 61903.1
Transmission Line | C0070048 | L5027B Replacements and Upgrades Ph | 535950 Royalty, Easement, Appraisal | 40000
Substation Operations | C0070327 | IR 673 NU - Benjamins Mill Wind | 531400 Materials | 31000
Substation Operations | C0070386 | IR 618 TPIF - Goose Harbour Lake Wi | 535700 Admin Overheads | 83412.75
Substation Operations | C0070909 | 70W-T51 Transformer Replacement | 531550 Contracts | 80000
Substation Operations | C0070909 | 70W-T51 Transformer Replacement | 535650 Vehicle Allocated Costs | 34304.06
Substation Operations | C0070909 | 70W-T51 Transformer Replacement | 535705 Contractor Admin Overhead | 11569.61
Substation Operations | C0071889 | 77V-T1 Transformer Replacement | 533400 Meals and Entertainment | 170.36
ECEI | C0072808 | Synchronous Condensers | 530050 Regular Labour | 13056115
Substation Operations | C0073308 | IR 677 TPIF - Wedgeport Wind | 535100 Other Goods and Services | 60040.4
Substation Operations | C0073309 | IR 677 NU - Wedgeport Wind | 530050 Regular Labour | 756028
Substation Operations | C0073975 | IR 671 NU - Bear Lake Wind | 530200 Overtime Labour | 56723
Substation Operations | 14973-T018-820 | PRIMARY EQUIPMENT SPARES | 533400 Meals and Entertainment | 59.46
Substation Operations | 14973-T018-820 | PRIMARY EQUIPMENT SPARES | 530050 Regular Labour | 3340.28
Substation Operations | 14841-T016-630 | PROTECTION MODIFICATIONS AND REPLAC | 455300 Other Income-Salvage | -255.95
Substation Operations | 23120-T003-820 | PROVINCIAL-TRANS SUBSTATION PRIMARY | 531400 Materials | 941368.55
Substation Operations | 23120-T003-820 | PROVINCIAL-TRANS SUBSTATION PRIMARY | 531800 Freight Postage Delivery | 20836.46
Substation Operations | 23121-T004-820 | PROVINCIAL- SUBSTATION ADDITIONS & | 530050 Regular Labour | 149399.03
Capital Projects Group - Transmission | 51098-T952 | L-6014 Shannon Park Trans Towers | 530950 Travel Expense | 26500
Substation Operations | C0011261 | 101W Port Mersey Expansion | 530050 Regular Labour | 36383.56
Substation Operations | C0022743 | Retire 9H-Yale Street Substation | 535100 Other Goods and Services | 12964
Substation Operations | C0031048 | 91H-T11 Transformer Replacement | 532500 Consulting | 29999.98
Substation Operations | C0031048 | 91H-T11 Transformer Replacement | 535650 Vehicle Allocated Costs | 81090.18
Transmission Line | C0031122 | L6539-2021 Replacements and Upgrade | 535705 Contractor Admin Overhead | 91110.6
Substation Operations | C0031267 | 2022 Oil Containment Program | 535100 Other Goods and Services | 1
Substation Operations | C0041830 | Spare Power Prod Unit Transformer | 530050 Regular Labour | 28834.36
Substation Operations | C0041837 | 2022 2023 Substation PCB Equip Remo | 530300 Term Labour | 7500
Transmission Line | C0043010 | 2022 2023 Wood Pole Retreatment Prg | 531550 Contracts | 40000
Large Industrial Reliability | C0044110 | 138kv Line Tap to 92V Substation | 530050 Regular Labour | 300000
ECEI | C0045132 | ECEI - Energy Storage | 530950 Travel Expense | 137844.46
ECEI | C0045132 | ECEI - Energy Storage | 532500 Consulting | 742085
ECEI | C0045132 | ECEI - Energy Storage | 534650 Training and Development | 54052.61
Transmission Line | C0050835 | 2023/2024 Steel Tower Refurbishment | 531550 Contracts | 555000
Substation Operations | C0050852 | 10V-T1 Transformer Replacement | 535650 Vehicle Allocated Costs | 56253.2
Substation Operations | C0053158 | 77V-T52 Transformer Replacement | 535100 Other Goods and Services | 166054.4
Substation Operations | C0053195 | 47C-T1 and T2 PHP Transformer Repl | 535650 Vehicle Allocated Costs | 75276.4
Large Industrial Reliability | C0053316 | Michelin Waterville Dynamic Voltage | 530050 Regular Labour | 95000
Transmission Line | C0055696 | L5031 Replacement & Upgrade R.C Tap | 535705 Contractor Admin Overhead | 36155
Substation Operations | C0059483 | Rebuild L5046 Tap | 535705 Contractor Admin Overhead | 86772
Substation Operations | C0059483 | Rebuild L5046 Tap | 530050 Regular Labour | 53002
Corporate Initiatives | C0060866 | Everwind 230kV Transmission Line | 535650 Vehicle Allocated Costs | 107259.2
Corporate Initiatives | C0060866 | Everwind 230kV Transmission Line | 535700 Admin Overheads | 121745.9
Transmission Line | C0061543 | L5048 Replacements and Upgrades | 530050 Regular Labour | -0.01
Transmission Line | C0061545 | L6006 Replacements and Upgrades | 531400 Materials | 483304.63
Transmission Line | C0061552 | L6043 Replacements and Upgrades | 535100 Other Goods and Services | 150000
Substation Operations | C0062123 | 143H-Mount Uniacke Substation | 535700 Admin Overheads | 177102.76
Transmission Line | C0067110 | L5532 Replacements and Upgrades | 535650 Vehicle Allocated Costs | 0.5
Transmission Line | C0069227 | L6516 Replacements and Upgrades Ph3 | 531400 Materials | 534245.15
Transmission Line | C0069231 | L8002 Replacements and Upgrades Ph1 | 535950 Royalty, Easement, Appraisal | 25000
Transmission Line | C0069232 | L6021 Replacements and Upgrades Ph1 | 535705 Contractor Admin Overhead | 269665.3
Substation Operations | C0069392 | 12V-T1 Transformer Replacement | 531550 Contracts | 80000
Substation Operations | C0069394 | 16N-T1 Transformer Replacement | 531550 Contracts | 80000
Substation Operations | C0070386 | IR 618 TPIF - Goose Harbour Lake Wi | 530950 Travel Expense | 4876.36
Substation Operations | C0070451 | 2026 Switch and Breaker Replacement | 605050 AFUDC Interest | 19518.46
Transmission Line | C0071771 | 2024 Non-NERC Trans LIDAR Surveys | 535650 Vehicle Allocated Costs | 6186.11
Substation Operations | C0071889 | 77V-T1 Transformer Replacement | 531550 Contracts | 100000
Substation Operations | C0071889 | 77V-T1 Transformer Replacement | 530050 Regular Labour | 69555.75
Substation Operations | C0072308 | Dartmouth Substation Addition | 535700 Admin Overheads | 17213.67
Substation Operations | C0072308 | Dartmouth Substation Addition | 535705 Contractor Admin Overhead | 3470.73
Substation Operations | C0072308 | Dartmouth Substation Addition | 532500 Consulting | 35000
ECEI | C0072808 | Synchronous Condensers | 530950 Travel Expense | 2000
Substation Operations | C0073308 | IR 677 TPIF - Wedgeport Wind | 531550 Contracts | 172173.9
Substation Operations | C0073308 | IR 677 TPIF - Wedgeport Wind | 535700 Admin Overheads | 75994.78
Substation Operations | C0073308 | IR 677 TPIF - Wedgeport Wind | 536750 Capital Contributions | -851230.56
Substation Operations | C0073309 | IR 677 NU - Wedgeport Wind | 535100 Other Goods and Services | 1857480
Substation Operations | 14841-T016-630 | PROTECTION MODIFICATIONS AND REPLAC | 530320 Term Labour-Overtime | 971.26
Substation Operations | 14841-T016-630 | PROTECTION MODIFICATIONS AND REPLAC | 531300 iExpenses-KMs (milage) | 764.15
Transmission Line | 23118-T011-820 | PROVINCIAL - PLANNED TRANS LINE REP | 530200 Overtime Labour | 82116
Transmission Line | 23118-T011-820 | PROVINCIAL - PLANNED TRANS LINE REP | 530300 Term Labour | 4356
Substation Operations | 23120-T003-820 | PROVINCIAL-TRANS SUBSTATION PRIMARY | 530900 Office Supplies | 86.23
Substation Operations | 23120-T003-820 | PROVINCIAL-TRANS SUBSTATION PRIMARY | 536150 Repairs & Maintenance | -6999.7
Substation Operations | 23121-T004-820 | PROVINCIAL- SUBSTATION ADDITIONS & | 530200 Overtime Labour | 58910.44
Substation Operations | 23121-T004-820 | PROVINCIAL- SUBSTATION ADDITIONS & | 530950 Travel Expense | 928.5
Substation Operations | 23121-T004-820 | PROVINCIAL- SUBSTATION ADDITIONS & | 533410 Overtime Meals | 1749.15
Substation Operations | 23121-T004-820 | PROVINCIAL- SUBSTATION ADDITIONS & | 532200 Tools and Equipment | 430.93
Capital Projects Group - Transmission | 51098-T952 | L-6014 Shannon Park Trans Towers | 605050 AFUDC Interest | 1605220.99
Substation Operations | C0022247 | 1N-Onslow 138 kV Add Second 42 MVA | 533400 Meals and Entertainment | 249.92
Transmission Line | C0031122 | L6539-2021 Replacements and Upgrade | 535100 Other Goods and Services | 400000
Substation Operations | C0031286 | Spare Padmounted Substation | 531400 Materials | 1130944.36
Transmission Line | C0041791 | L6551 Replacements and Upgrades | 531400 Materials | 320177.58
Substation Operations | C0041837 | 2022 2023 Substation PCB Equip Remo | 532500 Consulting | 5000
Substation Operations | C0041840 | Legacy Oil Containment Refurbish | 535650 Vehicle Allocated Costs | -0.01
Transmission Line | C0043010 | 2022 2023 Wood Pole Retreatment Prg | 530050 Regular Labour | 1001
Large Industrial Reliability | C0044110 | 138kv Line Tap to 92V Substation | 531550 Contracts | 150000
Transmission Line | C0044172 | L7005 Canso Crossing Vibration Miti | 535700 Admin Overheads | 5663.19
Transmission Line | C0044172 | L7005 Canso Crossing Vibration Miti | 531550 Contracts | 350000
Transmission Line | C0044172 | L7005 Canso Crossing Vibration Miti | 530050 Regular Labour | 10001
ECEI | C0044391 | ECEI - Transmission | 532750 Subscription/Info. Software | 42587
ECEI | C0045132 | ECEI - Energy Storage | 531400 Materials | 174166927
ECEI | C0045132 | ECEI - Energy Storage | 536100 Rental/Maint of Equipment | 9000
Substation Operations | C0050842 | 2024 Bulk Oil Breaker Replacement | 530950 Travel Expense | 648
Transmission Line | C0052299 | 2023 2024 Steel Tower Life Extensio | 531400 Materials | 9500
Substation Operations | C0053158 | 77V-T52 Transformer Replacement | 531400 Materials | 130000
Substation Operations | C0053195 | 47C-T1 and T2 PHP Transformer Repl | 535100 Other Goods and Services | 349307.68
Substation Operations | C0053214 | 76W-T1 Transformer Replacement | 530950 Travel Expense | 2000.04
Substation Operations | C0053234 | 96H-T1 Transformer Replacement | 530050 Regular Labour | 139696.12
Substation Operations | C0055557 | 76V-T1 Transformer Replacement | 535705 Contractor Admin Overhead | 125554.06
Substation Operations | C0057682 | Spare Transformer Replacement | 535700 Admin Overheads | 13340.34
Substation Operations | C0059483 | Rebuild L5046 Tap | 535700 Admin Overheads | 30012.92
Substation Operations | C0061046 | 2024 Merlin Gerin Breaker Replaceme | 535650 Vehicle Allocated Costs | 14863.86
Transmission Line | C0061543 | L5048 Replacements and Upgrades | 535705 Contractor Admin Overhead | -0.02
Transmission Line | C0061543 | L5048 Replacements and Upgrades | 535650 Vehicle Allocated Costs | -0.01
Transmission Line | C0061545 | L6006 Replacements and Upgrades | 530050 Regular Labour | 28601.01
Transmission Line | C0061546 | L6514 Replacements and Upgrades | 535100 Other Goods and Services | 100000
Transmission Line | C0061550 | L5031 - Hubbards to East Chester | 531400 Materials | 955000
Transmission Line | C0061551 | L7009 Replacements and Upgrades Pha | 535950 Royalty, Easement, Appraisal | 10000
Substation Operations | C0061883 | 129H - Kearney Lake Substation Rebu | 535950 Royalty, Easement, Appraisal | 17873.8
Substation Operations | C0061883 | 129H - Kearney Lake Substation Rebu | 535650 Vehicle Allocated Costs | 32825.81
Substation Operations | C0061883 | 129H - Kearney Lake Substation Rebu | 530950 Travel Expense | 1042.32
Transmission Line | C0065294 | L5561 Reroute - CBU Expansion | 605050 AFUDC Interest | 5113.31
Transmission Line | C0067111 | L5023 Rebuild | 535100 Other Goods and Services | 100000
Substation Operations | C0068961 | 2025 PCB Substation Sampling and Re | 530050 Regular Labour | 805000
Substation Operations | C0068961 | 2025 PCB Substation Sampling and Re | 531550 Contracts | 1006000
Substation Operations | C0068966 | 2025 Merlin Gerin Breaker Replaceme | 531400 Materials | 357745
Substation Operations | C0068966 | 2025 Merlin Gerin Breaker Replaceme | 535650 Vehicle Allocated Costs | 24944.1
Transmission Line | C0069227 | L6516 Replacements and Upgrades Ph3 | 535650 Vehicle Allocated Costs | 63960.97
Transmission Line | C0069238 | 2025/2026 Steel Tower Refurbishment | 535100 Other Goods and Services | 190156
Transmission Line | C0069238 | 2025/2026 Steel Tower Refurbishment | 530950 Travel Expense | 3000
Substation Operations | C0069534 | IR 669 NU - Higgins Mountain Wind | 531400 Materials | 927216.57
Substation Operations | C0069535 | IR 669 TPIF - Higgins Mountain Wind | 530200 Overtime Labour | 1375.34
Substation Operations | C0070327 | IR 673 NU - Benjamins Mill Wind | 530950 Travel Expense | 4965
Substation Operations | C0070367 | IR 618 NU - Goose Harbour Lake Wind | 531400 Materials | 468000
Substation Operations | C0071888 | 92H-T61 Transformer Replacement | 535700 Admin Overheads | 39386.73
Substation Operations | C0071889 | 77V-T1 Transformer Replacement | 530950 Travel Expense | 425.92
Substation Operations | C0073975 | IR 671 NU - Bear Lake Wind | 535650 Vehicle Allocated Costs | 254100.29
Substation Operations | C0073975 | IR 671 NU - Bear Lake Wind | 535700 Admin Overheads | 288419.64
Transmission Line | 23115-T001-820 | PROVINCIAL TRANSMISSION LINE REPLAC | 531550 Contracts | 2050000
Transmission Line | 23115-T001-820 | PROVINCIAL TRANSMISSION LINE REPLAC | 533410 Overtime Meals | 4561.07
Transmission Line | 23115-T001-820 | PROVINCIAL TRANSMISSION LINE REPLAC | 530200 Overtime Labour | 234000
Transmission Line | 23118-T011-820 | PROVINCIAL - PLANNED TRANS LINE REP | 530320 Term Labour-Overtime | 2028
Substation Operations | 23120-T003-820 | PROVINCIAL-TRANS SUBSTATION PRIMARY | 533410 Overtime Meals | 10371.19
Substation Operations | 23121-T004-820 | PROVINCIAL- SUBSTATION ADDITIONS & | 535100 Other Goods and Services | 9976.99
Vegetation Management | 43827-T010-840 | Transmission ROW Widening Routine | 531550 Contracts | 2474400
Capital Projects Group - Transmission | 51098-T952 | L-6014 Shannon Park Trans Towers | 535700 Admin Overheads | 198474.32
Substation Operations | C0011261 | 101W Port Mersey Expansion | 531400 Materials | 658
Substation Operations | C0011358 | New Bridgewater Substation | 532500 Consulting | 20000
Substation Operations | C0022247 | 1N-Onslow 138 kV Add Second 42 MVA | 530950 Travel Expense | 1000.01
Substation Operations | C0022743 | Retire 9H-Yale Street Substation | 535650 Vehicle Allocated Costs | 10770.5
Transmission Line | C0023802 | L6515 Replacements and Upgrades | 535700 Admin Overheads | 36688.5
Transmission Line | C0023802 | L6515 Replacements and Upgrades | 535705 Contractor Admin Overhead | 19523.7
Substation Operations | C0031046 | 77V New Transformer | 530050 Regular Labour | 21596.16
Transmission Line | C0031122 | L6539-2021 Replacements and Upgrade | 530050 Regular Labour | 8500.99
Substation Operations | C0031298 | 88S-T72 New Radiators | 535100 Other Goods and Services | 1
Transmission Line | C0041788 | L6516 Replacements and Upgrades Ph2 | 535650 Vehicle Allocated Costs | 14513.37
Transmission Line | C0041791 | L6551 Replacements and Upgrades | 535100 Other Goods and Services | 450000
Substation Operations | C0041830 | Spare Power Prod Unit Transformer | 535700 Admin Overheads | 17743.43
Transmission Line | C0043010 | 2022 2023 Wood Pole Retreatment Prg | 535700 Admin Overheads | 566.83
Transmission Line | C0043010 | 2022 2023 Wood Pole Retreatment Prg | 535705 Contractor Admin Overhead | 5784.8
Transmission Line | C0043010 | 2022 2023 Wood Pole Retreatment Prg | 535650 Vehicle Allocated Costs | 499.38
Large Industrial Reliability | C0044110 | 138kv Line Tap to 92V Substation | 531400 Materials | 520000
ECEI | C0045132 | ECEI - Energy Storage | 533750 Rent | 239220.63
Substation Operations | C0050834 | Spare EHV Breaker Replacements | 531400 Materials | 366535.02
Substation Operations | C0050842 | 2024 Bulk Oil Breaker Replacement | 535100 Other Goods and Services | 216770
Transmission Line | C0052299 | 2023 2024 Steel Tower Life Extensio | 533400 Meals and Entertainment | 150
Transmission Line | C0052299 | 2023 2024 Steel Tower Life Extensio | 530050 Regular Labour | 16001
Transmission Line | C0052654 | L5541 Water Crossing Upgrades | 535650 Vehicle Allocated Costs | 3609.08
Substation Operations | C0052994 | WRC 85S-GT1 85S-GT2 Transform Repl | 535100 Other Goods and Services | 356045.72
Substation Operations | C0053158 | 77V-T52 Transformer Replacement | 535700 Admin Overheads | -0.06
Substation Operations | C0053214 | 76W-T1 Transformer Replacement | 535650 Vehicle Allocated Costs | 16671.84
Substation Operations | C0053234 | 96H-T1 Transformer Replacement | 532500 Consulting | 23213.8
Large Industrial Reliability | C0053316 | Michelin Waterville Dynamic Voltage | 532500 Consulting | 232000
Substation Operations | C0055539 | 10H-T1 Transformer Replacement | 531100 iExpenses-Car rental | 591.99
Substation Operations | C0055796 | 2023 EHV Breaker Replacements | 531550 Contracts | 801724.91
Substation Operations | C0055796 | 2023 EHV Breaker Replacements | 530050 Regular Labour | 249101.81
Substation Operations | C0057682 | Spare Transformer Replacement | 531550 Contracts | 20000.01
AMO - Customer Operations | C0058703 | AMO 69kV Lightning Arrester Assessm | 605050 AFUDC Interest | 1063.6
Substation Operations | C0061023 | 2024 EHV Breaker Replacements | 535700 Admin Overheads | 130096.02
Transmission Line | C0061529 | L6001 Replacements and Upgrades | 535700 Admin Overheads | 0.02
Transmission Line | C0061529 | L6001 Replacements and Upgrades | 530050 Regular Labour | 0.04
Transmission Line | C0061543 | L5048 Replacements and Upgrades | 535700 Admin Overheads | -0.01
Transmission Line | C0061544 | L6536 Replacements and Upgrades | 531400 Materials | 175000
Transmission Line | C0061546 | L6514 Replacements and Upgrades | 531550 Contracts | 490073.76
Transmission Line | C0061546 | L6514 Replacements and Upgrades | 535650 Vehicle Allocated Costs | 16504.05
Transmission Line | C0061547 | L7022 Replacements and Upgrades | 531400 Materials | 532378
Transmission Line | C0061551 | L7009 Replacements and Upgrades Pha | 530050 Regular Labour | 119488.68
Transmission Line | C0061743 | L6038 Realignment | 530050 Regular Labour | 24502.32
Substation Operations | C0064903 | IR 664 - 99W Bridgewater BESS TPIF | 535650 Vehicle Allocated Costs | 4365.54
Substation Operations | C0065024 | IR 662 - 132H Spider Lake BESS TPIF | 535700 Admin Overheads | 4866.1
Transmission Line | C0067111 | L5023 Rebuild | 535700 Admin Overheads | 3115
Substation Operations | C0068868 | Fall River Substation Addition | 530950 Travel Expense | 250
Substation Operations | C0068868 | Fall River Substation Addition | 535650 Vehicle Allocated Costs | 10476.98
Substation Operations | C0068961 | 2025 PCB Substation Sampling and Re | 535650 Vehicle Allocated Costs | 504617.12
Substation Operations | C0068969 | 2026 Pennsylvania Breaker Replaceme | 530050 Regular Labour | 95827
Substation Operations | C0069392 | 12V-T1 Transformer Replacement | 530050 Regular Labour | 51668.98
Substation Operations | C0069394 | 16N-T1 Transformer Replacement | 605050 AFUDC Interest | 64321.83
Substation Operations | C0069446 | IR 668 - Weavers Mountain Wind | 535100 Other Goods and Services | 897113.5
Substation Operations | C0069534 | IR 669 NU - Higgins Mountain Wind | 530200 Overtime Labour | 19252.02
Substation Operations | C0070086 | 10H-T2 Transformer Replacement | 605050 AFUDC Interest | 16676.34
Substation Operations | C0070086 | 10H-T2 Transformer Replacement | 535705 Contractor Admin Overhead | 10846.56
Substation Operations | C0070327 | IR 673 NU - Benjamins Mill Wind | 535650 Vehicle Allocated Costs | 20746.25
Substation Operations | C0070367 | IR 618 NU - Goose Harbour Lake Wind | 535100 Other Goods and Services | 171071.6
Substation Operations | C0070367 | IR 618 NU - Goose Harbour Lake Wind | 535700 Admin Overheads | 100225.94
Substation Operations | C0070386 | IR 618 TPIF - Goose Harbour Lake Wi | 530200 Overtime Labour | 14345.16
Substation Operations | C0073308 | IR 677 TPIF - Wedgeport Wind | 532500 Consulting | 30608.7
Transmission Line | C0073388 | L8002 Replacements and Upgrades U&U | 535705 Contractor Admin Overhead | 17354.4
Substation Operations | C0073975 | IR 671 NU - Bear Lake Wind | 532500 Consulting | 100000
Substation Operations | 14841-T016-630 | PROTECTION MODIFICATIONS AND REPLAC | 531550 Contracts | 14770.89
Transmission Line | 23115-T001-820 | PROVINCIAL TRANSMISSION LINE REPLAC | 534750 Personal Equipment | 1078.51
Transmission Line | 23115-T001-820 | PROVINCIAL TRANSMISSION LINE REPLAC | 533400 Meals and Entertainment | 18903.71
Transmission Line | 23118-T011-820 | PROVINCIAL - PLANNED TRANS LINE REP | 455300 Other Income-Salvage | -19800
Substation Operations | 23120-T003-820 | PROVINCIAL-TRANS SUBSTATION PRIMARY | 532500 Consulting | 16798.88
Substation Operations | 23120-T003-820 | PROVINCIAL-TRANS SUBSTATION PRIMARY | 533400 Meals and Entertainment | 2837.96
Substation Operations | 23120-T003-820 | PROVINCIAL-TRANS SUBSTATION PRIMARY | 534500 Internal Services Received | 9400.36
Substation Operations | 23121-T004-820 | PROVINCIAL- SUBSTATION ADDITIONS & | 535650 Vehicle Allocated Costs | 92720.14
Capital Projects Group - Transmission | 51098-T952 | L-6014 Shannon Park Trans Towers | 531400 Materials | 3159000
Substation Operations | C0011261 | 101W Port Mersey Expansion | 535700 Admin Overheads | 20989.49
Substation Operations | C0021140 | 98N-Stellarton Substation | 535650 Vehicle Allocated Costs | 17960.18
Substation Operations | C0021140 | 98N-Stellarton Substation | 605050 AFUDC Interest | 364.46
Substation Operations | C0022247 | 1N-Onslow 138 kV Add Second 42 MVA | 535700 Admin Overheads | 21471.27
AMO - Customer Operations | C0028684 | AMO AM for Protection & Controls | 535100 Other Goods and Services | 1
Substation Operations | C0031046 | 77V New Transformer | 535705 Contractor Admin Overhead | 3298.2
Substation Operations | C0031048 | 91H-T11 Transformer Replacement | 530050 Regular Labour | 158419.41
Substation Operations | C0031048 | 91H-T11 Transformer Replacement | 531550 Contracts | 326203.93
Substation Operations | C0031048 | 91H-T11 Transformer Replacement | 535700 Admin Overheads | 92042.46
Substation Operations | C0031286 | Spare Padmounted Substation | 531550 Contracts | 12839.97
Substation Operations | C0031286 | Spare Padmounted Substation | 535100 Other Goods and Services | 136223
Substation Operations | C0032382 | Susie Lake Substation Addition | 535705 Contractor Admin Overhead | 144620
Substation Operations | C0032382 | Susie Lake Substation Addition | 535700 Admin Overheads | 20385.93
Transmission Line | C0041788 | L6516 Replacements and Upgrades Ph2 | 530050 Regular Labour | 29091.9
Transmission Line | C0041788 | L6516 Replacements and Upgrades Ph2 | 531400 Materials | 188551.63
Transmission Line | C0041788 | L6516 Replacements and Upgrades Ph2 | 535700 Admin Overheads | 16473.56
Transmission Line | C0041807 | L5534 Replacements and Upgrades | 535705 Contractor Admin Overhead | 29719.41
Transmission Line | C0041812 | L6040 Replacements and Upgrades | 535700 Admin Overheads | 4230.52
Substation Operations | C0043571 | 2022-2023 Transmission Switch & B | 535705 Contractor Admin Overhead | 1145.4
ECEI | C0044391 | ECEI - Transmission | 530050 Regular Labour | 5515382.98
ECEI | C0044391 | ECEI - Transmission | 533750 Rent | 103956
ECEI | C0045132 | ECEI - Energy Storage | 532700 Fleet Fuel | 36895.23
ECEI | C0045132 | ECEI - Energy Storage | 534750 Personal Equipment | 32422.05
Transmission Line | C0050835 | 2023/2024 Steel Tower Refurbishment | 530950 Travel Expense | 800
Transmission Line | C0050835 | 2023/2024 Steel Tower Refurbishment | 533400 Meals and Entertainment | 800
Transmission Line | C0050835 | 2023/2024 Steel Tower Refurbishment | 535700 Admin Overheads | 10901.12
Transmission Line | C0050835 | 2023/2024 Steel Tower Refurbishment | 535705 Contractor Admin Overhead | 80264.1
Substation Operations | C0050842 | 2024 Bulk Oil Breaker Replacement | 535705 Contractor Admin Overhead | 12411.36
Substation Operations | C0050852 | 10V-T1 Transformer Replacement | 530050 Regular Labour | 112759
Substation Operations | C0050852 | 10V-T1 Transformer Replacement | 530950 Travel Expense | 4693.53
Transmission Line | C0052654 | L5541 Water Crossing Upgrades | 530050 Regular Labour | 7234.35
Transmission Line | C0052654 | L5541 Water Crossing Upgrades | 535700 Admin Overheads | 4096.52
Substation Operations | C0053195 | 47C-T1 and T2 PHP Transformer Repl | 532500 Consulting | 16718.6
Substation Operations | C0053195 | 47C-T1 and T2 PHP Transformer Repl | 535700 Admin Overheads | 83907.52
Substation Operations | C0055557 | 76V-T1 Transformer Replacement | 605050 AFUDC Interest | 37273.16
Transmission Line | C0055696 | L5031 Replacement & Upgrade R.C Tap | 535700 Admin Overheads | 1699.35
Substation Operations | C0055796 | 2023 EHV Breaker Replacements | 605050 AFUDC Interest | 18151.01
Substation Operations | C0061023 | 2024 EHV Breaker Replacements | 531400 Materials | 1868390
Substation Operations | C0061046 | 2024 Merlin Gerin Breaker Replaceme | 535100 Other Goods and Services | 82748.7
Substation Operations | C0061046 | 2024 Merlin Gerin Breaker Replaceme | 530050 Regular Labour | 28672
Transmission Line | C0061547 | L7022 Replacements and Upgrades | 535650 Vehicle Allocated Costs | 46895.22
Transmission Line | C0061550 | L5031 - Hubbards to East Chester | 535700 Admin Overheads | 55133.1
Transmission Line | C0061550 | L5031 - Hubbards to East Chester | 530050 Regular Labour | 97363.69
Transmission Line | C0061743 | L6038 Realignment | 531400 Materials | 226666.67
Transmission Line | C0061743 | L6038 Realignment | 530950 Travel Expense | 1000
Substation Operations | C0061883 | 129H - Kearney Lake Substation Rebu | 533400 Meals and Entertainment | 252.5
Substation Operations | C0062123 | 143H-Mount Uniacke Substation | 532500 Consulting | 30000.01
Substation Operations | C0062123 | 143H-Mount Uniacke Substation | 530950 Travel Expense | 1418.01
Substation Operations | C0064883 | IR 697 - 105V White Rock BESS TPIF | 605050 AFUDC Interest | 24550.3
Substation Operations | C0064883 | IR 697 - 105V White Rock BESS TPIF | 532500 Consulting | 11538.8
Substation Operations | C0064903 | IR 664 - 99W Bridgewater BESS TPIF | 531400 Materials | 144504.45
Transmission Line | C0067110 | L5532 Replacements and Upgrades | 530050 Regular Labour | 1
Substation Operations | C0068966 | 2025 Merlin Gerin Breaker Replaceme | 605050 AFUDC Interest | 306.27
Substation Operations | C0068966 | 2025 Merlin Gerin Breaker Replaceme | 535700 Admin Overheads | 28312.99
Transmission Line | C0069232 | L6021 Replacements and Upgrades Ph1 | 531400 Materials | 443000
Substation Operations | C0069234 | L5532 Reliability Improvements Phas | 532500 Consulting | 40000
Substation Operations | C0069392 | 12V-T1 Transformer Replacement | 533400 Meals and Entertainment | 208.98
Substation Operations | C0069394 | 16N-T1 Transformer Replacement | 535650 Vehicle Allocated Costs | 25776.57
Substation Operations | C0069446 | IR 668 - Weavers Mountain Wind | 532500 Consulting | 108428.58
Substation Operations | C0069446 | IR 668 - Weavers Mountain Wind | 533400 Meals and Entertainment | 13357.04
Substation Operations | C0069534 | IR 669 NU - Higgins Mountain Wind | 535705 Contractor Admin Overhead | 105885.83
Substation Operations | C0070086 | 10H-T2 Transformer Replacement | 530050 Regular Labour | 88712.73
Substation Operations | C0070327 | IR 673 NU - Benjamins Mill Wind | 530200 Overtime Labour | 2578
Substation Operations | C0070328 | IR 673 TPIF - Benjamins Mill Wind | 535100 Other Goods and Services | 101627.4
Substation Operations | C0070367 | IR 618 NU - Goose Harbour Lake Wind | 535705 Contractor Admin Overhead | 100586.88
Substation Operations | C0070386 | IR 618 TPIF - Goose Harbour Lake Wi | 536750 Capital Contributions | -1055432.86
Substation Operations | C0070386 | IR 618 TPIF - Goose Harbour Lake Wi | 530050 Regular Labour | 137177.2
Substation Operations | C0070586 | 22N-603 and 604 Switch Repl L6536 | 535705 Contractor Admin Overhead | 8346.17
Transmission Line | C0071771 | 2024 Non-NERC Trans LIDAR Surveys | 535705 Contractor Admin Overhead | 26271.9
Substation Operations | C0071888 | 92H-T61 Transformer Replacement | 535705 Contractor Admin Overhead | 14461.98
Substation Operations | C0073309 | IR 677 NU - Wedgeport Wind | 530200 Overtime Labour | 79517
Substation Operations | C0073309 | IR 677 NU - Wedgeport Wind | 535705 Contractor Admin Overhead | 1022843.78
Substation Operations | 14973-T018-820 | PRIMARY EQUIPMENT SPARES | 530200 Overtime Labour | 723.34
Substation Operations | 14841-T016-630 | PROTECTION MODIFICATIONS AND REPLAC | 530200 Overtime Labour | 21671.51
Transmission Line | 23115-T001-820 | PROVINCIAL TRANSMISSION LINE REPLAC | 535700 Admin Overheads | 128761.23
Transmission Line | 23115-T001-820 | PROVINCIAL TRANSMISSION LINE REPLAC | 530300 Term Labour | 2972.16
Transmission Line | 23118-T011-820 | PROVINCIAL - PLANNED TRANS LINE REP | 530950 Travel Expense | 19020
Substation Operations | 23121-T004-820 | PROVINCIAL- SUBSTATION ADDITIONS & | 531100 iExpenses-Car rental | 75.76
Substation Operations | C0022247 | 1N-Onslow 138 kV Add Second 42 MVA | 532500 Consulting | 49999.98
Substation Operations | C0022743 | Retire 9H-Yale Street Substation | 535705 Contractor Admin Overhead | 16625.1
Transmission Line | C0023802 | L6515 Replacements and Upgrades | 535650 Vehicle Allocated Costs | 32323
Substation Operations | C0031048 | 91H-T11 Transformer Replacement | 535705 Contractor Admin Overhead | 47175.6
Transmission Line | C0041804 | 2022 Line Retirement Program | 530050 Regular Labour | 14024.36
Transmission Line | C0041804 | 2022 Line Retirement Program | 535705 Contractor Admin Overhead | 129434.9
Transmission Line | C0041812 | L6040 Replacements and Upgrades | 531550 Contracts | 450000
Transmission Line | C0041812 | L6040 Replacements and Upgrades | 535650 Vehicle Allocated Costs | 3727.13
Substation Operations | C0041822 | WRC Spare Cable Repl & Storage Syst | 535100 Other Goods and Services | 36166.25
Substation Operations | C0041840 | Legacy Oil Containment Refurbish | 531550 Contracts | 0.01
Transmission Line | C0044172 | L7005 Canso Crossing Vibration Miti | 535705 Contractor Admin Overhead | 50617
Transmission Line | C0049652 | 2022 Transmission Inspection Progra | 535100 Other Goods and Services | 1
Substation Operations | C0050852 | 10V-T1 Transformer Replacement | 535100 Other Goods and Services | 171100.68
Substation Operations | C0052994 | WRC 85S-GT1 85S-GT2 Transform Repl | 532500 Consulting | 12317.1
Substation Operations | C0053158 | 77V-T52 Transformer Replacement | 535650 Vehicle Allocated Costs | -0.06
Substation Operations | C0053234 | 96H-T1 Transformer Replacement | 535650 Vehicle Allocated Costs | 74405.59
Transmission Line | C0053295 | L5004 Kearney Lake Structure Replac | 531550 Contracts | 1422200
Substation Operations | C0055539 | 10H-T1 Transformer Replacement | 533400 Meals and Entertainment | 458.37
Substation Operations | C0055539 | 10H-T1 Transformer Replacement | 535700 Admin Overheads | 59572.11
Substation Operations | C0055539 | 10H-T1 Transformer Replacement | 605050 AFUDC Interest | 25331.91
Substation Operations | C0056240 | 2024-2025 Transmission Switch & Bre | 535650 Vehicle Allocated Costs | 45256.22
Substation Operations | C0057682 | Spare Transformer Replacement | 531400 Materials | 1892028
Corporate Initiatives | C0060866 | Everwind 230kV Transmission Line | 530050 Regular Labour | 215000
Substation Operations | C0061023 | 2024 EHV Breaker Replacements | 535705 Contractor Admin Overhead | 117985.36
Transmission Line | C0061403 | 2024 2025 Sacrificial Anode Install | 535705 Contractor Admin Overhead | 55967.94
Transmission Line | C0061403 | 2024 2025 Sacrificial Anode Install | 530950 Travel Expense | 2000
Transmission Line | C0061529 | L6001 Replacements and Upgrades | 535650 Vehicle Allocated Costs | 0.02
Transmission Line | C0061544 | L6536 Replacements and Upgrades | 531550 Contracts | 160000
Transmission Line | C0061552 | L6043 Replacements and Upgrades | 535700 Admin Overheads | 29889.81
Transmission Line | C0061743 | L6038 Realignment | 533400 Meals and Entertainment | 2000
Substation Operations | C0064883 | IR 697 - 105V White Rock BESS TPIF | 535650 Vehicle Allocated Costs | 5981.71
Substation Operations | C0065024 | IR 662 - 132H Spider Lake BESS TPIF | 530950 Travel Expense | 421.07
Transmission Line | C0065294 | L5561 Reroute - CBU Expansion | 530050 Regular Labour | 47839.84
Transmission Line | C0065294 | L5561 Reroute - CBU Expansion | 531550 Contracts | 15035.44
Transmission Line | C0067111 | L5023 Rebuild | 530050 Regular Labour | 5501
Substation Operations | C0068961 | 2025 PCB Substation Sampling and Re | 531400 Materials | 2430000
Substation Operations | C0068969 | 2026 Pennsylvania Breaker Replaceme | 605050 AFUDC Interest | 13260.83
Transmission Line | C0069238 | 2025/2026 Steel Tower Refurbishment | 531550 Contracts | 1497330
Transmission Line | C0069238 | 2025/2026 Steel Tower Refurbishment | 535705 Contractor Admin Overhead | 216543.84
Substation Operations | C0069392 | 12V-T1 Transformer Replacement | 535700 Admin Overheads | 29258.14
Substation Operations | C0069446 | IR 668 - Weavers Mountain Wind | 533410 Overtime Meals | 1178.58
Substation Operations | C0069446 | IR 668 - Weavers Mountain Wind | 535700 Admin Overheads | 363875.54
Substation Operations | C0069446 | IR 668 - Weavers Mountain Wind | 536750 Capital Contributions | -9075078.77
Substation Operations | C0069534 | IR 669 NU - Higgins Mountain Wind | 535650 Vehicle Allocated Costs | 95795.35
Substation Operations | C0069535 | IR 669 TPIF - Higgins Mountain Wind | 530950 Travel Expense | 1670.04
Transmission Line | C0070048 | L5027B Replacements and Upgrades Ph | 535705 Contractor Admin Overhead | 239070.47
Substation Operations | C0070086 | 10H-T2 Transformer Replacement | 535650 Vehicle Allocated Costs | 44257.05
Substation Operations | C0070328 | IR 673 TPIF - Benjamins Mill Wind | 531400 Materials | 203500
Substation Operations | C0070328 | IR 673 TPIF - Benjamins Mill Wind | 531550 Contracts | 224000
Substation Operations | C0070328 | IR 673 TPIF - Benjamins Mill Wind | 533400 Meals and Entertainment | 250
Substation Operations | C0070328 | IR 673 TPIF - Benjamins Mill Wind | 535650 Vehicle Allocated Costs | 36083
Substation Operations | C0070367 | IR 618 NU - Goose Harbour Lake Wind | 532500 Consulting | 85909.08
Substation Operations | C0070386 | IR 618 TPIF - Goose Harbour Lake Wi | 533400 Meals and Entertainment | 1636.36
Substation Operations | C0070386 | IR 618 TPIF - Goose Harbour Lake Wi | 535100 Other Goods and Services | 94515.4
Substation Operations | C0070386 | IR 618 TPIF - Goose Harbour Lake Wi | 531550 Contracts | 192272.76
Substation Operations | C0070386 | IR 618 TPIF - Goose Harbour Lake Wi | 531400 Materials | 406636.4
Transmission Line | C0071771 | 2024 Non-NERC Trans LIDAR Surveys | 535700 Admin Overheads | 7021.6
Transmission Line | C0071771 | 2024 Non-NERC Trans LIDAR Surveys | 531550 Contracts | 181661.61
Substation Operations | C0071888 | 92H-T61 Transformer Replacement | 531550 Contracts | 100000
Substation Operations | C0071888 | 92H-T61 Transformer Replacement | 535650 Vehicle Allocated Costs | 34700.03
Substation Operations | C0072089 | 2P Mobile Transformer Replacement | 535650 Vehicle Allocated Costs | 23040.51
Substation Operations | C0072308 | Dartmouth Substation Addition | 531550 Contracts | 23998.8
Substation Operations | C0073308 | IR 677 TPIF - Wedgeport Wind | 535650 Vehicle Allocated Costs | 66952.13

## Sheet2 (hidden)
Cc Cpc | Fp Number | Fp Description | Est Charge Type | ACE 2024 | ACE 2023 | ACE 2022 | ACE 2021
Transmission Line | C0033645 | 2021-2022 Steel Tower Refurbishment | 535100 Other Goods and Services | 249.66 | 249.66 | 0 | 152560
Transmission Line | C0041989 | 2022 2023 Sacrificial Anode Inst Pr | 535100 Other Goods and Services | 157.79 | 0 | 235109.99 | 0
Transmission Line | C0061529 | L6001 Replacements and Upgrades | 535100 Other Goods and Services | 53865.65 | 0 | 0 | 0
Capital Projects Group - Transmission | 34042-T594 | Dalhousie Mountain Wind Farm | 535100 Other Goods and Services | 123703.52 | 123703.52 | 0 | 0
Substation Operations | C0010956 | 78W-Martins Brook Substation Reloc | 535100 Other Goods and Services | 342.47 | 29.03 | 0 | 0
Substation Operations | C0031050 | New Spare Large Autotransformer | 535100 Other Goods and Services | 412.95 | 0 | 203954 | 203954
Transmission Line | C0031085 | L6516 Line Replacement and Upgrades | 535100 Other Goods and Services | 0 | 0 | 216832 | 216832
Substation Operations | C0053234 | 96H-T1 Transformer Replacement | 535100 Other Goods and Services | 220757.64 | 237744 | 0 | 0
Substation Operations | 14973-T018-820 | PRIMARY EQUIPMENT SPARES | 535100 Other Goods and Services | 465.65 | 3.79 | 3.79 | 3.79
Capital Projects Group - Transmission | 39628-T694 | Digby Wind Project Interconnect | 535100 Other Goods and Services | 29136.32 | 29136.32 | 0 | 0
Substation Operations | C0031303 | 82S-503 82S-504 Replace Structure | 535100 Other Goods and Services | 0 | 0 | 0 | 15416
Transmission Line | C0041807 | L5534 Replacements and Upgrades | 535100 Other Goods and Services | 161841.69 | 161841.69 | 0 | 0
Substation Operations | C0059046 | 101S and 79N Reactor Replacements | 535100 Other Goods and Services | 123674 | 0 | 0 | 0
Transmission Line | C0056721 | 2023 Transmission Inspection Progra | 535100 Other Goods and Services | 4415.96 | 0 | 0 | 0
Transmission Line | C0052654 | L5541 Water Crossing Upgrades | 535100 Other Goods and Services | 0 | 124648 | 0 | 0
Transmission Line | C0041794 | L5031 Replacements and Upgrades Ph2 | 535100 Other Goods and Services | 0 | 0 | 328866 | 0
Substation Operations | 52261 | 83V-503 & 83V-504 - Bring Switches | 535100 Other Goods and Services | 0 | 55 | 55 | 55
Substation Operations | C0011261 | 101W Port Mersey Expansion | 535100 Other Goods and Services | 2602.7 | 1187.52 | 0 | 0
Substation Operations | C0036846 | 1C-GT2 Transformer Failure Replacme | 535100 Other Goods and Services | 0 | 20165.99 | 0 | 0
Transmission Line | C0047035 | Feb 4th, 2022 Storm - Transmission | 535100 Other Goods and Services | 14.55 | 14.55 | 0 | 0
Transmission Line | C0041793 | L7002 Replacements and Upgrades Ph2 | 535100 Other Goods and Services | 0 | 0 | 417551 | 0
Transmission Line | C0041800 | L5537 Replacements and Upgrades | 535100 Other Goods and Services | 0 | 0 | 144294.25 | 0
Substation Operations | 51974-T971 | Remote Substation Video/Thermal Mon | 535100 Other Goods and Services | 225.35 | 225.35 | 0 | 0
Transmission Line | C0041788 | L6516 Replacements and Upgrades Ph2 | 535100 Other Goods and Services | 112500 | 350981.24 | 0 | 0
Substation Operations | 44985-T807 | Replace 230kV Kearney Disconnect Sw | 535100 Other Goods and Services | 8.61 | 8.61 | 0 | 0
Vegetation Management | C0041893 | 2022/2023 Trans ROW Widening 69kV | 535100 Other Goods and Services | 232.96 | 0 | 0 | 0
Substation Operations | C0041831 | Lingan Spare Potential Transformers | 535100 Other Goods and Services | 0 | 0 | 10720 | 0
Substation Operations | C0055557 | 76V-T1 Transformer Replacement | 535100 Other Goods and Services | 275223 | 204944 | 0 | 0
Transmission Line | C0021107 | L8001 Replacements and Upgrades PH1 | 535100 Other Goods and Services | 0 | 0 | 0 | 174528.4
Substation Operations | 14841-T016-630 | PROTECTION MODIFICATIONS AND REPLAC | 535100 Other Goods and Services | 12925.07 | 12865.84 | 12172.96 | 12172.96
Transmission Line | 45053-T818 | 69Kv Structure Replacements West | 535100 Other Goods and Services | 278.14 | 278.14 | 0 | 0
Substation Operations | 52328 | 56N-T1 Transformer Upgrades | 535100 Other Goods and Services | 334.7 | 334.7 | 0 | 0
Transmission Line | 52303 | L7019 2020 Replacements & Upgrades | 535100 Other Goods and Services | 0 | 0 | 0 | 107112
Substation Operations | C0059483 | Rebuild L5046 Tap | 535100 Other Goods and Services | 68090 | 0 | 0 | 0
Transmission Line | C0008461 | 2019 Transmission Inspection Prog | 535100 Other Goods and Services | 40 | 40 | 0 | 0
Large Industrial Reliability | C0044110 | 138kv Line Tap to 92V Substation | 535100 Other Goods and Services | 1400000 | 0 | 0 | 0
Transmission Line | C0046111 | Jan 7, 2022 Storm - Transmission | 535100 Other Goods and Services | 15.57 | 15.57 | 0 | 0
Substation Operations | C0044431 | 2022 - 2023 Capacitor Bank Breaker | 535100 Other Goods and Services | 179.82 | 0 | 20552 | 0
Transmission Line | C0053295 | L5004 Kearney Lake Structure Replac | 535100 Other Goods and Services | 207192 | 207192 | 0 | 0
Substation Operations | C0031042 | 5P-MS Rewind | 535100 Other Goods and Services | 0 | 0 | 0 | 64908
Transmission Line | C0021106 | L7005 Replacements and Upgrades PH1 | 535100 Other Goods and Services | 0 | 0 | 0 | 277387
Substation Operations | C0035651 | 2021 Battery Bank & Charger Replace | 535100 Other Goods and Services | 243.07 | 243.07 | 0 | 0
Substation Operations | C0041833 | 2022 2023 Bulk Oil Breaker Replace | 535100 Other Goods and Services | 794.66 | 29845 | 29845 | 0
Substation Operations | C0021323 | 50N-Trenton Replace 50N-T13 | 535100 Other Goods and Services | 319.68 | 228.72 | 0 | 0
Transmission Line | C0061387 | 2024 2025 Wood Pole Retreatment Pro | 535100 Other Goods and Services | 93211 | 0 | 0 | 0
Substation Operations | 23120-T003-820 | PROVINCIAL-TRANS SUBSTATION PRIMARY | 535100 Other Goods and Services | 338832.8 | 203720.62 | 175654.59 | 157618.68
Substation Operations | CONV-T016-820 | T016-PROTECTION MOD.CC820 | 535100 Other Goods and Services | 413.71 | 178.29 | 0 | 0
Transmission Line | C0010948 | T-2019/2020 Sacrificial Anode Inst | 535100 Other Goods and Services | 44.88 | 44.88 | 0 | 44.88
Transmission Line | C0021104 | L5550 Replacements and Upgrades Ph1 | 535100 Other Goods and Services | 0 | 0 | 0 | 171680
Substation Operations | C0011358 | New Bridgewater Substation | 535100 Other Goods and Services | 111212 | 111212 | 0 | 0
Substation Operations | C0021142 | 19W-T51 Transformer Replacement | 535100 Other Goods and Services | 36624.91 | 29494.91 | 0 | 0
Substation Operations | C0056240 | 2024-2025 Transmission Switch & Bre | 535100 Other Goods and Services | 253885.1 | 0 | 0 | 0
Substation Operations | C0050838 | 2023 Subst Primary Equip Spares | 535100 Other Goods and Services | 200000 | 177943 | 0 | 0
Transmission Line | 23118-T011-820 | PROVINCIAL - PLANNED TRANS LINE REP | 535100 Other Goods and Services | 128265.96 | 124405.99 | 121696.5 | 121603.61
Transmission Line | C0033644 | 2021-2022 Steel Tower Life Extensio | 535100 Other Goods and Services | 0 | 0 | 48467 | 180086
Transmission Line | C0061551 | L7009 Replacements and Upgrades Pha | 535100 Other Goods and Services | 364842.04 | 0 | 0 | 0
Substation Operations | C0010952 | 2019/20 Substation PCB Equip Replac | 535100 Other Goods and Services | 1168.59 | 1168.59 | 0 | 1168.59
Transmission Line | 47949-T876 | L5028 Replacements and Upgrades | 535100 Other Goods and Services | 6887.83 | 6887.83 | 0 | 0
Transmission Line | C0061547 | L7022 Replacements and Upgrades | 535100 Other Goods and Services | 255792.04 | 0 | 0 | 0
Substation Operations | 49818-T923 | 2017/2018 Tx Switch & Breaker Rplmt | 535100 Other Goods and Services | 67.83 | 67.83 | 0 | 0
Transmission Line | 51398 | 2018/2019 Steel Tower Refurb | 535100 Other Goods and Services | 1786.25 | 1786.25 | 0 | 0
Substation Operations | C0031051 | Pennsylvania Breaker Replacements | 535100 Other Goods and Services | 59.36 | 0 | 0 | 0
Substation Operations | C0031262 | 2021-22 Transmission Switch & Break | 535100 Other Goods and Services | 1680.61 | 1680.61 | 1656.85 | 111305
Substation Operations | C0041837 | 2022 2023 Substation PCB Equip Remo | 535100 Other Goods and Services | 18640.75 | 410.44 | 263010 | 0
Substation Operations | C0021132 | 24C-T54G Grounding Bank Replacement | 535100 Other Goods and Services | 0 | 0 | 61262 | 0
Vegetation Management | C0010042 | 2019 Transmission ROW Widening 69kV | 535100 Other Goods and Services | 507.08 | 507.08 | 0 | 0
Transmission Line | C0031053 | L5506 Line Replacements and Upgrade | 535100 Other Goods and Services | 283.44 | 0 | 0 | 58101
Substation Operations | C0048114 | 88S-301 Switchgear Replacement | 535100 Other Goods and Services | 44.57 | 15000 | 0 | 0
Substation Operations | C0059403 | 62H Low Voltage Switchgear Replacem | 535100 Other Goods and Services | 148064.55 | 0 | 0 | 0
Substation Operations | C0022743 | Retire 9H-Yale Street Substation | 535100 Other Goods and Services | 12964 | 12964 | 0 | 0
Transmission Line | C0061552 | L6043 Replacements and Upgrades | 535100 Other Goods and Services | 164955.8 | 0 | 0 | 0
Substation Operations | 43268 | 9W-B53 Tusket Replace Structure | 535100 Other Goods and Services | 0 | 16972 | 16972.3 | 0
Vegetation Management | C0020627 | 2020 Transmission ROW Widening 69kV | 535100 Other Goods and Services | 789.24 | 789.24 | 0 | 789.24
Transmission Line | 49775-T927 | L5004 Replacements and Upgrades | 535100 Other Goods and Services | 1043.48 | 1043.48 | 0 | 0
Substation Operations | 46811-T872 | 2H Armdale Transformer Addition | 535100 Other Goods and Services | 6387.98 | 6387.98 | 0 | 0
AMO - Customer Operations | C0031268 | AMO Critical Equipment Online Mon. | 535100 Other Goods and Services | 98.61 | 0 | 0 | 0
Substation Operations | C0010978 | T-2019/2020 Tran Switch & Breaker R | 535100 Other Goods and Services | 760.14 | 760.14 | 760.14 | 555
Transmission Line | C0041796 | L6020 Replacements and Upgrades Ph2 | 535100 Other Goods and Services | 0 | 0 | 285770.11 | 0
Substation Operations | C0053214 | 76W-T1 Transformer Replacement | 535100 Other Goods and Services | 0 | 74339 | 0 | 0
Substation Operations | C0041830 | Spare Power Prod Unit Transformer | 535100 Other Goods and Services | 0 | 0 | 76693 | 0
Substation Operations | C0031267 | 2022 Oil Containment Program | 535100 Other Goods and Services | 0 | 0 | 30514.73 | 0
Substation Operations | 48057-T965 | Replace 69kV cables between 2S& 83S | 535100 Other Goods and Services | 4306.46 | 4306.46 | 0 | 0
Substation Operations | C0045510 | 20V-T52 Transformer Replacement | 535100 Other Goods and Services | 391.52 | 0 | 0 | 0
Transmission Line | C0052634 | L5016 Replacements and Upgrades | 535100 Other Goods and Services | 286935.93 | 306935.93 | 0 | 0
Transmission Line | C0061543 | L5048 Replacements and Upgrades | 535100 Other Goods and Services | 103765.09 | 0 | 0 | 0
Substation Operations | 52314 | 1C-GT1/UT1 Replacement | 535100 Other Goods and Services | 434.21 | 434.21 | 0 | 0
Substation Operations | C0027362 | 2020 Petroleum Storage Tank Replace | 535100 Other Goods and Services | 582.19 | 582.19 | 0 | 0
Transmission Line | C0031122 | L6539-2021 Replacements and Upgrade | 535100 Other Goods and Services | 0 | 0 | 0 | 223741.14
Transmission Line | C0049212 | L8001 Replacements and Upgrades Ph3 | 535100 Other Goods and Services | 45 | 143253.92 | 0 | 0
Transmission Line | C0041812 | L6040 Replacements and Upgrades | 535100 Other Goods and Services | 37788 | 37788 | 75576 | 0
Substation Operations | C0031263 | 2021/2022 Substation Polychlorinate | 535100 Other Goods and Services | 145369.94 | 52331.59 | 50.48 | 523576
Substation Operations | C0024868 | Battery Bank and Charger Replacemen | 535100 Other Goods and Services | 169.91 | 0 | 0 | 0
Transmission Line | C0041805 | L7005 Replacements and Upgrades Ph2 | 535100 Other Goods and Services | 0 | 0 | 363741.47 | 0
Transmission Line | C0050835 | 2023/2024 Steel Tower Refurbishment | 535100 Other Goods and Services | 148.1 | 162764 | 0 | 0
ECEI | C0045132 | ECEI - Energy Storage | 535100 Other Goods and Services | 971742.86 | 0 | 315400168.08 | 0
Transmission Line | C0061546 | L6514 Replacements and Upgrades | 535100 Other Goods and Services | 235133.91 | 0 | 0 | 0
Substation Operations | C0021123 | 2020/2021 Substation PCB Equipment | 535100 Other Goods and Services | 21778.08 | 14731.71 | 0 | 2417.89
Substation Operations | C0053195 | 47C-T1 and T2 PHP Transformer Repl | 535100 Other Goods and Services | 0 | 350216 | 0 | 0
Substation Operations | 23121-T004-820 | PROVINCIAL- SUBSTATION ADDITIONS & | 535100 Other Goods and Services | 63035.15 | 62971.02 | 62483.03 | 60159.64
Transmission Line | 23115-T001-820 | PROVINCIAL TRANSMISSION LINE REPLAC | 535100 Other Goods and Services | 64824.13 | 64144.4 | 64037.63 | 64037.63
Substation Operations | C0057882 | 2024 Pennsylvania Breaker Replace | 535100 Other Goods and Services | 165441 | 0 | 0 | 0
Transmission Line | C0052299 | 2023 2024 Steel Tower Life Extensio | 535100 Other Goods and Services | 0 | 169667.5 | 0 | 0
Substation Operations | C0061883 | 129H - Kearney Lake Substation Rebu | 535100 Other Goods and Services | 79250.8 | 0 | 0 | 0
Transmission Line | C0041791 | L6551 Replacements and Upgrades | 535100 Other Goods and Services | 226785 | 226785 | 224950 | 0
Substation Operations | C0021122 | 2020-21 Transmission Switch and Br | 535100 Other Goods and Services | 2673.32 | 2673.32 | 2541.32 | 2541.32
Substation Operations | C0050842 | 2024 Bulk Oil Breaker Replacement | 535100 Other Goods and Services | 261985 | 0 | 0 | 0
Transmission Line | C0061545 | L6006 Replacements and Upgrades | 535100 Other Goods and Services | 596725.58 | 0 | 0 | 0
Substation Operations | C0011039 | 5V-GT1 Generating Transformer | 535100 Other Goods and Services | 1152.48 | 1152.48 | 0 | 0
Substation Operations | C0021140 | 98N-Stellarton Substation | 535100 Other Goods and Services | 195.81 | 0 | 0 | 0
Transmission Line | 44987-T820 | L7003 Lidar Upgrades | 535100 Other Goods and Services | 5741.35 | 5741.35 | 0 | 0
Substation Operations | C0061023 | 2024 EHV Breaker Replacements | 535100 Other Goods and Services | 291783 | 0 | 0 | 0
Transmission Line | C0044591 | Hwy 103 Exit 12 Public Works Line | 535100 Other Goods and Services | 87.74 | 0 | 0 | 0
Substation Operations | 51406 | 2018/2019 Transmission Switch & Bre | 535100 Other Goods and Services | 281.97 | 281.97 | 0 | 281.97
Large Industrial Reliability | C0053316 | Michelin Waterville Dynamic Voltage | 535100 Other Goods and Services | 5869090.97 | 0 | 0 | 0
Substation Operations | C0001900 | Mount Hope 69-25kV Substation | 535100 Other Goods and Services | 152.98 | 77.98 | 0 | 77.98
Substation Operations | C0031045 | 75W-T1 Replacement | 535100 Other Goods and Services | 0 | 247620 | 0 | 0
Substation Operations | C0058103 | 2023 Merlin Gerin Breaker Replaceme | 535100 Other Goods and Services | 35980.28 | 0 | 0 | 0
Substation Operations | 43267-T835 | 13V Gulch Replace 13V-GT1 & 13V-VR1 | 535100 Other Goods and Services | 254 | 254 | 0 | 0
Transmission Line | C0036826 | L8004 Parallel Canso Strait Cross | 535100 Other Goods and Services | 0 | 0 | 166961 | 0
Substation Operations | C0031283 | 2021 Substation Theft Prevention | 535100 Other Goods and Services | 263.54 | 263.54 | 263.54 | 36021
Substation Operations | C0021026 | Replace Willow Lane Power Transform | 535100 Other Goods and Services | 1233.06 | 1233.06 | 0 | 0
Substation Operations | C0031298 | 88S-T72 New Radiators | 535100 Other Goods and Services | 0 | 0 | 0 | 23646
Substation Operations | 43428-T787 | Remove 6S 4kV Switchgear Breakers | 535100 Other Goods and Services | 2.71 | 2.71 | 0 | 0
Transmission Line | C0041790 | L8001 Replacements and Upgrades Ph2 | 535100 Other Goods and Services | 0 | 0 | 156873.54 | 0
Substation Operations | C0041828 | Auto-Regen Breather Retrofit Progra | 535100 Other Goods and Services | 157.01 | 8944 | 8944 | 0
Substation Operations | C0061046 | 2024 Merlin Gerin Breaker Replaceme | 535100 Other Goods and Services | 89174.4 | 0 | 0 | 0
Substation Operations | C0055796 | 2023 EHV Breaker Replacements | 535100 Other Goods and Services | 90346 | 153027 | 0 | 0
Transmission Line | C0056843 | July 22, 2023 Level 3 Storm Transm | 535100 Other Goods and Services | 5.97 | 0 | 0 | 0
Transmission Line | C0035846 | 2021 Transmission Inspection Progra | 535100 Other Goods and Services | 0 | 28.48 | 0 | 0
Transmission Line | C0031064 | L5054 Line Replacements and Upgrade | 535100 Other Goods and Services | 0 | 0 | 0 | 89373
Substation Operations | C0034209 | 1C-GT2 Transformer Failure | 535100 Other Goods and Services | 982.26 | 982.26 | 0 | 0
Substation Operations | C0024875 | 30W Deteriorated Bus Structure Repl | 535100 Other Goods and Services | 10700 | 10700 | 0 | 0
Transmission Line | C0041810 | L5022 Replacements and Upgrades | 535100 Other Goods and Services | 220.04 | 220.04 | 244493.65 | 0
Transmission Line | C0021105 | L7002 Replacements and Upgrades PH1 | 535100 Other Goods and Services | 0 | 0 | 0 | 243564.61
Transmission Line | C0061550 | L5031 - Hubbards to East Chester | 535100 Other Goods and Services | 618485.57 | 0 | 0 | 0
Substation Operations | C0036187 | 3C-T71 Transformer Refurbishment | 535100 Other Goods and Services | 2650 | 1250 | 0 | 0
Substation Operations | C0031286 | Spare Padmounted Substation | 535100 Other Goods and Services | 136223 | 0 | 0 | 0
AMO - Customer Operations | C0028684 | AMO AM for Protection & Controls | 535100 Other Goods and Services | 0 | 5000 | 0 | 0
Transmission Line | C0010955 | 2020/2021 Wood Pole Retreatment | 535100 Other Goods and Services | 29.68 | 29.68 | 29.68 | 0
Transmission Line | C0020628 | L6055 - Hwy 107 Monopoles TIR | 535100 Other Goods and Services | 43.48 | 43.48 | 0 | 0
Transmission Line | C0031069 | L6020 Replacements and Upgrades | 535100 Other Goods and Services | 0 | 0 | 0 | 144084.99
Transmission Line | C0041789 | L5550 Replacements and Upgrades Ph2 | 535100 Other Goods and Services | 0 | 0 | 306295.75 | 0
Substation Operations | C0050852 | 10V-T1 Transformer Replacement | 535100 Other Goods and Services | 199809 | 0 | 0 | 0
Transmission Line | 48047-T870 | Trans Inspection Programs | 535100 Other Goods and Services | 179.99 | 179.99 | 0 | 0
Substation Operations | C0031052 | Replenish Spare used at 58C | 535100 Other Goods and Services | 0 | 0 | 81500 | 81500
Substation Operations | C0020162 | Substation Replacement of Grounds | 535100 Other Goods and Services | 10384.2 | 2608.76 | 0 | 0
Transmission Line | C0061403 | 2024 2025 Sacrificial Anode Install | 535100 Other Goods and Services | 186805 | 0 | 0 | 0
Transmission Line | C0061743 | L6038 Realignment | 535100 Other Goods and Services | 115241.85 | 0 | 0 | 0
Transmission Line | C0043010 | 2022 2023 Wood Pole Retreatment Prg | 535100 Other Goods and Services | 0 | 0 | 98320 | 0
Substation Operations | 51403 | T-2018 PCB Removal Program | 535100 Other Goods and Services | 1634.44 | 1634.44 | 0 | 0
Substation Operations | C0037907 | 5V-501 Switch & Structure Replace | 535100 Other Goods and Services | 1439.44 | 134.79 | 0 | 0
Substation Operations | C0041822 | WRC Spare Cable Repl & Storage Syst | 535100 Other Goods and Services | 40184.72 | 40184.72 | 49102.5 | 0
Substation Operations | 51956 | 6P Mobile Substation Rewind | 535100 Other Goods and Services | 1037.33 | 1037.33 | 0 | 0
Transmission Line | C0021102 | L5029 Replacements and Upgrades | 535100 Other Goods and Services | 0 | 0 | 0 | 480523
Substation Operations | C0035647 | 2021 Unplanned Failures (T003) | 535100 Other Goods and Services | 6667.78 | 6667.78 | 0 | 0
Substation Operations | C0043571 | 2022-2023 Transmission Switch & B | 535100 Other Goods and Services | 719.14 | 705.17 | 113588 | 0
Substation Operations | C0052997 | Subst Switch Motor Operator Retrofi | 535100 Other Goods and Services | 0 | 2762 | 0 | 0
Substation Operations | C0022742 | Retire 6S-Terrace Street | 535100 Other Goods and Services | 0 | 11214.64 | 0 | 0
Transmission Line | C0055696 | L5031 Replacement & Upgrade R.C Tap | 535100 Other Goods and Services | 0 | 151681.11 | 0 | 0
Transmission Line | C0041804 | 2022 Line Retirement Program | 535100 Other Goods and Services | 0 | 0 | 139272.54 | 0
Transmission Line | C0010949 | T - 2019/2020 Steel Tower Life Ext | 535100 Other Goods and Services | 232.29 | 232.29 | 0 | 232.29
ECEI | C0044391 | ECEI - Transmission | 535100 Other Goods and Services | 845.59 | 0 | 317811601.68 | 0
Substation Operations | C0024862 | 2020 Unplanned Failures (T003) | 535100 Other Goods and Services | 475.98 | 475.98 | 0 | 0
Substation Operations | C0032382 | Susie Lake Substation Addition | 535100 Other Goods and Services | 0 | 525373.1 | 525373.1 | 0
Substation Operations | C0055539 | 10H-T1 Transformer Replacement | 535100 Other Goods and Services | 275822.01 | 275822.01 | 0 | 0