## R1a - 2025 Spend
NS Power 2025 Capital Spend Detail - As per 2025 ACE Plan
4th Quarter Overview - as of December 31, 2025
| Generation | Distribution | Transmission | General Property | Total NS Power
2025 ACE Plan Total | 188123238.18 | 182568886.69 | 256543819.14 | 65139528.19 | 692375472.2
Total 2025 ACE Plan Spend (note 1)* | 173375248.8773 | 165186955.6991 | 224596274.8163 | 55062229.4664 | 618220708.8591
Other 2025 Capital Spending
Preliminary Spending (note 2) | 9554079.9312 | 1564825.54 | 8953475.55 | 4969846.88 | 25042227.9012
Spending on projects started prior to 2025, not in 2025 ACE Plan (note 3) | 14971193.3636 | 4520341.45 | 8380155.6887 | 1922308.89 | 29793999.3923
Spending on 2025 U&Us/P&As submitted to the Board (note 4) | 20198055 | 2554759.54 | 1757780.28 | 13980813.11 | 38491407.93
2025 Capital Spend | 218098577.1721 | 173826882.2291 | 243687686.335 | 75935198.3464 | 711548344.0827
*Total YTD Transmission spend includes ($11M) of proceeds received from WTI for the transfer of pre-2025 development costs transferred to Wasoqonatl Transmission Inc. (WTI) for CI C0044391 NS-NB Reliability Tie.
Note 1 - Top 10 2025 spend projects are listed in following report
Note 2 - Top 10 2025 preliminary spending projects are listed in following report
Note 3 - Top 10 2025 spend for projects started prior to 2025, not in 2025 ACE Plan are listed in following report
Note 4 - Top 10 2025 spend for U&U and P&A projects in are listed in following report

## R1b - Top 10s
Top 10 Projects
This report provides the Top 10 projects by the categories included in the preceding report
(1) | Total 2025 Spend: Top 10 projects that were included in the 2025 ACE Plan
| CI | Project Title | Functional Class | 2025
| C0045132 | ECEI - Energy Storage | Transmission Plant - T | 167944718.94
| C0068655 | LM6000 191-332 Life Extension | Gas Turbine Generation Plant - G | 18774149.23
| C0061521 | New Distribution Rights-of-Way Phase 10 | Distribution Plant - D | 18432929.5704
| C0013838 | HYD WRC LEM Unit Rehabilitation | Hydro Generation Plant - H | 13038174.28
| C0006418 | HYD WRC Tailrace Rock Bolting Phase 2 | Hydro Generation Plant - H | 12120971.78
| 23127 | Provincial Distribution Rights-Of-Way (D010) | Distribution Plant - D | 11944225.7178
| 39305 | Work Vehicle Replacements Routine (P062) | General Plant - P | 11756539.73
| 39767 | New Customers - Residential Central (D061) | Distribution Plant - D | 10474997.5
| 39769 | New Customers - Residential West (D061) | Distribution Plant - D | 7772373.11
| C0062123 | 143H - Mount Uniacke Substation Replacement | Transmission Plant - T | 6618511.55
(2) | Preliminary Spending: Top 10 preliminary spending on projects that have not been brought forward to the NSEB, are awaiting NSEB approval, or are included in the 2025 ACE Plan
| CI | Project Title | Functional Class | 2025
| C0081985 | Dynamic Voltage Restorer DVR 4 | Transmission Plant - T | 3037041.52
| C0062144 | Rural Nova Scotia EV Fast Charging (1) | General Plant - P | 2735574.07
| C0044172 | L7005 Canso Crossing Vibration Mitigation | Transmission Plant - T | 2105997.81
| 47650 | HYD - Annapolis Decision Analysis | Hydro Generation Plant - H | 1496449.51
| C0056722 | Distribution Inspection Program | Distribution Plant - D | 1383338.21
| C0062043 | IT - SharePoint Technical Migration | General Plant - P | 949983.06
| C0022247 | 1N-Onslow 138 kV Add Second 42 MVA | Transmission Plant - T | 941151.64
| C0032746 | WRC Tunnel T-1 Remediation | Hydro Generation Plant - H | 909202.17
| C0067403 | TRE5 PE Secondary Air Heater | Steam Generation Plant - S | 760867.63
| C0069687 | M10905 - Interconnection Study Decision | General Plant - P | 760570.98
(1) C0062144 - Rural Nova Scotia EV Fast Charging is a non-regulated project and is excluded from in NS Power's regulated Property, Plant and Equipment.
(3) | Spending on projects started prior to 2025, not in the 2025 ACE Plan: Top 10 projects that were included in prior ACE Plans or approved prior to 2025
| CI | Project Title | Functional Class | 2025
| C0055557 | 76V-T1 Transformer Replacement | Transmission Plant - T | 2135383.57
| C0064883 | IR 697 - 105V White Rock BESS TPIF | Transmission Plant - T | 1481163.86
| C0051136 | TUC2 - HP/IP Turbine Refurbishment 2024 | Steam Generation Plant - S | 1298811.653
| C0065024 | IR 662 - 132H Spider Lake BESS TPIF | Transmission Plant - T | 965945.55
| C0041837 | 2022 2023 Substation PCB Equipment Removal | Transmission Plant - T | 898603.02
| C0061289 | IT - Network Next Generation Security Design | General Plant - P | 844746.4
| 44978-H715 | HYD - Wreck Cove Controls Upgrade | Hydro Generation Plant - H | 756792.92
| C0060903 | POA Coal Transformer Replacement | Steam Generation Plant - S | 678143.56
| C0072568 | TRE6 Stack Breach Duct Refurbishment U&U | Steam Generation Plant - S | 638521.03
| C0071928 | 652V-212 Kentville Conversion | Distribution Plant - D | 626814.21
(4) | Spending on 2025 U&Us/P&As submitted to the NSEB or initiated: Top 10 projects not included in the 2025 ACE Plan that were initiated in 2025
| CI | Project Title | Functional Class | 2025
| C0080150 | TUC1 HP Turbine Vibration Refurbishment | Steam Generation Plant - S | 3574427.04
| C0073168 | Tusket Powerhouse Fish Passage | Hydro Generation Plant - H | 850024.15
| C0076072 | PHB - Stacker Conveyor Refurbishment U&U | Steam Generation Plant - S | 810672.22
| C0074110 | RC TRMC Roof Structure U&U | Steam Generation Plant - S | 600335.66
| C0082445 | PHB - Precipitator Duct Work Refurbishment U&U | Steam Generation Plant - S | 553020.51
| C0074452 | L6552 - 124C TOA Grid Modernization | Transmission Plant - T | 527282.2
| C0069626 | PHB - Wennberg South Screw Replacement U&U | Steam Generation Plant - S | 501487.46
| C0082589 | 99H-312 Farrell Street Feeder Upgrade | Distribution Plant - D | 472229.27
| C0076251 | 2025 Substation Theft Prevention | Transmission Plant - T | 446763.71
| C0080136 | Engine 191-443 HPC Blade Replacement | Gas Turbine Generation Plant - G | 427397.13

## R2 - Capital Items Status
NS Power Capital Item Status Update
4th Quarter Overview - as of December 31, 2025
This report includes all projects submitted to the NSEB and remain active, as well as ACE Plan subsequent submittal projects. Projects are removed from this report once the project has been final costed (internal or external), cancelled, or falls below $1M.
Status | Category | CI Number | Title | ACE Plan Reference (or U&U and P&A) | Submission/Date | ACE Amount | Submission or Approved Amount | Actual Spend | FIN Submission Date | FIN Amount | Variance
Deferred | Generation | 39472 | HYD - Mersey Redevelopment Phase 1 | 2022 ACE Plan (for Subsequent Approval) |  | 189447075.51 |  | 20979409.99
Approved | General Plant | 47751 | ECC Dynamic Line Rating Implementation | 2022 ACE Plan (for Subsequent Approval) | OTQ - December 1, 2025 | 5144525.08 | 2148364 | 1908420.39
Approved | Generation | 49634 | HYD - Trout River Diversion Structure Replacement | 2022 ACE Plan (for Subsequent Approval) | Q1 - May 13, 2024 | 1822299.7 | 3402776 | 3309527.65
Approved | Distribution | C0008638 | Cogswell HRM Redevelopment Program | 2022 ACE Plan (for Subsequent Approval) | OTQ - June 6, 2022 | 6982854.44 | 6617148.24 | 6661327.0359
Approved | Transmission | 43267 | 13V Gulch Hydro Replace 13V-GT1 and 13V-VR1 | 2015 ACE Plan | 2015 ACE Plan | 1061901.92 | 1061901.92 | 1011993.16
Approved | Transmission | 52314 | 1C-GT1/UT1 Replacement | 2018 ACE Plan | 2018 ACE Plan | 2032393 | 2032393 | 1678006.2 | OTQ - December 1, 2025 | 1678006 | -354386.8
Approved | Transmission | 49815 | 2017 / 2018 Steel Tower Refurbishment | 2017 ACE Plan | 2017 ACE Plan | 2003316.81 | 2003316.81 | 1937432.56
Approved | Distribution | 49919 | 2017 PCB Pole Top Transformer Replacement | 2017 ACE Plan | 2017 ACE Plan | 2446051.2 | 2446051.2 | 2550603.38
Approved | Distribution | 51493 | 2018 PCB Pole Top Transformer Replacement | 2018 ACE Plan | 2018 ACE Plan | 1360354 | 1360354 | 1384292.41
Approved | Transmission | 51403 | 2018 PCB Removal Program | 2018 ACE Plan | 2018 ACE Plan | 4402342 | 4402342 | 3533546.34
Approved | Transmission | 52258 | 2018/2019 Isolated Structure Replacement | 2018 ACE Plan | 2018 ACE Plan | 4818521 | 4818521 | 294849.4
Approved | Transmission | 51398 | 2018/2019 Steel Tower Refurbishment | 2018 ACE Plan | 2018 ACE Plan | 1992692 | 1992692 | 2055803.57
Approved | Distribution | 47787 | 2H Armdale New Feeders | 2017 ACE Plan (for Subsequent Approval) | OTQ - April 6, 2020 | 1285679 | 1734221 | 1723920.45
Approved | Transmission | 52328 | 56N-T1 Transformer Upgrades | 2018 ACE Plan | 2018 ACE Plan | 1279271 | 1279271 | 1307910.2
Approved | Transmission | 51975 | 5P Mobile Substation Replacement | 2018 ACE Plan | 2018 ACE Plan | 4829458 | 4829458 | 2979107.49
Approved | Transmission | 51956 | 6P Mobile Substation Rewind U&U | U&U | Q3 2017 - October 30, 2017 | 0 | 1516120.57 | 635776 | OTQ - December 1, 2025 | 635776 | -880344.57
Approved | Distribution | 47124 | Advanced Metering Infrastructure | 2017 ACE Plan (for Subsequent Approval) | OTQ - February 17, 2023 | 8274738 | 143495843.8622 | 142942429.5
Approved | Generation | 48914 | HYD - Malay Falls Facility Repair | 2017 ACE Plan (for Subsequent Approval) | Q3 2017 - October 30, 2017 | 446237 | 1034045 | 1105327.73
Approved | Generation | 47551 | HYD - SHH Controls Upgrade | 2016 ACE Plan (for Subsequent Approval) | Q4 2015 - January 29, 2016 | 1092850.61 | 1749212 | 1956464.95
Deferred | Generation | 49942 | HYD - Tidewater Facility Refurbishment | 2018 ACE Plan | 2018 ACE Plan | 1234178 | 1234178 | 1229298.05
Withdrawn | Generation | 29807 | HYD - Tusket Falls Main Dam | 2017 ACE Plan (for Subsequent Approval) | OTQ - July 23, 2021 | 9940664 | 36826119 | 25502028.21
Approved | Generation | 51234 | HYD - WRC HVAC Upgrade | 2018 ACE Plan | 2018 ACE Plan | 1876537 | 1876537 | 1883155.09
Approved | Generation | 48791 | HYD - WRC Safety Standards Upgrades | 2018 ACE Plan (for Subsequent Approval) | OTQ - June 4, 2018 | 1019927.73 | 1760570 | 1919440.54
Approved | Generation | 51236 | HYD - WRC Tailrace Rock Bolting | 2018 ACE Plan | 2018 ACE Plan | 8861996 | 8861996 | 7746964.37
Approved | Generation | 48052 | HYD Annapolis HVAC Upgrade | 2017 ACE Plan (for Subsequent Approval) | OTQ - March 8, 2017 | 1498367 | 1573596 | 1862133.01
Approved | Generation | 44978 | HYD-Wreck Cove Automation | 2015 ACE Plan (for Subsequent Approval) | Q2 2015 - July 31, 2015 | 2379999.4 | 3802446.04 | 4026571.02
Deferred | General Plant | 49600 | IT - Network Architecture Redesign | 2017 ACE Plan (for Subsequent Approval) |  | 1183826 |  | 0
Approved | General Plant | 49855 | IT Desktop SW Modernization | 2017 ACE Plan (for Subsequent Approval) | Q3 2017 - October 30, 2017 | 2013034 | 4620515.89 | 4501620.94
Approved | Transmission | 47950 | L5017 Replacements & Upgrades | 2016 ACE Plan | Q1 2018 - May 7, 2018 | 2182142.33 | 3062664 | 3012632.2
Approved | Transmission | 47949 | L5028 Replacements and Upgrades | 2016 ACE Plan | 2016 ACE Plan | 1144354.64 | 1144354.64 | 943265
Approved | Transmission | 49778 | L5535 Replacements and Upgrades | 2017 ACE Plan | OTQ - April 16, 2018 | 1261920.05 | 2590269 | 2837177.2
Approved | Transmission | 49779 | L6537 Replacements and Upgrades | 2018 ACE Plan | OTQ - March 4, 2019 | 1255220 | 2331474.13 | 2284615.84
Approved | Transmission | 52320 | L6549 2018 Replacements & Upgrades | 2018 ACE Plan | 2018 ACE Plan | 1406535 | 1406535 | 1452522.7
Approved | Transmission | 44987 | L7003 Lidar Upgrades | 2015 ACE Plan (for Subsequent Approval) | OTQ - August 31, 2015 | 6885816.76 | 11032275 | 10907019.52
Approved | Transmission | 49793 | L7011 Replacements and Upgrades | 2017 ACE Plan | OTQ - April 1, 2019 | 3343484.22 | 4810276 | 4591706.24
Approved | Transmission | 47954 | L7012 Replacements and Upgrades | 2017 ACE Plan | 2017 ACE Plan | 4428519.78 | 4428519.78 | 4392085.97
Approved | Generation | 49940 | LM6000 TUC5 Control System Upgrade | 2017 ACE Plan (for Subsequent Approval) | OTQ - July 3, 2018 | 1018769 | 1275559 | 1070506.19
Approved | Transmission | C0001900 | Mount Hope 69-25kV Substation | 2018 ACE Plan | 2018 ACE Plan | 2982338 | 2982338 | 2998217.16
Approved | Transmission | 52323 | Port Hastings 2C BPS Upgrade | P&A | Q2 - August 7, 2018 | 0 | 4201448.53 | 3997957.67
Approved | General Plant | 50153 | Self Serve Development Phase 2 | 2017 ACE Plan (for Subsequent Approval) | OTQ - September 15, 2017 | 1827720 | 1160528 | 1316269.11
Not Approved at this time | Transmission | 43678 | Separate L8004/L7005 on Canso Crossing Double Circuit Tower(DCT) | 2017 ACE Plan (for Subsequent Approval) | OTQ - January 27, 2022* | 16183691 | 20387278 | 20387277.51
Not Approved at this time | Transmission | 45066 | Upgrade L6511 and L7019 Thermal Rating | 2015 ACE Plan (for Subsequent Approval) | OTQ - January 27, 2022* | 3693032.91 | 2691017 | 2691016.62
Not Approved at this time | Transmission | 43324 | Replace L6513 / Upgrade Line Terminals | 2015 ACE Plan (for Subsequent Approval) | OTQ - January 27, 2022* | 23429902 | 18626428 | 18625268.15
Not Approved at this time | Transmission | 45067 | 67N Onslow 345 KV Node Swap | 2014 ACE Plan (for Subsequent Approval) | OTQ - January 27, 2022* | 3006487 | 2982714 | 2982585.13
Approved | Transmission | 48022 | Spider Lake Substation Addition | 2016 ACE Plan (for Subsequent Approval) | OTQ - March 4, 2019 | 6348980.72 | 9158260 | 9066397.53
Approved | Generation | 50518 | HYD - Ruth Falls Main Dam Refurbishment | 2019 ACE Plan | OTQ - October 11, 2024 | 7244422 | 14839116 | 9460999.82
Approved | Transmission | C0010042 | 2019 Transmission Right-of-Way Widening 69kV | 2019 ACE Plan | 2019 ACE Plan | 5650794 | 5650794 | 5634125.15
Approved | Transmission | C0010948 | 2019/2020 Sacrificial Anode Installation Program | 2019 ACE Plan | 2019 ACE Plan | 3099862 | 3099862 | 3244208.44
Approved | Transmission | C0010952 | 2019/2020 Substation Polychlorinated Biphenyl (PCB) Equipment Removal | 2019 ACE Plan | 2019 ACE Plan | 2786245 | 2786245 | 2796215.85
Approved | Transmission | C0010949 | 2019/2020 Steel Tower Life Extension | 2019 ACE Plan | 2019 ACE Plan | 2414140 | 2414140 | 2178231.16
Approved | Transmission | C0011339 | L6549 - Replacements and Upgrades Phase 2 | 2019 ACE Plan | Q1 - May 13, 2024 | 2209907 | 3993973.66 | 3913058.01
Approved | Transmission | C0011241 | L5026 - Replacements and Upgrades | 2019 ACE Plan | 2019 ACE Plan | 1498789 | 1498789 | 1379562.67
Approved | Transmission | C0010978 | 2019/2020 Transmission Switch & Breaker Replacement | 2019 ACE Plan | 2019 ACE Plan | 1044148 | 1044148 | 1029498.49
Approved | Transmission | C0011243 | L5551 - Replacements and Upgrades | 2019 ACE Plan | 2019 ACE Plan | 1014077 | 1014077 | 1115386.39
Approved | Distribution | C0011208 | 2019 Padmount Replacement Program | 2019 ACE Plan | 2019 ACE Plan | 1413544 | 1413544 | 1496436.01
Approved | Distribution | C0006319 | 2019 PCB Pole Top Transformer Replacements | 2019 ACE Plan | 2019 ACE Plan | 1177592 | 1177592 | 1625291.36
Approved | General Plant | C0013438 | IT - T&D WAM Phase 1 - GIS and Field Design System | 2019 ACE Plan (2018 Pending Submission) | OTQ - December 7, 2018 | 7978434 | 7978434 | 8098332.98
Partial Approval | Generation | C0013838 | HYD WRC LEM Unit Rehabilitation | 2020 ACE Plan (2019 Pending Submission) | OTQ - February 21, 2020 | 109691966.51 | 101787264 | 104196288.2
Approved | Distribution | 47794 | Heckman's Island Submarine Cable Replacement | 2021 ACE Plan (for Subsequent Approval) | Q1 2021 - May 3, 2021 | 1296112.43 | 1338363.88 | 1554825.72
Approved | General Plant | C0011378 | Route Network Upgrades | 2020 ACE Plan (2019 Pending Submission) | OTQ - December 2, 2019 | 5724239.86 | 5717751.93 | 5946763.15
Approved | General Plant | 49480 | IT - Data Centre Disaster Recovery | 2020 ACE Plan (2019 Pending Submission) | OTQ - December 2, 2019 | 6103797.71 | 6335161.85 | 6249505.23
Approved | General Plant | C0010838 | MCC - HVAC Replacement | 2019 ACE Plan (for Subsequent Approval) | OTQ - October 4, 2021 | 1071364 | 1606253.82 | 1531909.94
Approved | General Plant | C0002137 | ECC - Map Board and Technology Modernization | 2019 ACE Plan (for Subsequent Approval) | Q3 - November 4, 2019 | 2568789 | 2506267.89 | 2274318.45
Approved | Transmission | C0021105 | L7002 Replacements and Upgrades Phase 2 | P&A | Q3 - November 4, 2019 | 0 | 3121441.58 | 3320026.92
Approved | Distribution | C0020623 | New Distribution Rights-of-Way Phase 5 | 2020 ACE Plan | 2020 ACE Plan | 10015266.14 | 10015266.14 | 9930357.98
Approved | Transmission | C0020627 | 2020 Transmission Right-of-Way Widening 69kV | 2020 ACE Plan | 2020 ACE Plan | 5489820 | 5489820 | 5617281.86
Approved | Transmission | C0011261 | 101W Port Mersey Substation Expansion | 2020 ACE Plan | 2020 ACE Plan | 4651384 | 4651384 | 4734493.18
Approved | Transmission | C0021123 | 2020/2021 Substation Polychlorinated Biphenyl (PCB) Equipment Removal | 2020 ACE Plan | 2020 ACE Plan | 5197371.63 | 5197371.63 | 5497127.42
Approved | Generation | 49949 | LM6000 TUC4 Control System Replacement | 2020 ACE Plan | 2020 ACE Plan | 1149996.27 | 1149996.27 | 901766.31
Approved | Transmission | C0011321 | L5031 Replacements and Upgrades Phase 1 | 2020 ACE Plan | 2020 ACE Plan | 2147211.75 | 2147211.75 | 368505.25
Approved | Transmission | C0021107 | L8001 Replacements and Upgrades Phase 1 | 2020 ACE Plan | 2020 ACE Plan | 2292092.86 | 2292092.86 | 2517260.08
Approved | Distribution | C0020835 | 2020 Padmount Replacement Program | 2020 ACE Plan | 2020 ACE Plan | 1612389.23 | 1612389.23 | 1519347.68
Approved | Transmission | C0021122 | 2020/2021 Transmission Switch & Breaker Replacement | 2020 ACE Plan | 2020 ACE Plan | 1312642.8 | 1312642.8 | 1525838.42
Approved | Distribution | C0020834 | 2020/2021 Inaccessible PCB Transformer Replacements | 2020 ACE Plan | 2020 ACE Plan | 2950294.39 | 2950294.39 | 3099462.57
Approved | General Plant | C0021109 | New RTU Deployment Project | 2020 ACE Plan | 2020 ACE Plan | 8028097.17 | 8028097.17 | 7862440.42
Approved | Transmission | 52303 | L7019 Replacements and Upgrades | 2020 ACE Plan | 2020 ACE Plan | 1374091.91 | 1374091.91 | 1383195.98
Approved | Transmission | C0021026 | Willow Lane 15N-T3 Replacement | 2020 ACE Plan | 2020 ACE Plan | 1326646.57 | 1326646.57 | 1179586.14
Approved | Generation | 49756 | HYD - Marshall Falls Main Dam Refurbishment | 2020 ACE Plan | 2020 ACE Plan | 5452793.82 | 5452793.82 | 675055.72
Approved | Transmission | C0021142 | 19W-T51 Transformer Replacement | 2020 ACE Plan | 2020 ACE Plan | 1512336.33 | 1512336.33 | 1473278.51
Approved | Distribution | C0021182 | 93V-313-Meteghan Rebuild | 2020 ACE Plan | 2020 ACE Plan | 1075624.51 | 1075624.51 | 927225.44
Approved | Distribution | C0010778 | Smart Grid Nova Scotia Project | 2020 ACE Plan (for Subsequent Approval) | OTQ - December 5, 2019 | 6740589.05 | 7053622 | 6670498.28
Approved | Distribution | C0019379 | 50N-410 - 4C-430 Highway 104 Twinning | 2020 ACE Plan (for Subsequent Approval) | OTQ - June 1, 2020 | 1361237.37 | 1137222.61 | 1228681.6
Approved | General Plant | C0023622 | AMO Substation and Transmission APM Program | 2020 ACE Plan (for Subsequent Approval) | OTQ - April 6, 2020 | 2087848.28 | 2217589 | 2369151.05
Partial Approval | Generation | C0014218 | HYD WRC LEM Balance of Plant | 2021 ACE Plan (2020 Pending Submission) | OTQ - April 30, 2021 | 21186378.42 | 27637896 | 20353238.86
Approved | General Plant | C0023623 | AMO Distribution APM Program | 2020 ACE Plan (for Subsequent Approval) | OTQ - April 6, 2020 | 1708239.85 | 1721484.45 | 1817941.65
Approved | Generation | 16374 | HYD Gaspereau Dam Safety | 2008 ACE Plan | OTQ - February 23, 2020 | 4354889 | 22703451 | 12345952.89
Approved | Distribution | C0031083 | New Distribution Rights-of-Way Phase 6 | 2021 ACE Plan | 2021 ACE Plan | 9762734.52 | 9762734.52 | 9705372.68
Approved | Transmission | C0031263 | 2021/2022 Substation Polychlorinated Biphenyl (PCB) Equipment Removal | 2021 ACE Plan | 2021 ACE Plan | 7512225.73 | 7512225.73 | 7061872.02
Approved | Transmission | C0031089 | 2021/2022 Transmission Right-of-Way Widening 69kV | 2021 ACE Plan | 2021 ACE Plan | 5288520 | 5288520 | 5512846.46
Approved | Transmission | C0031122 | L6539 Replacements and Upgrades | 2021 ACE Plan | OTQ - April 7, 2025 | 2821842.28 | 5584042.12 | 1415433.41
Approved | Transmission | C0031085 | L6516 Line Replacement and Upgrades | 2021 ACE Plan | 2021 ACE Plan | 2730591.81 | 2730591.81 | 2544182.7
Approved | Transmission | C0031050 | New Spare Large Autotransformer | 2021 ACE Plan | 2021 ACE Plan | 2398564.03 | 2398564.03 | 2374092.32
Approved | Transmission | C0033644 | 2021/2022 Steel Tower Life Extension | 2021 ACE Plan | 2021 ACE Plan | 2332745.87 | 2332745.87 | 1831087.15
Approved | Transmission | C0033645 | 2021/2022 Steel Tower Refurbishment | 2021 ACE Plan | 2021 ACE Plan | 1944004.84 | 1944004.84 | 2208430.38
Approved | Distribution | C0031145 | 2021 Padmount Replacement Program | 2021 ACE Plan | 2021 ACE Plan | 1636152.76 | 1636152.76 | 1165437.05
Approved | Transmission | C0031262 | 2020/2021 Transmission Switch and Breaker Replacement | 2021 ACE Plan | 2021 ACE Plan | 1483047.6 | 1483047.6 | 1456539.46
Approved | Transmission | C0031064 | L5054 Replacements and Upgrades | 2021 ACE Plan | 2021 ACE Plan | 1134737.48 | 1134737.48 | 996871.76
Approved | Generation | 46483 | CT - TUS Control System Upgrade | 2021 ACE Plan | 2021 ACE Plan | 1046322.12 | 1046322.12 | 1092842.27
Approved | Generation | C0026285 | TRE Heavy Fuel Oil Tank Refurbishment | 2021 ACE Plan (for Subsequent Approval) | OTQ - June 10, 2021 | 1732920.72 | 2979545.51 | 2464227.58
Approved | General Plant | C0030987 | IT - NERC CIP Environment Refresh | 2022 ACE Plan (2021 Pending Submission) | OTQ - March 7, 2022 | 1446131 | 1259927 | 1309292.99
Approved | Distribution | C0041892 | New Distribution Rights-of-Way Phase 7 | 2022 ACE Plan | 2022 ACE Plan | 9854290.53 | 9854290.53 | 10222016.49
Approved | Transmission | C0041893 | 2022/2023 Transmission Right-of-Way Widening 69kV | 2022 ACE Plan | 2022 ACE Plan | 5312315 | 5312315 | 5187077.9
Approved | Transmission | C0041837 | 2022/2023 Substation Polychlorinated Biphenyl (PCB) Equipment Removal | 2022 ACE Plan | 2022 ACE Plan | 3805434.21 | 3805434.21 | 4013356.05
Approved | Transmission | C0041793 | L7002 Replacements and Upgrades Phase 2 | 2022 ACE Plan | 2022 ACE Plan | 3640960.16 | 3640960.16 | 3856784.58
Approved | Transmission | C0041989 | 2022/2023 Sacrificial Anode Installation Program | 2022 ACE Plan | 2022 ACE Plan | 3015106.56 | 3015106.56 | 2773422.66
Deferred | Transmission | C0041794 | L5031 Replacements and Upgrades Phase 2 | 2022 ACE Plan | 2022 ACE Plan | 2905019.26 | 2905019.26 | 0
Approved | Transmission | C0041791 | L6551 Replacements and Upgrades | 2022 ACE Plan | 2022 ACE Plan | 1988245.66 | 1988245.66 | 1060031.65
Approved | Distribution | C0043130 | 2022 Padmount Replacement Program | 2022 ACE Plan | 2022 ACE Plan | 1807359.37 | 1807359.37 | 1918298.57
Approved | Transmission | C0043571 | 2022/2023 Transmission Switch & Breaker Replacement | 2022 ACE Plan | 2022 ACE Plan | 1612637.79 | 1612637.79 | 1874672.45
Approved | Generation | C0036368 | HYD - Lower Great Brook Switchgear Replacement | 2022 ACE Plan | 2022 ACE Plan | 1362281.36 | 1362281.36 | 1409664.6
Approved | Transmission | C0043010 | 2022/2023 Wood Pole Retreatment Program | 2022 ACE Plan | 2022 ACE Plan | 1300037.21 | 1300037.21 | 791054.43 | OTQ - October 10, 2025 | 791054 | -508983.21
Approved | Transmission | C0041804 | 2022 Line Retirement Program | 2022 ACE Plan | 2022 ACE Plan | 1242178.29 | 1242178.29 | 159804.05
Approved | Generation | C0024484 | HYD - Fourth Lake Switchgear Replacement | 2022 ACE Plan | 2022 ACE Plan | 1145245.46 | 1145245.46 | 1382071.35
Approved | Generation | C0029691 | CT - VJ1 Control System Upgrade | 2022 ACE Plan | 2022 ACE Plan | 1016224.92 | 1016224.92 | 1002085.09
Approved | Transmission | C0045132 | ECEI - Battery Energy Storage System Project | 2022 ACE Plan (for Subsequent Approval) | OTQ - January 25, 2024 | 171207919.79 | 237772259 | 214109186.1
Deferred | Generation | C0044392 | Eastern Clean Energy Initiative (ECEI) - Coal Conversion | 2022 ACE Plan (for Subsequent Approval) |  | 32341324.51 |  | 1810843.13
Deferred | Generation | C0034486 | HYD - WRC LEM Penstock intake | 2022 ACE Plan (for Subsequent Approval) |  | 11239850.61 |  | 1206698.21
Approved | Generation | C0000979 | HYD - Governor Dam Refurbishment | 2022 ACE Plan (for Subsequent Approval) | OTQ - November 6, 2023 | 2696629.84 | 4844345.32 | 4940761.96
Approved | Distribution | C0022662 | 22C-404GA Lennox Passage Rebuild | 2022 ACE Plan (for Subsequent Approval) | OTQ - July 4, 2022 | 2352190.78 | 2609595.48 | 2908812.9
Deferred | Transmission | C0036826 | L8004 Parallel Canso Strait Crossing | 2022 ACE Plan (for Subsequent Approval) |  | 2139081.25 |  | 0
Approved | General Plant | C0041994 | NERC CIP 2022 | 2022 ACE Plan (for Subsequent Approval) | OTQ - April 4, 2022 | 1379473.59 | 1247663 | 1185536.49
Approved | Generation | C0041651 | TUC HFO Tank 4 Refurbishment | 2022 ACE Plan (for Subsequent Approval) | Q4 - February 6, 2023 | 1110292.77 | 2734313 | 2756903.42
Approved | Transmission | C0010956 | 78W-Martin’s Brook Substation Relocation | P&A | OTQ - March 3, 2025 | 0 | 5122761 | 4640479.04
Approved | Transmission | C0045510 | 20V-T52 Transformer Replacement | U&U | Q3 - November 7, 2022 | 0 | 1506565.52 | 1520530.22
Approved | Transmission | C0041807 | L5534 Replacements and Upgrades | P&A | OTQ - December 5, 2022 | 0 | 1426418.29 | 1558693.82
Approved | Transmission | C0049212 | L8001 Replacements and Upgrades Phase 3 | P&A | OTQ - December 5, 2022 | 0 | 1263906.4 | 1220001.27
Approved | Transmission | C0050835 | 2023/2024 Steel Tower Refurbishment | P&A | OTQ - December 5, 2022 | 0 | 2056634.87 | 1546237.65
Approved | Transmission | C0052055 | 2023/2024 Transmission Right-of-Way Widening 69kV | P&A | OTQ - December 5, 2022 | 0 | 5332315 | 5333377.69
Approved | Distribution | C0052056 | New Distribution Rights-of-Way Phase 8 | P&A | OTQ - December 5, 2022 | 0 | 9796663.1 | 9088167.29
Approved | Transmission | C0052634 | L5016 Replacements and Upgrades | P&A | OTQ - December 5, 2022 | 0 | 2697636.73 | 2905454.9
Approved | Generation | C0001222 | CT BGT1 Engine Exchange | P&A | OTQ - January 9, 2023 | 0 | 2338747 | 2350941.06
Approved | Generation | C0055376 | TUC1 - LP Blade Refurbishment U&U | U&U | Q4 - February 6, 2023 | 0 | 2025440.22 | 1988074.59
Approved | Generation | C0041506 | LM6000 Engine 191-253 Refurbishment | 2023 ACE Plan | OTQ - March 7, 2024 | 8740978.85 | 13473407 | 13049104.69
Approved | Generation | C0012838 | HYD - Lequille Canal Dyke, Gates and Tailrace Refurbishment | 2023 ACE Plan | 2023 ACE Plan | 7058816.14 | 7058816.14 | 6220627.98
Approved | Generation | C0029682 | CT VJ2 - Replace Generator Assembly | 2023 ACE Plan | 2023 ACE Plan | 5397737.93 | 5397737.93 | 4759604.1294
Approved | Generation | C0051134 | TUC2 - L-0 Blade Replacement | 2023 ACE Plan | 2023 ACE Plan | 4157503.35 | 4157503.35 | 4171776.93
Approved | Transmission | C0041788 | L6516 Replacements and Upgrades Phase 2 | 2023 ACE Plan | OTQ July 2, 2024 | 3123474.28 | 5442793.92 | 4675857.42
Approved | Transmission | C0055539 | 10H-T1 Transformer Replacement | 2023 ACE Plan | 2023 ACE Plan | 2420891.67 | 2420891.67 | 95289.81
Approved | Transmission | C0052299 | 2023/2024 Steel Tower Life Extension | 2023 ACE Plan | 2023 ACE Plan | 2195463.46 | 2195463.46 | 1920910.07
Approved | Transmission | C0055796 | 2023 EHV Breaker Replacements | 2023 ACE Plan | OTQ - October 2, 2023 | 2048410.56 | 3463488.74 | 1477032.66
Approved | Transmission | C0055696 | L5031 Replacement and Upgrades Robinson Corner Tap | 2023 ACE Plan | 2023 ACE Plan | 1357477.23 | 1357477.23 | 1382764.29
Approved | Distribution | C0050836 | 2023 Padmount Replacement Program | 2023 ACE Plan | 2023 ACE Plan | 1309551.39 | 1309551.39 | 1556722.5
Approved | Generation | C0051135 | TUC2 - Turbine Valves Refurbishment 2023 | 2023 ACE Plan | 2023 ACE Plan | 1048924 | 1048924 | 967210.58
Approved | Transmission | C0052654 | L5541 Water Crossing Upgrades | 2023 ACE Plan | 2023 ACE Plan | 1047073.87 | 1047073.87 | 0
Approved | Transmission | C0053316 | Michelin Voltage Sag Reduction DVR | 2023 ACE Plan (for Subsequent Approval) | OTQ - April 12, 2024 | 21007507.1 | 31170675 | 32580748.19
Approved | General Plant | C0042166 | IT - Data Loss Prevention (DLP) Platform | 2023 ACE Plan (for Subsequent Approval) | OTQ - June 7, 2023 | 3233905.29 | 4261239.1945 | 3944258.36
Approved | Generation | C0051894 | TUC - HFO Tank 3 Refurbishment | 2023 ACE Plan (for Subsequent Approval) | OTQ - March 7, 2024 | 2053937.48 | 2218012 | 2250702.55
Approved | Generation | C0044030 | WIN - DIG Haight's Brook Crossing Replacement | 2023 ACE Plan (for Subsequent Approval) | OTQ - November 6, 2023 | 2046984.81 | 2024051.53 | 306367.3224
Approved | Transmission | C0055557 | 76V-T1 Transformer Replacement | 2023 ACE Plan (for Subsequent Approval) | OTQ - April 7, 2025 | 1751258.26 | 3151575 | 2354694.76
Approved | General Plant | C0011167 | IT - Backup Infrastructure Upgrade | 2023 ACE Plan (for Subsequent Approval) | OTQ - June 7, 2023 | 1557470.73 | 2315457.44 | 2324003.44
Approved | Generation | C0048591 | CT VJ1 Engine P686621 Refurbishment | P&A | OTQ - March 6, 2023 | 0 | 2312509.06 | 2283878.09
Approved | Generation | C0054356 | TUC – Roof Replacement U&U | U&U | OTQ - March 6, 2023 | 0 | 1459455.09 | 1412184.76
Approved | Generation | C0053916 | CT BGT4 Engine P686630 Refurbishment | U&U | OTQ - April 3, 2023 | 0 | 1850500.99 | 1718317.45
Approved | Transmission | C0031052 | Replenish Spare Transformer Used at 58C | 2021 ACE Plan (Less than $1M) | OTQ - June 7, 2023 | 982910 | 1303826.93 | 1188276.71
Approved | Generation | 51761 | LIN2 2022/2023 Winter Capacity Requirement | U&U | OTQ - September 5, 2023 | 0 | 2512340.71 | 2526651.43
Approved | Generation | C0006418 | HYD WRC Tailrace Tunnel Rock Bolting Phase 2 | 2024 ACE Plan | 2024 ACE Plan | 15722669.17 | 15722669.17 | 12992023.46
Approved | General Plant | C0047277 | IT - GIS Utility Network Upgrade | 2024 ACE Plan | 2024 ACE Plan | 6175229.82 | 6175229.82 | 3377292.58
Approved | Generation | C0049013 | HYD - Lower Great Brook Log Hoist Replacement | 2024 ACE Plan | 2024 ACE Plan | 2158657.9 | 2158657.9 | 1849596.12
Approved | Generation | C0049032 | HYD - Cowie Falls Log Hoist Replacement | 2024 ACE Plan | 2024 ACE Plan | 2237991.11 | 2237991.11 | 1777586.39
Approved | General Plant | C0049619 | IT - ERP Upgrade (EBS, PS, PP, OBIA) | 2024 ACE Plan | 2024 ACE Plan | 6198799.37 | 6198799.37 | 5543293.15
Approved | Transmission | C0050842 | 2024 Bulk Oil Breaker Replacement Program | 2024 ACE Plan | 2024 ACE Plan | 3274755.9 | 3274755.9 | 1142609.86
Approved | Generation | C0051136 | TUC2 - HP/IP Turbine Refurbishment | 2024 ACE Plan | 2024 ACE Plan | 4264777.44 | 5965028 | 6173867.8652
Approved | Transmission | C0056240 | 2024/2025 Transmission Switch and Breaker Replacements | 2024 ACE Plan | 2024 ACE Plan | 3271621.79 | 3271621.79 | 3156825.05
Approved | Distribution | C0057142 | New Distribution Rights-of-Way Phase 9 | 2024 ACE Plan | 2024 ACE Plan | 19141913.7 | 19141913.7 | 19189121.4
Approved | Transmission | C0057882 | 2024 Pennsylvania Breaker Replacements | 2024 ACE Plan | 2024 ACE Plan | 2163831.86 | 2163831.86 | 531098.66
Approved | Generation | C0058942 | WRC D11-2 Foundation Stabilization | 2024 ACE Plan | 2024 ACE Plan | 1540602.39 | 1540602.39 | 1416577.81
Approved | Transmission | C0059046 | 101S and 79N Reactor Replacements | 2024 ACE Plan | 2024 ACE Plan | 1460062.22 | 1460062.22 | 827303.24
Approved | Generation | C0060608 | TUC6 Turbine Refurbishment | 2024 ACE Plan | 2024 ACE Plan | 2472311.19 | 2472311.19 | 566530.14
Approved | Generation | C0060707 | CT BGT1 Generator Refurbishment | 2024 ACE Plan | 2024 ACE Plan | 3482602.45 | 3482602.45 | 7685.96
Approved | Distribution | C0060749 | 2024 Padmount Replacement Program | 2024 ACE Plan | 2024 ACE Plan | 1288197.9 | 1288197.9 | 2140302.3
Approved | Transmission | C0061023 | 2024 EHV Breaker Replacements | 2024 ACE Plan | 2024 ACE Plan | 3638479.75 | 3638479.75 | 701.66
Approved | Transmission | C0061046 | 2024 Merlin Gerin Breaker Replacements | 2024 ACE Plan | 2024 ACE Plan | 1169590.5 | 1169590.5 | 353878.19
Approved | Transmission | C0061387 | 2024 2025 Wood Pole Retreatment Program | 2024 ACE Plan | 2024 ACE Plan | 1209391.21 | 1209391.21 | 258382.07
Approved | Transmission | C0061403 | 2024 2025 Sacrificial Anode Installation Program | 2024 ACE Plan | 2024 ACE Plan | 2382112.6 | 2382112.6 | 2414188.19
Approved | Transmission | C0061545 | L6006 Replacements and Upgrades | 2024 ACE Plan | 2024 ACE Plan | 5032640.4 | 5032640.4 | 5091679.88
Approved | Transmission | C0061546 | L6514 Replacements and Upgrades | 2024 ACE Plan | 2024 ACE Plan | 2102666.38 | 2102666.38 | 1643937.09
Approved | Transmission | C0061547 | L7022 Replacements and Upgrades | 2024 ACE Plan | 2024 ACE Plan | 2283568.76 | 2283568.76 | 875331.51
Approved | Transmission | C0061550 | L5031 Replacements and Upgrades - Hubbards to East Chester | 2024 ACE Plan | 2024 ACE Plan | 5297583.52 | 5297583.52 | 3904537.65
Approved | Transmission | C0061551 | L7009 Replacements and Upgrades | 2024 ACE Plan | 2024 ACE Plan | 3280328.4 | 3280328.4 | 1153388.87
Approved | Transmission | C0061743 | L6038 Realignment | 2024 ACE Plan | 2024 ACE Plan | 1032910.93 | 1032910.93 | 1022478.32
Approved | Transmission | C0061883 | 129H - Kearney Lake Substation Rebuild | 2024 ACE Plan | 2024 ACE Plan | 1017322.14 | 1017322.14 | 55532.73
Approved | General Plant | C0054755 | IT - Connect My Data (Green Button) | 2024 ACE Plan (for Subsequent Approval) | Q4 - February 5, 2024 | 2309350.36 | 2964237 | 3088072.63
Deferred | Transmission | C0031286 | Spare Padmounted Substation | 2024 ACE Plan (for Subsequent Approval) |  | 1319837.87 |  | 0
Awaiting Approval | General Plant | C0032664 | ECC Optimization Tools Project | 2024 ACE Plan (for Subsequent Approval) | OTQ - December 1, 2025 | 4329149.97 | 7486068 | 6532898
Approved | Generation | C0050414 | HYD Roseway Asset Decommissioning | 2024 ACE Plan (for Subsequent Approval) | OTQ - December 20, 2024 | 4650648.04 | 4915649 | 3772273.13
Approved | Generation | C0060816 | POT - HFO Tank Refurbishment | 2024 ACE Plan (for Subsequent Approval) | OTQ - December 17, 2024 | 2012802.82 | 3684622 | 3625065.15
Deferred | General Plant | C0061287 | IT - Third Party Risk Management | 2024 ACE Plan (for Subsequent Approval) |  | 1405970.41 |  | 0
Approved | General Plant | C0061289 | IT - Network Next Generation Security Design | 2024 ACE Plan (for Subsequent Approval) | OTQ - April 7, 2025 | 2632635 | 1814215.74 | 1647378.15
Approved | Distribution | C0061521 | New Distribution Rights-of-Way Phase 10 | 2024 ACE Plan (for Subsequent Approval) | OTQ - October 7, 2024 | 18904608 | 20890176 | 22516405.0804
Approved | Generation | C0038126 | HYD Cowie Falls Unit 12 Overhaul | 2024 ACE Plan (Less than $1M) | Q1 - May 13, 2024 | 964521.17 | 1274890 | 1271879.83
Approved | Generation | C0053655 | HYD Cowie Falls Unit 11 Overhaul | 2023 ACE Plan (Less than $1M) | Q1 - May 13, 2024 | 913947.02 | 1225491 | 1294063.14
Approved | Generation | C0059283 | LIN2 PE 2023/2024 Winter Capacity Requirements | U&U | Q1 - May 13, 2024 | 0 | 1661834 | 1663743.67
Approved | Transmission | C0062123 | 143H-Mount Uniacke Substation | P&A | Q2 - August 6, 2024 | 0 | 9040869 | 7973135.91
Approved | General Plant | C0056461 | IT - Contact Centre Cloud Migration | 2024 ACE Plan (for Subsequent Approval) | OTQ - September 16, 2024 | 929372 | 3237539 | 2423382.44
Approved | Transmission | C0031048 | 91H-T11 Transformer Replacement | 2025 ACE Plan | 2025 ACE Plan | 6914621.96 | 6914621.96 | 4763214.75
Approved | Generation | C0039266 | HYD - Gulch Overhaul | 2025 ACE Plan | 2025 ACE Plan | 1371379.09 | 1371379.09 | 771033.48
Approved | Generation | C0048990 | HYD AVO 2 Switchgear Replacement | 2025 ACE Plan | 2025 ACE Plan | 1814631.36 | 1814631.36 | 900321.76
Approved | Transmission | C0050834 | Spare EHV Breaker Replacements | 2025 ACE Plan | 2025 ACE Plan | 1178831.81 | 1178831.81 | 164.18
Approved | Transmission | C0050852 | 10V-T1 Transformer Replacement | 2025 ACE Plan | 2025 ACE Plan | 2113336.98 | 2113336.98 | 1620868.28
Awaiting Approval | General Plant | C0051815 | RTU Replacements Program Phase 6 | 2025 ACE Plan | 2025 ACE Plan | 5959915.27 | 5959915.27 | 1483595.86
Approved | Transmission | C0053295 | L5004 Kearney Lake Structure Replacement | 2025 ACE Plan | 2025 ACE Plan | 2478536.78 | 2478536.78 | 423938.55
Approved | Transmission | C0057682 | Spare Transformer Replacement | 2025 ACE Plan | 2025 ACE Plan | 2286389.47 | 2286389.47 | 2041602.45
Approved | Generation | C0068659 | TRE5 - IP-LP Turbine Refurbishment | 2025 ACE Plan | 2025 ACE Plan | 1282669.84 | 1282669.84 | 3452270.33
Approved | Distribution | C0068786 | 2025 Padmount Replacement Program | 2025 ACE Plan | 2025 ACE Plan | 1354219.4 | 1354219.4 | 940850
Approved | Generation | C0068882 | TUC1 Generator Refurbishment | 2025 ACE Plan | 2025 ACE Plan | 2124210.74 | 2124210.74 | 597129.59
Approved | Generation | C0068887 | TUC3 Turbine Valves Refurbishment | 2025 ACE Plan | 2025 ACE Plan | 1869103.9 | 1869103.9 | 2371442.86
Approved | Distribution | C0068952 | 2025 PCB Poletop Sampling and Replacement | 2025 ACE Plan | 2025 ACE Plan | 7158973.99 | 7158973.99 | 2316982.16
Approved | Distribution | C0068953 | 2025 PCB Light Replacement | 2025 ACE Plan | 2025 ACE Plan | 4225224.41 | 4225224.41 | 0
Approved | Distribution | C0068954 | 2025 PCB Downline Device Sampling and Replacement | 2025 ACE Plan | 2025 ACE Plan | 1716718.39 | 1716718.39 | 0
Approved | Transmission | C0068961 | 2025 PCB Substation Sampling and Replacement | 2025 ACE Plan | 2025 ACE Plan | 6650932.5 | 6650932.5 | 52461.55
Approved | Transmission | C0069227 | L6516 Replacements and Upgrades Phase 3 | 2025 ACE Plan | 2025 ACE Plan | 3104924.75 | 3104924.75 | 1784770.69
Approved | Transmission | C0069231 | L8002 Replacements and Upgrades Phase 1 | 2025 ACE Plan | 2025 ACE Plan | 3093175.63 | 3093175.63 | 2112868.24
Approved | Transmission | C0069232 | L6021 Replacements and Upgrades Phase 1 | 2025 ACE Plan | 2025 ACE Plan | 3253068.08 | 3253068.08 | 1536155
Deferred | Transmission | C0069238 | 2025/2026 Steel Tower Refurbishment | 2025 ACE Plan | 2025 ACE Plan | 2337250.27 | 2337250.27 | 0
Approved | General Plant | C0069270 | 2025 SCADA/EMS Upgrade | 2025 ACE Plan | 2025 ACE Plan | 1306288.06 | 1306288.06 | 342246.2
Approved | Transmission | C0070048 | L5027B Replacements and Upgrades Phase 1 | 2025 ACE Plan | 2025 ACE Plan | 2916727.9 | 2916727.9 | 194960.49
Approved | Distribution | C0070787 | 91W-411 Labelle Road Phase Extension | 2025 ACE Plan | 2025 ACE Plan | 1150615.99 | 1150615.99 | 0
Deferred | General Plant | C0070907 | MDR-8000 Microwave Radio Replacement | 2025 ACE Plan | 2025 ACE Plan | 1572477.91 | 1572477.91 | 0
Deferred | Generation | 48913 | HYD - Tusket Facility Refurbishment | 2025 ACE Plan (for Subsequent Approval) |  | 12972226.16 |  | 1088599.83
Deferred | Transmission | C0011358 | New Bridgewater Substation | 2025 ACE Plan (for Subsequent Approval) |  | 18173046.53 |  | 2257632.66
Approved | Transmission | C0021140 | New 138KV-25KV Substation Stellarton | 2025 ACE Plan (for Subsequent Approval) | Q1 - May 16, 2025 | 10511998.19 | 12960396 | 5909406.01
Approved | Transmission | C0041830 | Spare Power Production Unit Transformer | 2025 ACE Plan (for Subsequent Approval) | OTQ - April 7, 2025 | 1264622.46 | 1266552.19 | 1257331.4
Awaiting Approval | General Plant | C0053699 | Renewable to Retail Implementation | 2025 ACE Plan (for Subsequent Approval) | OTQ - December 1, 2025 | 5062652.18 | 5644468 | 4394231.96
Approved | Generation | C0059783 | HYD Upper Lake Falls 2 Overhaul | 2025 ACE Plan (for Subsequent Approval) | OTQ - September 9, 2025 | 1678152.72 | 1582014 | 60426.41
Approved | General Plant | C0061284 | IT - OT Cyber Security Control Implementation | 2025 ACE Plan (for Subsequent Approval) | OTQ - March 3, 2025 | 5459312.92 | 6826426 | 2206705.49
Approved | Generation | C0063803 | HYD AVO 2 Access Road Stabilization | 2025 ACE Plan (for Subsequent Approval) | OTQ - April 7, 2025 | 2406283.37 | 1862825.78 | 245420.96
Approved | Generation | C0067023 | LIN2 2024/25 Capacity Requirement | 2025 ACE Plan (for Subsequent Approval) | OTQ - June 9, 2025 | 1083800.37 | 1257127 | 1287091.21
Approved | Generation | C0068566 | LIN DCS Upgrade 2025 | 2025 ACE Plan (for Subsequent Approval) | Q1 - May 16, 2025 | 1440910.59 | 1544190 | 385358
Awaiting Approval | Generation | C0068655 | LM6000 191-332 Life Extension | 2025 ACE Plan (for Subsequent Approval) | Q2 - August 5, 2025 | 6013453.54 | 18948560 | 18991705.52
Pending Submission | Generation | C0069166 | POT-Turbine Valve Refurbishment | 2025 ACE Plan (for Subsequent Approval) |  | 2872597.56 |  | 0
Approved | Generation | C0070486 | HYD LGB Stoplog Replacement | 2025 ACE Plan (for Subsequent Approval) | OTQ - December 1, 2025 | 1288403.9 | 3593884 | 2761401.79
Approved | Distribution | C0071528 | FLISR Implementation | 2025 ACE Plan (for Subsequent Approval) | Q2 - August 5, 2025 | 5299247.73 | 4638245 | 100399.97
Approved | Generation | C0061003 | POA LP HP IP Turbine Refurbishment | 2025 ACE Plan (for Subsequent Approval) | OTQ - July 7, 2025 | 4155130.87 | 4861261 | 4825324
Approved | Generation | C0061005 | POA Cell Capping 2025 | 2025 ACE Plan (for Subsequent Approval) | OTQ - July 7, 2025 | 3255439.91 | 2530405 | 1963816.4
Approved | Generation | C0067906 | POA Boiler Refurbishment 2025 | 2025 ACE Plan (for Subsequent Approval) | OTQ - July 7, 2025 | 1213152.46 | 1218254 | 1200000
Approved | Generation | C0067908 | POA Boiler Refractory Refurbishment 2025 | 2025 ACE Plan (for Subsequent Approval) | OTQ - July 7, 2025 | 1089478.33 | 1378466 | 1400000
Approved | General Plant | C0011159 | Plant Information System Upgrade | 2024 ACE Plan (Less than $1M) | OTQ - March 3, 2025 | 362679 | 1142652 | 1008134.24
Approved | Distribution | C0042687 | 15N-202 Arthur St Conversion | 2022 ACE Plan (Less than $1M) | OTQ - April 7, 2025 | 718195 | 1399459 | 1194466.99
Approved | Generation | C0049192 | HYD - GUL Generator Refurbishment | 2025 ACE Plan (Less than $1M) | Q1 - May 16, 2025 | 732043 | 1316589 | 721661.32
Approved | Generation | C0068662 | TRE5 Baghouse Filter Replacement | 2025 ACE Plan (Less than $1M) | Q1 - May 16, 2025 | 534006 | 1241640 | 1321762.95
Approved | Generation | C0073348 | HYD - WRC Surge Lake Volume Optimization | U&U | Q1 - May 16, 2025 | 0 | 1736278 | 1001976.73
Approved | Generation | C0073965 | TRE5 U&U Burner Nest Waterwall Tube Replacement | U&U | Q1 - May 16, 2025 | 0 | 2156407 | 751048.07
Approved | General Plant | C0073777 | IT - Complex Customer Projects | P&A | OTQ - June 9, 2025 | 0 | 3025518 | 777184.35
Approved | General Plant | 49036 | HYD - Avon 2 Controls Upgrade | 2025 ACE Plan (Less than $1M) | Q2 - August 5, 2025 | 0 | 1073463 | 543264.75
Awaiting Approval | Generation | C0073491 | LM6000 191-443 Engine Replacement | P&A | Q2 - August 5, 2025 | 0 | 24217289 | 31344.56
Approved | Generation | C0067183 | TUC Wharf Access Bridge Replacement | U&U | Q2 - August 5, 2025 | 0 | 2426669 | 1745133.66
Approved | Transmission | C0074130 | Robie Street Underground | P&A | OTQ - September 9, 2025 | 0 | 4465119 | 115930.09
Approved | Generation | C0080112 | HYD Big Falls Unit 6 Rotor Re-Insulation | U&U | OTQ - October 10, 2025 | 0 | 1025626 | 335499.86
Approved | General Plant | C0053696 | ECC Wind Integration | 2025 ACE Plan (Less than $1M) | OTQ - December 1, 2025 | 757358 | 4428335 | 94081.12
Approved | Generation | C0080228 | HYD HOB Stator Rewind and Generator Refurbishment | U&U | OTQ - December 1,2025 | 0 | 2587170 | 342267.26
Awaiting Approval | Generation | C0021608 | TUC Shoreline Sheetpile Refurbishment | 2026 ACE Plan | 2026 ACE Plan | 5691466 | 5691466 | 280131.21
Awaiting Approval | Transmission | C0053214 | 76W-T1 Transformer Replacement | 2026 ACE Plan | 2026 ACE Plan | 2818855 | 2818855 | 2077282.59
Awaiting Approval | Transmission | C0053234 | 96H-T1 Transformer Replacement | 2026 ACE Plan | 2026 ACE Plan | 2056752 | 2056752 | 37090.59
Awaiting Approval | Generation | C0068888 | TUC3 Continuous Ash Hauling System | 2026 ACE Plan | 2026 ACE Plan | 1359984 | 1359984 | 30190.41
Awaiting Approval | Generation | C0068898 | TUC1 IP LP Last Stage Blade Replacement | 2026 ACE Plan | 2026 ACE Plan | 5215861 | 5215861 | 3490876.62
Awaiting Approval | Transmission | C0068969 | 2026 Pennsylvania Breaker Replacements | 2026 ACE Plan | 2026 ACE Plan | 1620028 | 1620028 | 37661.61
Awaiting Approval | Transmission | C0070586 | L6536 Switch Replacements | 2026 ACE Plan | 2026 ACE Plan | 2074494 | 2074494 | 94309.19
Awaiting Approval | Transmission | C0070909 | 70W-T52 Transformer Addition | 2026 ACE Plan | 2026 ACE Plan | 3957128 | 3957128 | 14852.34
Awaiting Approval | Distribution | C0080104 | 36V-303 Baxter's Harbour Rd Reconductor Phase 1 | 2026 ACE Plan | 2026 ACE Plan | 1062416 | 1062416 | 0
Awaiting Approval | Transmission | C0080109 | L7001 Replacements and Upgrades Phase 1 | 2026 ACE Plan | 2026 ACE Plan | 3063280 | 3063280 | 0
Awaiting Approval | Transmission | C0080110 | L7012 Replacements and Upgrades Phase 1 | 2026 ACE Plan | 2026 ACE Plan | 5370318 | 5370318 | 0
Awaiting Approval | General Plant | C0080111 | 2026 RTU Deployment | 2026 ACE Plan | 2026 ACE Plan | 8322655 | 8322655 | 0
Awaiting Approval | Generation | C0080133 | TUC3 IP Turbine Refurbishment | 2026 ACE Plan | 2026 ACE Plan | 2588734 | 2588734 | 0
Awaiting Approval | Generation | C0080134 | TUC2 Stack Coating and Structural Refurbishment | 2026 ACE Plan | 2026 ACE Plan | 4256511 | 4256511 | 0
Awaiting Approval | Generation | C0080135 | CT - BGT2 Engine Refurbishment | 2026 ACE Plan | 2026 ACE Plan | 2462664 | 2462664 | 0
Awaiting Approval | Generation | C0080205 | POA Boiler Refractory Replacement 2026 | 2026 ACE Plan | 2026 ACE Plan | 1024385 | 1024385 | 0
Awaiting Approval | Generation | C0080206 | POA Boiler Refurbishment 2026 | 2026 ACE Plan | 2026 ACE Plan | 1304600 | 1304600 | 0
Awaiting Approval | General Plant | C0080252 | Intelligent Asset Data Capture & Integration Platform | 2026 ACE Plan | 2026 ACE Plan | 267941 | 267941 | 121790
Awaiting Approval | Distribution | C0080266 | New Distribution Right of Way Phase 11 | 2026 ACE Plan | 2026 ACE Plan | 20889694 | 20889694 | 0
Awaiting Approval | Distribution | C0080612 | 57C-426H Melrose Reconductor and Line Extension Phase 1 | 2026 ACE Plan | 2026 ACE Plan | 1288474 | 1288474 | 0
Pending Submission | Generation | 47649 | HYD Salmontail Gate Pedestal and Main Dam Refurbishment | 2026 ACE Plan (for Subsequent Approval) |  | 5870708 |  | 692838.89
Pending Submission | Generation | 47650 | HYD - Annapolis Decision Analysis | 2026 ACE Plan (for Subsequent Approval) |  | 30732442 |  | 3060381.06
Pending Submission | Generation | 49595 | HYD - TUS 1 Overhaul | 2026 ACE Plan (for Subsequent Approval) |  | 5649954 |  | 373649.84
Pending Submission | Transmission | 51098 | L-6014 Shannon Park Transmission Towers | 2026 ACE Plan (for Subsequent Approval) |  | 39471723 |  | 1433680.64
Pending Submission | General Plant | C0000017 | Storm Management Software Implementation | 2026 ACE Plan (for Subsequent Approval) |  | 2235914 |  | 0
Pending Submission | General Plant | C0021835 | IT - CIS Replacement | 2026 ACE Plan (for Subsequent Approval) |  | 84502844 |  | 3418027.96
Pending Submission | Transmission | C0022247 | 1N Onslow Transformer Addition (1N-T66) | 2026 ACE Plan (for Subsequent Approval) |  | 3645131 |  | 2403846.14
Pending Submission | Transmission | C0023802 | L-6515 Canso Causeway Rebuild | 2026 ACE Plan (for Subsequent Approval) |  | 3925352 |  | 417727.86
Pending Submission | General Plant | C0032202 | Sydney Depot Improvements | 2026 ACE Plan (for Subsequent Approval) |  | 2700000 |  | 0
Pending Submission | Transmission | C0032382 | 142H - Susie Lake Substation | 2026 ACE Plan (for Subsequent Approval) |  | 8256386 |  | 3313075.85
Pending Submission | General Plant | C0047278 | IT - Oracle MDM Upgrade | 2026 ACE Plan (for Subsequent Approval) |  | 7949409 |  | 2862698.11
Pending Submission | General Plant | C0047301 | IT - Cloud Integration Platform | 2026 ACE Plan (for Subsequent Approval) |  | 2004962 |  | 180029.87
Pending Submission | Generation | C0047973 | HYD ANN Sluice Gates and Check Refurbishment | 2026 ACE Plan (for Subsequent Approval) |  | 5673491 |  | 218466.63
Pending Submission | Generation | C0052514 | HYD MacDonald Dam Access Improvements | 2026 ACE Plan (for Subsequent Approval) |  | 1547398 |  | 139849.58
Pending Submission | Generation | C0057361 | HYD ANN Facility Isolation | 2026 ACE Plan (for Subsequent Approval) |  | 4083925 |  | 3134767.32
Awaiting Approval | Transmission | C0059483 | 83V L-5017 and L-5046 Rebuild Tap | 2026 ACE Plan (for Subsequent Approval) | Q4 - February 26, 2026 | 1207318 | 1558116 | 231432.85
Pending Submission | Transmission | C0061552 | L-6043 Replacements and Upgrades | 2026 ACE Plan (for Subsequent Approval) |  | 2457629 |  | 0
Pending Submission | General Plant | C0062043 | IT - SharePoint Technical Migration | 2026 ACE Plan (for Subsequent Approval) |  | 3134674 |  | 1126739.73
Pending Submission | Generation | C0064966 | Tusket Powerhouse Tidal Pool Fish Passage | 2026 ACE Plan (for Subsequent Approval) |  | 1315495 |  | 561285.69
Pending Submission | Generation | C0067686 | HYD Lumsden Rubber Dam Replacement | 2026 ACE Plan (for Subsequent Approval) |  | 1304068 |  | 93015.81
Pending Submission | General Plant | C0067863 | IT - Managed Detect & Respond | 2026 ACE Plan (for Subsequent Approval) |  | 2585071 |  | 803216.42
Pending Submission | General Plant | C0068714 | IT - Identity & Access Management | 2026 ACE Plan (for Subsequent Approval) |  | 4324589 |  | 2478826.37
Pending Submission | General Plant | C0068718 | IT - DERMS Solution Project | 2026 ACE Plan (for Subsequent Approval) |  | 2954002 |  | 117703.94
Pending Submission | General Plant | C0068719 | IT - Distributed Intelligence Apps | 2026 ACE Plan (for Subsequent Approval) |  | 2637356 |  | 23203.46
Pending Submission | General Plant | C0068721 | IT - ADMS Upgrade 2026 | 2026 ACE Plan (for Subsequent Approval) |  | 7200000 |  | 0
Pending Submission | Transmission | C0069534 | IR 669 Network Upgrade Higgins Mountain Wind | 2026 ACE Plan (for Subsequent Approval) |  | 9496174 |  | -0.81
Pending Submission | Transmission | C0070086 | 10H-T2 Transformer Replacement | 2026 ACE Plan (for Subsequent Approval) |  | 2878891 |  | 24359.59
Pending Submission | Transmission | C0070327 | IR 673 Network Upgrade Benjamins Mill Wind | 2026 ACE Plan (for Subsequent Approval) |  | 265000 |  | -696.44
Pending Submission | Transmission | C0070367 | IR 618 Network Upgrade Goose Harbour Lake Wind | 2026 ACE Plan (for Subsequent Approval) |  | 11015684 |  | -0.02
Pending Submission | Transmission | C0071888 | New Tidewater Substation | 2026 ACE Plan (for Subsequent Approval) |  | 4141223 |  | 188052.92
Pending Submission | Transmission | C0071889 | 77V-T1 Transformer Replacement | 2026 ACE Plan (for Subsequent Approval) |  | 3486796 |  | 10571.02
Pending Submission | Transmission | C0072808 | ECEI Synchronous Condensers | 2026 ACE Plan (for Subsequent Approval) |  | 364566804 |  | 712013.22
Pending Submission | Generation | C0073368 | HYD Malay Falls Rubber Dam | 2026 ACE Plan (for Subsequent Approval) |  | 2237339 |  | 73488.69
Pending Submission | Generation | C0076273 | Bear Head Ash Management Site - Life Extension | 2026 ACE Plan (for Subsequent Approval) |  | 10148108 |  | 151655.03
Pending Submission | Generation | C0076672 | ICP - RC SCR Bridge 10.10 Refurbishment | 2026 ACE Plan (for Subsequent Approval) |  | 1353592 |  | 0
Pending Submission | Distribution | C0080101 | 539N-210 Big Island Sub-Sea Cable Replacement | 2026 ACE Plan (for Subsequent Approval) |  | 3539067 |  | 0
Pending Submission | Distribution | C0080102 | 92H-331 Double Circuit Peggys Cove Rd | 2026 ACE Plan (for Subsequent Approval) |  | 1882573 |  | 0
Pending Submission | Transmission | C0080107 | L-5532 Reliability Upgrade - 91W Middle Field Substation | 2026 ACE Plan (for Subsequent Approval) |  | 3053526 |  | 0
Pending Submission | Transmission | C0080108 | L-5532 Replacements and Upgrades Phase 1 | 2026 ACE Plan (for Subsequent Approval) |  | 2490532 |  | 0
Pending Submission | Generation | C0080219 | HYD Deep Brook Spillway & Intake Refurbishment | 2026 ACE Plan (for Subsequent Approval) |  | 3142201 |  | 39419.72
Pending Submission | Generation | C0080671 | LIN1 HIP Turbine Refurbishment 2026 | 2026 ACE Plan (for Subsequent Approval) |  | 3244992 |  | 0
Pending Submission | Generation | C0080691 | LIN3 DCS Migration 2026 | 2026 ACE Plan (for Subsequent Approval) |  | 1359218 |  | 0
Pending Submission | Generation | C0080732 | POA Ash Cell Capping/ Cell Development 2026 | 2026 ACE Plan (for Subsequent Approval) |  | 2420358 |  | 0
Pending Submission | Generation | C0080768 | POT - CW Pump & Motor Replacement | 2026 ACE Plan (for Subsequent Approval) |  | 2872183 |  | 0
Pending Submission | Transmission | C0081985 | Michelin DVR Phase 2 | 2026 ACE Plan (for Subsequent Approval) |  | 13000000 |  | 3037041.52
Pending Submission | General Plant | C0082133 | IT - Renew Microsoft Enterprise Agreement | 2026 ACE Plan (for Subsequent Approval) |  | 1800000 |  | 0
Pending Submission | Generation | C0082195 | LIN2 2025/26 Capacity Requirement | 2026 ACE Plan (for Subsequent Approval) |  | 3162203 |  | 0
* Maritime Link Transmission capital work orders were filed as part of the Company's General Rate Application. They were not approved at the time of report issuance.

## R3 - Deferred or Cancelled
NS Power 2025 ACE Plan Items – Deferred or Cancelled
4th Quarter Overview - as of December 31, 2025
This report includes any deferred or cancelled projects that were included in the 2025 ACE Plan.
CI | Project Title | 2025 ACE Amount | 2025 ACE Project Total | Cancelled / Deferred | Deferred To | Prior Approval | 2025 ACE Plan Reference | Commentary
Generation
48913 | HYD - Tusket Facility Refurbishment | 1093904 | 12972226 | Deferred | 2027 |  | Subsequent Submittal | As condition assessments related to the Powerhouse continue, it has been determined that additional engineering is required to prepare the capital filing. Curent assessment indicates that this can safety be deferred to 2027.
C0020329 | TRE5 Stack Expansion Joint Repl | 362991 | 395291 | Deferred | 2026 |  | Less than $1M | Through further scoping it was determined the risk could be mitigated in 2025 with additional monitoring and detection.
C0020331 | TRE5 Air Heater Expansion Joint Replacement | 354575 | 385222 | Deferred | 2026 |  | Less than $1M | Through further scoping it was determined the risk could be mitigated in 2025 with additional monitoring and detection.
C0061366 | TRE6 - Caustic Heater Heat Exchanger | 84017 | 91767 | Cancelled |  |  | Less than $1M | This project has been cancelled. Leak test on existing heat exchange bundle and gasket replacements mitigated risk and need for project.
C0068660 | TRE5 - Boiler Refurbishment 2025 | 825182 | 896932 | Cancelled |  |  | Less than $1M | This project has been cancelled as the scope of work will not be completed under C0073965 TRE5 U&U Burner Nest Waterwall Tube Replacement
C0030122 | LIN4 HIP Insulation Replacement | 106894 | 126234 | Deferred | 2026 |  | Less than $1M | Additional scoping found the condition of the insulation allows for this project to be deferred to 2026.
C0067945 | POA Pond Transfer Pumps | 367194 | 417194 | Cancelled |  |  | Pt. Aconi | This project has been cancelled, as updated condition assessment revealed the risk does not need immediate mitigation.
C0060572 | TUC1 Secondary Air & Recirc Damper Replacement | 77424 | 77424 | Cancelled |  |  | Less than $1M | This project has been cancelled, as the risk can be managed through 2026 and will also be completed as part of a major boiler upgrade on TUC1 which will begin in 2027.
C0068894 | TUC1 Gas Block Valve Upgrades | 607737 | 607737 | Cancelled |  |  | Less than $1M | This project has been cancelled, as the risk can be managed through 2026 and will also be completed as part of a major boiler upgrade on TUC1 which will begin in 2027.
C0069047 | TUC2 FD Fan Duct Refurbishment | 99940 | 99940 | Cancelled |  |  | Less than $1M | This project has been cancelled, as updated condition assessment revealed the risk does not need immediate mitigation.
C0069567 | TUC1 - Boiler Cyclone Tube Replacem | 859647 | 859647 | Cancelled |  |  | Less than $1M | This project has been cancelled, as the risk can be managed through 2026 and will also be completed as part of a major boiler upgrade on TUC1 which will begin in 2027.
C0068303 | LIN Wastewater Lagoon Algae Control 2025 | 102074 | 111164 | Cancelled |  |  | Less than $1M | Monitoring has shown that recent algae levels are being managed through current risk mitigation practices.
C0068236 | LIN4 North Water Wall Replacement 2025 | 446612 | 526275 | Deferred | 2026 |  | Less than $1M | This project is being deferred to the 2026 outage. The existing approach to management of this asset is expected to address near-term risks.
C0068228 | LIN3 Air Preheater Seal Refurbishment 2025 | 102249 | 110788 | Deferred | 2026 |  | Less than $1M | As part of an updated condition assessment during this year's planned outage, the condiiton of the air preheater seals allows for this project to be deferred to 2026.
40023 | TRE - Sewage Lift Station Upgrades | 158493 | 158493 | Cancelled |  |  | Less than $1M | This project has been cancelled, as updated condition assessment revealed the risk does not need immediate mitigation.
C0020367 | TRE5 Main Oil Pump & Gearbox Refurbishment | 195312 | 212312 | Deferred | 2026 |  | Less than $1M | This project is being deferred to 2026 outage. The existing approach to management of this asset is expected to address near-term risks.
C0061363 | TRE5 - Screenwash Pump Replacement | 129989 | 151107 | Deferred | 2026 |  | Less than $1M | Updated condition assessment determined the condition of the asset allows the project to be deferred to 2026.
C0068624 | TRE - Overhead / Person Door Refurbishments | 92756 | 100556 | Cancelled |  |  | Less than $1M | This project is cancelled as the necessary scope to mitigate these risks will be completed through CI C0061356 TRE Overhead/Person Door Refurbishments
C0068627 | TRE - Rotating Equipment Guards 2025 | 131614 | 143314 | Cancelled |  |  | Less than $1M | This project has been cancelled, as further scoping revealed the risk can be managed without need for proactive replacement.
C0068658 | TRE6 - Battery Charger Replacement | 80589 | 87789 | Deferred | 2026 |  | Less than $1M | Further scoping determined the condition of the asset allows the project to be deferred to 2026.
C0068675 | TRE6 Parallel Slide HP heater isolations | 494861 | 540411 | Deferred | 2026 |  | Less than $1M | Deferred due to U&U capital work utilizing available resources. The existing approach to management of this asset is expected to address near-term risks.
C0068691 | TRE6 - Boiler Main Stop Valve | 148839 | 162539 | Deferred | 2026 |  | Less than $1M | Deferred due to U&U capital work utilizing available resources. The existing approach to management of this asset is expected to address near-term risks.
C0068692 | TRE6 - 6A BFP Discharge Valve Refurbishment | 149279 | 159779 | Deferred | 2026 |  | Less than $1M | Deferred due to U&U capital work utilizing available resources. The existing approach to management of this asset is expected to address near-term risks.
C0068693 | TRE6 Instrument Air Dry Replacement | 81210 | 88310 | Deferred | 2026 |  | Less than $1M | Deferred due to U&U capital work utilizing available resources. The existing approach to management of this asset is expected to address near-term risks.
C0070850 | TRE Shaker House Hoist Replacement | 83854 | 91354 | Deferred | 2026 |  | Less than $1M | Deferred to better define project scope. The exisiting approach to management of this asset is expected to address near-term risks.
C0060610 | TUC Cable Spreading Rm Fire Prot | 250108 | 250108 | Cancelled |  |  | Less than $1M | This project has been cancelled. Project scope will be completed as part of CI C0069829 TUC - Relay Room Fire Suppression System.
C0068906 | TUC6 Boiler Feed Pump Refurb 2025 | 302097 | 302097 | Deferred | 2026 |  | Less than $1M | This project is deferred until the 2026 TUC6 outage. The existing approach to management of this asset is expected to address near-term risks.
C0057361 | HYD - ANN Facility Isolation | 210689 | 2899094 | Deferred | 2026 |  | Subsequent Submittal | Deferred to better define project scope. The exisiting approach to management of this asset is expected to address near-term risks.
C0051932 | HYD - Avon 2 Penstock Recoating | 152346 | 688897 | Deferred | 2027 |  | Less than $1M | Deferred due to reprioritization. The existing approach to management of this asset is expected to address near-term risks.
C0067383 | HYD HMS Electrical Replacement | 135290 | 156003 | Cancelled |  |  | Less than $1M | This project has been cancelled as further scoping needed before proceeding, and near-term risks being managed by current asset management approach.
C0068703 | HYD COW Battery Bank Replacement | 78187 | 90747 | Deferred | 2027 |  | Less than $1M | Deferred due to reprioritization. The existing approach to asset management of this asset is expected to address near-term risks.
C0039046 | LIN Ash Silo Refurbishment 2024 | 197599 | 214456 | Cancelled |  |  | Less than $1M | This project has been cancelled, as updated condition assessment revealed the risk does not need immediate mitigation.
C0061340 | LIN12 Diesel Generator Room Refurbishment | 336843 | 365589 | Cancelled |  |  | Less than $1M | This project has been cancelled, as updated condition assessment revealed the risk does not need immediate mitigation.
C0068144 | LIN Coal Amenities Trailer Replacement | 302813 | 331363 | Cancelled |  |  | Less than $1M | This project has been cancelled, as updated condition assessment revealed the risk does not need immediate mitigation.
C0068150 | LIN Coal Stacker Refurbishment 2025 | 135428 | 147338 | Cancelled |  |  | Less than $1M | This project has been cancelled, as updated condition assessment revealed the risk does not need immediate mitigation.
C0068184 | LIN HFO/LFO Line Refurbishment 2025 | 195187 | 212427 | Cancelled |  |  | Less than $1M | This project has been cancelled. Project scope will be completed as part of CI C0060819 LIN HFO/LFO Line Refurbishment 2024.
C0068186 | LIN Kubota Replacement 2025 | 36674 | 43972 | Cancelled |  |  | Less than $1M | Cancelled due to U&U capital work utilizing available resources. Kubota will not be replaced.
C0068226 | LIN1 SoER Installation 2025 | 227364 | 246717 | Cancelled |  |  | Less than $1M | Cancelled due to U&U capital work utilizing available resources. The exisiting approach is sufficient to address near-term risks.
C0052536 | POA Demin Tank Heater | 86963 | 98963 | Cancelled |  |  | Pt. Aconi | Cancelled due to U&U capital work utilizing available resources. The exisiting approach is sufficient to address near-term risks.
C0068039 | POA Sootblower Refurb 2025 | 102854 | 117854 | Deferred | 2027 |  | Pt. Aconi | Deferred due to U&U capital work utilizing available resources. The existing approach to management of this asset is expected to address near-term risks.
C0068687 | TRE6 "A" and "B" CW Screens Refurb | 177892 | 192892 | Deferred | 2026 |  | Less than $1M | Deferred due to U&U capital work utilizing available resources. The existing approach to management of this asset is expected to address near-term risks.
C0059533 | WIN - DIG WTG#9 Gearbox Replacement | 716489 | 761741 | Deferred | 2026 |  | Less than $1M | Deferred due to reprioritization. The existing approach to asset management of this asset is expected to address near-term risks.
C0059602 | WIN - DIG WTG#10 Gearbox Replacement | 714917 | 782510 | Deferred | 2026 |  | Less than $1M | Deferred due to reprioritization. The existing approach to asset management of this asset is expected to address near-term risks.
C0068253 | LIN1 Analytical Rack Refurbishment 2025 | 62077 | 72289 | Cancelled |  |  | Less than $1M | This project has been cancelled as a smaller repair was sufficient to mitigate the risk with no capital investment necessary.
C0068205 | LIN WTP A Polisher Resin Replacement 2025 | 75899 | 85274 | Cancelled |  |  | Less than $1M | This project has been cancelled, as further condition assessment revealed the risk can be managed without need for proactive replacement.
C0068622 | LIN E Belt Metal Detector Install 2025 | 140033 | 152166 | Deferred | 2027 |  | Less than $1M | Deferred due to U&U capital work utilizing available resources. The exisiting approach is sufficient to address near-term risks.
C0068163 | LIN Coal Wash Down Line Replacement | 153953 | 166566 | Deferred | 2027 |  | Less than $1M | Deferred due to U&U capital work utilizing available resources. The exisiting approach is sufficient to address near-term risks.
C0068167 | LIN Fly Ash Hopper Vibrator Replacement 2025 | 263705 | 288107 | Deferred | 2027 |  | Less than $1M | Deferred as further condition assessment indicated this risk could be managed until the 2027 outage window.
C0068143 | LIN BFP Recirc Line Replacement 2025 | 277892 | 302521 | Cancelled |  |  | Less than $1M | Cancelled due to U&U capital work utilizing available resources. The exisiting approach is sufficient to address near-term risks.
C0068206 | LIN1 Boiler Erosion Reduction System 2025 | 299820 | 353599 | Deferred | 2027 |  | Less than $1M | LIN1 outage was condensed to meet shorter outage window. The exisiting approach is sufficient to address near-term risks.
C0068225 | LIN1 RH1 Boiler Tube Replacement 2025 | 409412 | 481590 | Deferred | 2027 |  | Less than $1M | LIN1 outage was condensed to meet shorter outage window. The exisiting approach is sufficient to address near-term risks.
C0068223 | LIN1 Burner Front Replacement 2025 | 427031 | 484919 | Deferred | 2027 |  | Less than $1M | LIN1 outage was condensed to meet shorter outage window. The exisiting approach is sufficient to address near-term risks.
C0064304 | HYD WRC Gallery Tailrace Hoist | 195735 | 228259 | Deferred | 2027 |  | Less than $1M | Deferred due to U&U capital work utilizing available resources. The exisiting approach is sufficient to address near-term risks.
C0027882 | HYD WRC Fire Protection Partial Replacement | 215725 | 251107 | Deferred | 2026 |  | Less than $1M | Deferred due to timing of ongoing LEM and Tailrace work impacting access to tunnel. The existing approach is sfficient to address near-term risks
C0042327 | HYD WRC Oil Containment Shed | 445890 | 516712 | Cancelled |  |  | Less than $1M | Cancelled as a less costly solution was found to mitigate the risk that did not require a separate capital project.
C0069432 | TRE0 Grease Pump Replacement | 79815 | 87465 | Deferred | 2026 |  | Less than $1M | Deferred due to Materials delay. The existing approach is sufficient to address near-term risks.
C0061331 | TRE0 - 6A Service Air Compressor Replacement | 99684 | 108684 | Deferred | 2026 |  | Less than $1M | Deferred due to Materials delay. The existing approach is sufficient to address near-term risks.
C0069077 | TUC WWTP Sludge Level Probe | 48742 | 48742 | Cancelled |  |  | Less than $1M | Cancelled as this was completed under another related WWTP project C0060552 TUC Condensate Recovery.
C0069079 | TUC3 Polisher Resin Replacement | 49013 | 49013 | Cancelled |  |  | Less than $1M | Cancelled as this is a duplicate project. Scope captured under C0069014 TUC3 EW Polished Resin Replacement 2025.
C0060560 | TUC Cooling Water Reduction | 49297 | 49297 | Deferred | 2026 |  | Less than $1M | Deferred to better define project scope. The exisiting approach to management of this asset is expected to address near-term risks.
C0069052 | TUC WTP4 PLC Upgrade | 75503 | 75503 | Deferred | 2026 |  | Less than $1M | Deferred due to U&U capital work utilizing available resources. The exisiting approach is sufficient to address near-term risks.
C0069055 | TUC Plant Security Upgrades 2025 | 76751 | 76751 | Cancelled |  |  | Less than $1M | Cancelled due to Materials delay. The existing approach is sufficient to address near-term risks.
C0069050 | TUC EST3 Fire Panel Replacement | 81096 | 81096 | Deferred | 2026 |  | Less than $1M | Deferred due to Materials delay. The existing approach is sufficient to address near-term risks.
C0069033 | TUC Oil Water Separator Replace | 98471 | 98471 | Cancelled |  |  | Less than $1M | Updated condition assessment and further scoping determined mitigation was no longer needed.
C0069032 | TUC WWTP EQ Ventilation Upgrades | 99004 | 99004 | Cancelled |  |  | Less than $1M | Updated condition assessment and further scoping determined mitigation was no longer needed.
C0069020 | TUC3 DCS HMI Upgrade 2025 | 147122 | 147122 | Cancelled |  |  | Less than $1M | Cancelled due to reprioritization. The existing approach to asset management of this asset is expected to address near-term risks.
C0069012 | TUC Stack Lighting 2025 | 147898 | 147898 | Deferred | 2026 |  | Less than $1M | Deferred due to ongoing work in the stacks. The existing approach to asset management of this asset is expected to address near-term risks.
C0069015 | TUC1 DCS HMI Upgrade 2025 | 152049 | 152049 | Cancelled |  |  | Less than $1M | Cancelled due to reprioritization. The existing approach to asset management of this asset is expected to address near-term risks.
C0069011 | TUC - DCS / HMI Network 2025 | 153077 | 153077 | Cancelled |  |  | Less than $1M | Cancelled due to reprioritization. The existing approach to asset management of this asset is expected to address near-term risks.
C0060563 | TUC1 Steam Drum Refurb 2024 | 204859 | 204859 | Deferred | 2026 |  | Less than $1M | This project is being deferred to 2026 outage. The existing approach to management of this asset is expected to address near-term risks.
C0068901 | TUC1 CW Pump Refurb 2025 | 346353 | 346353 | Deferred | 2026 |  | Less than $1M | Deferred due to reprioritization. The existing approach to asset management of this asset is expected to address near-term risks.
51841 | TUC1 Turbine Generator Fire Suppression System | 346638 | 346638 | Deferred | 2026 |  | Less than $1M | Deferred due to Materials delay. The existing approach is sufficient to address near-term risks.
C0068898 | TUC1 IP LP Last Stage Blade Replace | 501860 | 501860 | Deferred | 2026 |  | Less than $1M | Deferred as further scoping revealed that scope is larger than anticipated. Awaiting blade manufacturing and longer outage window to execute project. The existing approach to asset management of this asset is expected to address near-term risks.
C0068930 | PHB - Wennberg Screw Replacement | 562602 | 562602 | Deferred | 2026 |  | Less than $1M | Deferred due to Materials delay. The existing approach is sufficient to address near-term risks.
C0026082 | HYD - NIC Mid Life Refurbishment | 191306 | 191306 | Deferred | 2027 |  | Less than $1M | Deferred due to reprioritization. The existing approach to asset management of this asset is expected to address near-term risks.
C0038876 | HYD - HMS Veritcal Boring Mill Repl | 454412 | 544412 | Deferred | 2026 |  | Less than $1M | Deferred due to U&U capital work utilizing available resources. The exisiting approach is sufficient to address near-term risks.
C0068869 | LM6000 Gas Cooler Structure Refurb | 491479 | 491479 | Deferred | 2026 |  | Less than $1M | Additional scoping found the condition allows for this project to be safely deferred to 2026.
C0067783 | ICP - RC Locomotive Refurb 2025 | 224448 | 224448 | Deferred | 2026 |  | Less than $1M | Deferred due to reprioritization. The existing approach to asset management of this asset is expected to address near-term risks.
C0068875 | CT Fleet Stack Condition Assessment | 100412 | 100412 | Deferred | 2026 |  | Less than $1M | Deferred due to reprioritization. The existing approach to asset management of this asset is expected to address near-term risks.
C0069587 | CT - BGT4 Inverter Replacement | 52903 | 52903 | Deferred | 2026 |  | Less than $1M | Deferred due to Materials delay. The existing approach is sufficient to address near-term risks.
C0038134 | HYD - LUM Crane Replacement | 251353 | 299165 | Deferred | 2026 |  | Less than $1M | Deferred due to U&U capital work utilizing available resources. The exisiting approach is sufficient to address near-term risks.
C0068043 | POA Fire System Upgrade 2025 | 80014 | 90014 | Cancelled |  |  | Pt. Aconi | Cancelled as no fire system upgrades were identified for 2025 based on the insurance audit.
Transmission
C0041822 | WRC Spare Cable Replacement & Storage System | 50000 | 189342 | Deferred | 2027 |  | Less than $1M | Additional engineering is required before project can progress to construction.
C0011358 | New Bridgewater Substation | 1385538 | 18173047 | Deferred | 2027 |  | Subsequent Submittal | Additional engineering is required before project can progress to construction.
C0032382 | Susie Lake Substation Addition | 5149415 | 13954518 | Deferred | 2026 |  | Subsequent Submittal | Additional engineering is required before project can progress to construction and delays with land procurement.
C0053214 | 76W-T1 Transformer Replacement | 1938848 | 2279295 | Deferred | 2026 |  | Subsequent Submittal | Project now forecasted for 2026 ACE request approval. Project had been deferred as additional engineering was required before project could progress to construction.
C0072808 | Synchronous Condensers (ECEI) | 27197774 | 243807241 | Deferred | 2026 |  | Subsequent Submittal | Project now forecasted for filing in 2026, as preliminary engineering and planning work continues throughout 2025 and is required prior to submission.
C0061552 | L6043 Replacements and Upgrades | 796677 | 1346809 | Deferred | 2027 |  | Subsequent Submittal | Deferred to better define project scope.
C0069238 | 2025/2026 Steel Tower Refurbishment | 715698 | 2337250 | Cancelled | 2027 |  | Request Approval | Cancelled as work will be completed under the new Routine T030, outlined in the 2026 ACE Plan.
C0060003 | AMO 85S Thermal Camera Upgrade | 74885 | 74885 | Deferred | 2026 |  | Less than $1M | Deferred to better define project scope.
Distribution
C0071410 | 25W-301 Welshtown Phase Addition | 322774 | 594945 | Deferred | 2026 |  | Less than $1M | Deferred due to reprioritization of projects in the West. The existing approach to asset management of this asset is expected to address near-term risks.
C0068956 | 2025 PCB Program - Reclosers | 82553 | 797250 | Deferred | 2026 |  | Less than $1M | An extension on the removal of PCBs was granted to allow for continued removal beyond 2025.
C0070509 | 2025 Feeder Exit Replacements | 109639 | 109639 | Deferred | 2026 |  | Less than $1M | Deferred due to Materials delay. The existing approach is sufficient to address near-term risks.
C0070508 | 2025 Manhole Automatic Pumps | 150938 | 150938 | Deferred | 2026 |  | Less than $1M | Deferred due to pumps being delayed. The existing approach is sufficient to address near-term risks.
C0070506 | 2025 Vault Replacement | 382690 | 414376 | Deferred | 2026 |  | Less than $1M | Deferred due to Materials delay. The existing approach is sufficient to address near-term risks.
C0068789 | 2025 1H-403 Targeted Underground Device Replacements | 458350 | 458350 | Deferred | 2026 |  | Less than $1M | Deferred due to reprioritization. The existing approach to asset management of this asset is expected to address near-term risks.
C0043930 | 1H-419 Targeted Underground Device Replacements | 599382 | 635382 | Deferred | 2026 |  | Less than $1M | Deferred due to waiting on decision from the municipality about HRM Ferry project as it could impact this project.
C0068955 | 2025 PCB Program - Underground Assets | 780075 | 856950 | Deferred | 2026 |  | Less than $1M | An extension on the removal of PCBs was granted to allow for continued removal beyond 2025.
C0071990 | 2025 Step Down Transformer Capital Spares | 255326 | 255326 | Deferred | 2026 |  | Less than $1M | Deferred due to Materials delay.
General Plant
C0071652 | IT - ZTN Security and Restrictive Network Controls | 725124 | 869124 | Cancelled |  |  | Less than $1M | Scope of this project included in C0061289 - IT - Network Next Generation Security Design.
C0032202 | Sydney T&D Depot Consolidation | 1578174 | 1879855 | Deferred | 2026 |  | Subsequent Submittal | Deferred to better define project scope.
C0021835 | IT - CIS Replacement | 2243592 | 77890771 | Deferred | 2026 |  | Subsequent Submittal | This project is delayed due to the cyber event. Resources were required for priority restoration.
C0047278 | IT - Oracle MDM Upgrade | 912789 | 3010689 | Deferred | 2026 |  | Subsequent Submittal | This project is delayed due to the cyber event. Resources were required for priority restoration.
C0061285 | IT - Enterprise Governance, Risk, and Compliance | 664056 | 1179857 | Deferred | 2026 |  | Subsequent Submittal | This project is delayed due to the cyber event. Resources were required for priority restoration.
C0061347 | IT - Wireless Video Solution | 56424 | 72924 | Deferred | 2026 |  | Less than $1M | This project is delayed due to the cyber event. Resources were required for priority restoration.
C0068719 | IT - Distributed Intelligence Apps | 2086440 | 4353461 | Deferred | 2026 |  | Subsequent Submittal | This project is delayed due to the cyber event. Resources were required for priority restoration.
C0068718 | IT - DERMS Solution Project | 1950047 | 2993200 | Deferred | 2026 |  | Subsequent Submittal | Deferred to better define project scope through the Distributed Energy Resource Integration Roadmap.
C0068714 | IT - Identity and Access Management | 963267 | 1275524 | Deferred | 2026 |  | Subsequent Submittal | This project is delayed due to the cyber event. Resources were required for priority restoration.
C0067863 | IT - Managed Detect & Respond | 668280 | 1126413 | Deferred | 2026 |  | Subsequent Submittal | This project is delayed due to the cyber event. Resources were required for priority restoration.
C0070907 | MDR-8000 Microwave Radio Replacement | 511996 | 1572478 | Deferred | 2026 |  | Request Approval | Deferred due to software tool delay. The existing approach to asset management is expected to address near-term risks.
C0068726 | IT - BlueCross Integration with PeopleSoft | 139092 | 171092 | Deferred | 2026 |  | Less than $1M | This project is delayed due to the cyber event. Resources were required for priority restoration.
C0068723 | IT - Scanning Technology for SCM Operations | 162801 | 210801 | Deferred | 2027 |  | Less than $1M | This project is delayed due to the cyber event. Resources were required for priority restoration.

## R4 - FIN Report
NS Power Final Cost Report
4th Quarter Overview - as of December 31, 2025
This report includes a list of all FIN capital work orders that have fallen outside the timelines under the CEJC. (Within six months of in-service.)
These projects have either been completed and are outside the FIN tolerances or forecast to be outside of the FIN tolerances. (The greater of +/- 5% or +/- $250,000.)
Projects that have been in-service for 6 months, but have a project forecast within the allowed FIN tolerance, are not included on this list.
Project # | Project | In-service Date | NSEB Approval | Spend to December 31, 2025 | Comment
C0033644 | 2021-2022 Steel Tower Life Extension | 2021-09-30 | 2332746 | 1831087.15 | This project is now complete and a Final Cost Application is planned for submission in 2026.
C0010778 | Smart Grid Nova Scotia Project | 2020-05-31 | 7053622 | 6670498.28 | This project is now complete and a Final Cost Application is planned for submission in 2026.

## R5 - Unapproved Spending(2025)
NS Power Unapproved Spending
As of December 31, 2025
This report includes all projects that have been removed from rate base per the conditions as established and approved in the CEJC and Accounting Policy 1520 - Rate Base, and their associated 2025 Income Statement impact.
Note 1: This report has been amended to include the new columns titled "Forgone Earning Potential" in compliance with the Board's direction by letter of August 30, 2017 (M07568)
Note 2: This report has been amended to reflect the new Board approval threshold of $1,000,000, effective October 30, 2019.
(1) | Capital Items with NSEB unapproved plant in service above $1,000,000 ($250,000 prior to October 30, 2019), where a capital work order has not been filed with the NSEB within 6 months of the project’s completion:
CI | Project Title | Functional Class | Periods not Included in Rate Base | Approval Threshold | Spend | Unapproved Balance | Depreciation Expense on Unapproved Balance | Interest Expense on Unapproved Balance | AFUDC on Unapproved Spending | Total Income Tax Impact | 2025 Income Statement Impact | Forgone Earning Potential 2025 | Filing Date
(2) | Capital Spend above $1,000,000 ($250,000 prior to October 30, 2019) associated with a preliminary engineering project that has been inactive (i.e. no internal or external engineering or scoping work, exceeding $10,000, being carried out within the last 12 month period) and is not yet submitted for approval to the NSEB:
CI | Project Title | Functional Class | Periods not Included in Rate Base | Approval Threshold | Spend | Unapproved Balance | Depreciation Expense on Unapproved Balance | Interest Expense on Unapproved Balance | AFUDC on Unapproved Spending | Total Income Tax Impact | 2025 Income Statement Impact | Forgone Earning Potential 2025 | Expected/ Actual Filing Date
C0034486 | WRC LEM Penstock Intake | Hydro Plant | Q2 2023-Q4 2025 | 1000000 | 1206698.21 | 206698.21 | [5 empty] | 5891.147 | 2026
C0044392 | ECEI - Coal Conversion | Steam Generation | Q3 2024-Q4 2025 | 1000000 | 1810843.13 | 810843.13 | [5 empty] | 23110.0022 | TBD
(3) | Any other capital projects that are not filed with the NSEB for approval within six months of the project exceeding $1,000,000 ($250,000 prior to October 30, 2019) will have all costs in excess of $1,000,000 ($250,000 prior to October 30, 2019) removed from rate base in the quarter after the six month timeframe until these costs are submitted for approval to the NSEB:
CI | Project Title | Functional Class | Periods not Included in Rate Base | Approval Threshold | Spend | Unapproved Balance | Depreciation Expense on Unapproved Balance | Interest Expense on Unapproved Balance | AFUDC on Unapproved Spending | Total Income Tax Impact | 2025 Income Statement Impact | Forgone Earning Potential 2025 | Expected/ Actual Filing Date
C0057361 | HYD - ANN Facility Isolation | Hydro Plant | Q1 2024 - Q4 2025 | 1000000 | 3134768.3663 | 2134768.3663 | [5 empty] | 49030.8372 | Q3 2026
C0032664 | ECC Optimization Tools Project | General Property | Q1 2024 - Q3 2025 | 1000000 | 6532898 | 5532898 | [5 empty] | -17665.6956 | 2025-12-01
C0053699 | Renewable to Retail Implementation | General Property | Q3 2024 - Q3 2025 | 1000000 | 4394231.96 | 3394231.96 | [5 empty] | 69709.377 | 2025-12-01
(4) | Previously approved capital projects exceeding the allowable variance of the greater of 5% or $250,000 and are not filed within six months of exceeding the approved amount:
CI | Project Title | Functional Class | Periods not Included in Rate Base | Approval Threshold | Spend | Unapproved Balance | Depreciation Expense on Unapproved Balance | Interest Expense on Unapproved Balance | AFUDC on Unapproved Spending | Total Income Tax Impact | 2025 Income Statement Impact | Forgone Earning Potential 2025 | Expected/ Actual Filing Date
29807 | Tusket Main Dam Refurbishment | Hydro Plant | Q2 2022 - Q4 2025 | 18157609 | 25502027.6059 | 7344418.6059 | [5 empty] | 198989.0797 | Q1 2027
(5) | Other Unapproved Spending:
CI | Project Title | Functional Class | Periods not Included in Rate Base | Approval Threshold | Spend | Unapproved Balance | Depreciation Expense on Unapproved Balance | Interest Expense on Unapproved Balance | AFUDC on Unapproved Spending | Total Income Tax Impact | 2025 Income Statement Impact | Forgone Earning Potential 2025 | Expected/Actual Filing Date
45066 | Upgrade L6511 and L7019 | Transmission Plant | Q4 2019 - Q4 2025 |  | 2691016.62 | 2691016.62 | 69764.7166 | 64536 |  | -47513.1869 | 86787.5297 | 60026.3358 | TBD*
45067 | 67N Onslow 345 KV Node Swap | Transmission Plant | Q4 2019 - Q4 2025 |  | 2982713.4 | 2982713.4 | 63830.0668 | 76751.8278 |  | -52729.673 | 87852.2215 | 71366.6354 | TBD*
43324 | L6513 Rebuild/upgrade line terminal | Transmission Plant | Q4 2019 - Q4 2025 |  | 18625268.79 | 18625082.14 | 717065.667 | 425974.5958 |  | -346612.8443 | 796427.4185 | 396494.4038 | TBD*
43678 | Separate L8004/L7005 | Transmission Plant | Q4 2019 - Q4 2025 |  | 20387278.07 | 20387278.07 | 485136.2605 | 518844.5978 |  | -391147.2739 | 612833.5844 | 482500.8304 | TBD*
39472-H596 | HYD Mersey Redevelopment Phase 1 | Hydro Plant | Q4 2025 | 1000000 | 20979410.27 | 20387278.07 | [6 empty] | TBD
* Maritime Link Transmission capital work orders were filed as part of the Company's General Rate Application. They were not approved at the time of report issuance.
[10 empty] | Total Impact to 2025 | 1583900.7541 | 1339452.953

## R6 - Unapproved over $1M
Unapproved Spending Over $1M
As of December 31, 2025
This report includes all capital projects greater than $1 million that are within the rate base thresholds as established and approved in the CEJC and Accounting Policy 1520 - Rate Base, that have not been approved by the Board at December 31, 2025. This is distinct from the preceding Unapproved Spending report, as that report includes projects removed from Rate Base.
Note 1: This report has been included in compliance the NSEB's direction by letter of August 30, 2017 (M07568).
Note 2: This report has been amended to reflect the new Board approval threshold of $1,000,000, effective October 30, 2019.
Project # | Project | Status as at December 31, 2025 | Spend as at December 31, 2024 | Spend as at December 31, 2025 | Comment
39472-H596 | HYD Mersey Redevelopment Phase 1 | PE | 20978080.51 | 20979409.99 | Preliminary Engineering efforts to determine the scope / cost of the project. This PE will inform multiple dam safety and power house projects on the Mersey Hydro system.
C0068655 | LM6000 191-332 Hot Section Refurbishment | Awaiting Approval | 217556.29 | 18991705.52 | CWO filed on August 5, 2025.
C0032664 | ECC Optimization Tools | Awaiting Approval | 3388539.19 | 15156876.68 | CWO filed on December 1, 2025.
C0044110 | 138kv Line Tap to 92V Substation | PE | 4419262.27 | 4932883.27 | Preliminary Engineering efforts to determine the scope / cost of the project.
C0053699 | Renewable to Retail Implementation | Awaiting Approval | 2977604.76 | 4394231.96 | CWO filed on December 1, 2025.
C0080150 | TUC1 HP Turbine Vibration Refurbishment | Pending Submission | 0 | 3574427.04 | Project to be filed as a U&U in 2026.
C0068898 | TUC1 IP LP Last Stage Blade Replacement | Awaiting Approval | 0 | 3490876.62 | CWO filed on December 12, 2025 in 2026 ACE Plan.
C0032382 | 142H - Susie Lake Substation | Pending Submission | 415322.5 | 3313075.85 | Project included in 2026 ACE Plan as a Subsequent Submittal.
C0057361 | HYD ANN Facility Isolation | Pending Submission | 2473465.96 | 3134767.32 | Project included in 2026 ACE Plan as a Subsequent Submittal.
47650-H774 | HYD - Annapolis Decision Analysis | Pending Submission | 1563931.55 | 3060381.06 | Project included in 2026 ACE Plan as a Subsequent Submittal.
C0081985 | Michelin DVR Phase 2 | Pending Submission | 0 | 3037041.52 | Project included in 2026 ACE Plan as a Subsequent Submittal.
C0047278 | IT - Oracle MDM Upgrade | Pending Submission | 13549.93 | 2862698.11 | Project included in 2026 ACE Plan as a Subsequent Submittal.
C0068714 | IT - Identity & Access Management | Pending Submission | 121417.61 | 2478826.37 | Project included in 2026 ACE Plan as a Subsequent Submittal.
C0044172 | L7005 Canso Crossing Vibration Mitigation | Pending Submission | 367176.28 | 2473174.09 | Project is complete with application pending for submission to NSEB.
C0056722 | Dist. Inspection Programs (1) | PE | 973014.22 | 3075763.38 | This project includes inspection costs, which will be subsequently allocated to capital projects.
C0022247 | 1N Onslow Transformer Addition (1N-T66) | Pending Submission | 1462694.5 | 2403846.14 | Project included in 2026 ACE Plan as a Subsequent Submittal.
C0011358 | New Bridgewater Substation | PE | 36065.68 | 2257632.66 | Preliminary Engineering efforts to determine the scope / cost of the project.
C0021835 | IT - CIS Replacement | Pending Submission | 2067185.41 | 3418027.96 | Project included in 2026 ACE Plan as a Subsequent Submittal.
47751 | ECC Dynamic Line Rating Implementation | Awaiting Approval | 302046.91 | 1908420.39 | CWO filed on December 1, 2025 and approved March 3, 2026.
C0032746 | WRC Tunnel T-1 Remediation | PE | 818054.1 | 1727256.27 | Preliminary Engineering efforts to determine the scope / cost of the project.
C0068689 | PHB - Boiler Refurbishment 2025 | Less than $1M | 0 | 1670575.55 | Project originally forecast to be completed for less than $1M, therefore not filed. Project exceeded $1M in spend during construction, but will remain less than $1M.
48047-T870 | Trans. Inspection Programs (1) | PE | 2679083.31 | 4062479.7 | This project includes inspection costs, which will be subsequently allocated to capital projects.
C0067183 | TUC Wharf Access Bridge Replacement | Awaiting Approval | 108462.9655 | 1744056.9 | Project included in 2026 ACE Plan for Request Approval.
C0069166 | POT - Turbine Valves Refurbishment | Pending Submission | 8979.45 | 1629647.52 | Project is complete with application pending for submission to NSEB.
C0051815 | 2025 RTU Replacement Program | Awaiting Approval | 194976.27 | 1483595.86 | Revised CWO filed December 9, 2025.
51098-T952 | L-6014 Shannon Park Trans Towers | Pending Submission | 1043035.15 | 1433680.64 | Project included in 2026 ACE Plan as a Subsequent Submittal.
C0068937 | POT - Boiler Refurbishment 2025 | Less than $1M | 0 | 1432049.28 | Project originally forecast to be completed for less than $1M, therefore not filed. Project exceeded $1M in spend during construction, but will remain less than $1M.
C0068769 | TRE6 - Boiler Refurbishment | Less than $1M | 0 | 1388284.06 | Project originally forecast to be completed for less than $1M, therefore not filed. Project exceeded $1M in spend during construction, but will remain less than $1M.
41350-D782 | 16W-301 Hebron Rebuild Phase 2 | Less than $1M | 674772.81 | 1258488.62 | Project originally forecast to be completed for less than $1M, therefore not filed. Project exceeded $1M in spend during construction, but will remain less than $1M.
C0068701 | PHB - Precipitator Refurbishment 2025 | Less than $1M | 0 | 1254931.07 | Project originally forecast to be completed for less than $1M, therefore not filed. Project exceeded $1M in spend during construction, but will remain less than $1M.
C0060570 | TUC1 AVR Replacement | Less than $1M | 327408.15 | 1242036.05 | Project originally forecast to be completed for less than $1M, therefore not filed. Project exceeded $1M in spend during construction, but will remain less than $1M.
C0071248 | 2024 PCB Poletop Sampling and Replacement | Less than $1M | 889043.63 | 1152673.02 | Project originally forecast to be completed for less than $1M, therefore not filed. Project exceeded $1M in spend during construction, but will remain less than $1M.
C0069687 | M10905 Interconnection Study Decision | PE | 385575.12 | 1146146.1 | Preliminary Engineering efforts to determine the scope / cost of the project.
C0067950 | POA Coal Gallery Refurbishment 2025 | Less than $1M | 0 | 1136991.15 | Listed as Point Aconi <$1M in 2025 ACE. Project exceeded $1M in spend during construction, but will remain less than $1M.
48913-H765 | HYD - Tusket Facility Repairs | PE | 685471.51 | 1088599.83 | Project included in 2026 ACE Plan as a Subsequent Submittal.
C0067123 | TUC1 South BFP & Motor Refurbishment 2024 | Less than $1M | 577552.8 | 1077361.86 | Project originally forecast to be completed for less than $1M, therefore not filed. Project exceeded $1M in spend during construction, but will remain less than $1M.
C0031125 | TRE5 Boiler Refurbishment 2024 | Less than $1M | 951665.45 | 1065886.36 | Project originally forecast to be completed for less than $1M, therefore not filed. Project exceeded $1M in spend during construction, but will remain less than $1M.
C0068187 | LIN Mill Refurbishment 2025 | Less than $1M | 0 | 1063820.71 | Project originally forecast to be completed for less than $1M, therefore not filed. Project exceeded $1M in spend during construction, but will remain less than $1M.
C0063383 | TUC2 SDIR Findings Refurbishment/Replacement | Less than $1M | 579368.33 | 1033059.27 | Project originally forecast to be completed for less than $1M, therefore not filed. Project exceeded $1M in spend during construction, but will remain less than $1M.
C0070646 | 57C-426H-Stillwater Phase Extension | Less than $1M | 2728.97 | 1023233.95 | Project originally forecast to be completed for less than $1M, therefore not filed. Project exceeded $1M in spend during construction, but will remain less than $1M.
C0063543 | WRC Penstock Mucking Tunnel Rock Bolting | Less than $1M | 995073.1 | 1004317.17 | Project originally forecast to be completed for less than $1M, therefore not filed. Project exceeded $1M in spend during construction, but will remain less than $1M.
C0063964 | TUC2 Boiler Attemperator Replacement | Less than $1M | 1006568.27 | 1002424.65 | Project originally forecast to be completed for less than $1M, therefore not filed. Project exceeded $1M in spend during construction, but will remain less than $1M.
(1) Costs for the Distribution and Transmission Programs are accumulated in multiple Inspection Program projects, for the purposes of reporting, the total costs of all Inspection Program projects has been presented in the table above.

## R7 - Capital Write Offs > 1M
2025 Capital Write Offs in Excess of $1,000,000
This report includes capital write offs in excess of $1,000,000. A write-off occurs typically when a capital project is no longer feasible and will not proceed. The costs associated with these projects are written-off to operating expenses. This report is included in compliance to NS Power’s commitment as noted in its letter of August 15, 2016. This report has been amended to reflect the new Board approval threshold of $1,000,000, effective October 30, 2019.
CI Number | Project Title | Value | Description
There were no write-offs in excess of $1,000,000 in 2025.

## R8 - Routines
NS Power 2025 Capital Spend Detail - As per ACE
Routine Capital Reconciliation to 2025 ACE - as of December 31, 2025
This report includes an overview of routine expenditures showing actual 2025 spending compared to the 2025 ACE Plan.
|  | 2025 ACE Plan Amount (2025) | 2025 Spend | Variance Actual/ACE
Generation
| Generation Equipment Replacements | 5317515 | 6128993.6986 | 811478.6986
| Generation Other Hydro | 1352219 | 1099903.39 | -252315.61
| Generation Other Thermal | 475944 | 199826.2389 | -276117.7611
|  | 7145678 | 7428723.3275 | 283045.3275
Transmission
| Transmission Substation Replacement, Add'ns/Mod'ns | 4375511 | 4244317.5563 | -131193.4437
| Primary Equipment Spares | 300000 | 14422.27 | -285577.73
| Protection Modification & Replacement | 987791 | 531788.68 | -456002.32
| Transmission Line Replacement, Add'ns/Mod'ns | 9329311 | 6011113.59 | -3318197.41
| Transmission Right-of-Way Widening | 2999500 | 2881237.62 | -118262.38
|  | 17992113 | 13682879.7163 | -4309233.2837
Distribution
| Meters | 4876834 | 3733502.2 | -1143331.8
| Distribution Upgrades and Replacement | 44744622 | 51799132 | 7054510
| New Customers | 69444057 | 65099707 | -4344350
| Joint Use | 4581201.7 | 2553346 | -2027855.7
| Distribution Right-of-Way Widening | 12502941.7 | 11944225.7178 | -558715.9822
|  | 136149656.4 | 135129912.9178 | -1019743.4822
General Plant
| Work Vehicles | 19199029 | 19673001.73 | 473972.73
| Tools and Test Equipment | 1921927 | 2064260.28 | 142333.28
| Telecommunications | 1387013 | 1347295.18 | -39717.82
| Computing Asset Management | 4471479 | 3596973.04 | -874505.96
| Property Improvements and Furniture | 4882004 | 4125289.6 | -756714.4
| Other | 1450720 | 967519.99 | -483200.01
|  | 33312172 | 31774339.82 | -1537832.18
| Total Routine Capital Spending | 194599619.4 | 188015855.7816 | -6583763.6184
*2025 Routine spend excludes amounts related to Point Aconi. Total 2025 routine spend including Point Aconi is $188.5M
*Any routine actual spending which exceeds the CEJC ATO thresholds will have ATO applications submitted to the NSEB in due course.

## R9 - Carry Over
NS Power 2025 Capital Spend Detail - As per ACE 2025
2025 ACE Carryover Spending - as of December 31, 2025
This report includes an overview of carryover expenditures showing actual 2025 spending compared to the 2025 ACE Plan.
Project Number | CI # | Title | 2025 ACE Plan Amount (2025) | 2025 ACE Plan Amount (Project Total) | 2025 Actual Spend | Variance Actual/ACE
Generation
| C0013838 | HYD WRC LEM Unit Rehabilitation and Replacement | 9356145 | 103496429 | 13038174.28 | 3682029.28
| 29807 | HYD - Tusket Falls Main Dam | 2165510 | 71816443 | 626019.36 | -1539490.64
| C0014218 | Wreck Cove Life Extension and Modernization (LEM) Project - Balance of Plant | 7136068 | 27555415 | 42633.08 | -7093434.92
| 16374 | HYD - Gaspereau Dam Safety Remedial Works | 1206182 | 20412708 | 266025.95 | -940156.05
| C0006418 | HYD WRC Tailrace Tunnel Rock Bolting Phase 2 | 12267054 | 15785675 | 12120971.78 | -146082.22
| 50518 | HYD - Ruth Falls Main Dam Refurbishment | 8283749 | 15020672 | 5269246.18 | -3014502.82
| 51236 | HYD WRC Tailrace Tunnel Rock Bolting Phase 1 | 1966113 | 8598176 | 633153.82 | -1332959.18
| C0012838 | HYD - Lequille Canal Dyke, Gates and Tailrace Refurbishment | 4251482 | 5776813 | 4725532.09 | 474050.09
| C0000979 | HYD - Governor Dam Refurbishment | 27626 | 4850246 | 178070.16 | 150444.16
| C0029682 | CT - VJ2 Generator Replacement | 3331179 | 4813997 | 3364872.9894 | 33693.9894
| C0060707 | CT BGT1 Generator Refurbishment | 741745 | 4192349 | 1206.05 | -740538.95
| C0060608 | TUC6 Turbine Refurbishment | 1949728 | 2438762 | 13301.18 | -1936426.82
| C0044030 | WIN - DIG Haights Brook Crossing Replacement | 1379804 | 1665828 | 70129.0024 | -1309674.9976
| C0064966 | Tusket Powerhouse Tidal Pool Fish Passage | 594972 | 982263 | 220149.31 | -374822.69
| C0029690 | CT - VJ2 - Control System Upgrade | 882848 | 965772 | 769860.22 | -112987.78
| C0055155 | TUC2 Stack Platform Replacement | 684011 | 964563 | 26476.39 | -657534.61
| C0038126 | HYD - Cowie Falls Unit 12 Overhaul | 596310 | 957437 | 967607.2 | 371297.2
| C0060570 | TUC1 AVR Replacement | 453297 | 950282 | 914627.9 | 461330.9
| 49942 | HYD - Tidewater Facility Refurbishment | 799190 | 949162 | 1149916.43 | 350726.43
| C0060323 | PTMT-Coal Pile Modifications | 16222 | 944556 | 49552.75 | 33330.75
| C0063559 | PTMT Conveyor Refurbishment | 521935 | 942139 | 465488.2381 | -56446.7619
| C0069151 | TUC WTP Tank 3 Cation Vessel Replacement | 844852 | 935246 | 462178.53 | -382673.47
| C0067183 | TUC Wharf Structural Refurbishment 2024 | 825893 | 927528 | 1636670.6945 | 810777.6945
| C0060594 | TUC6 Turbine Valves Refurb 2024 | 454019 | 905991 | 28249.45 | -425769.55
| C0021982 | ICP UU Unloading Hopper Replacement | 199387 | 766202 | 167010.44 | -32376.56
| C0053654 | HYD Cowie Falls Generator Refurbishment | 356377 | 760803 | 819696.64 | 463319.64
| C0053657 | HYD COW Filler Gate Replacements | 33773 | 756380 | 83308.01 | 49535.01
| C0052914 | ICP Rail Center Fuel System Refurbishment | 525122 | 702664 | 631624.35 | 106502.35
| C0060598 | TUC6 Heat Recovery Steam Generator Boiler Refurb 2024 | 612261 | 695727 | 220038.85 | -392222.15
| C0019025 | HYD - Sloane Dam Refurbishment | 485902 | 694060 | 33748.43 | -452153.57
| C0068344 | HYD PCB Removal | 350351 | 685315 | 221286.98 | -129064.02
| C0060775 | POT - South Boiler Feed Pump Refurbishment | 530536 | 546619 | 700047.74 | 169511.74
| C0063550 | ICP Conveyor Take-Up Refurbishment | 138620 | 521299 | 4882.65 | -133737.35
| 49036 | HYD - Avon 2 Controls Upgrade | 391178 | 496293 | 502009.69 | 110831.69
| C0010324 | TRE5 - Condenser Inlet Piping and Valve Replacement | 442488 | 449052 | 0 | -442488
| C0050892 | TUC - Elevator Upgrade | 399700 | 442172 | 0 | -399700
| C0061376 | TRE5 - 5-2 CW Pump Refurbishment | 35936 | 423227 | 222496.24 | 186560.24
| C0038629 | HYD - Ridge Surge Tank Refurbishment | 416413 | 418877 | 7358.29 | -409054.71
| C0063555 | ICP Chute Replacement | 47600 | 400463 | 82708.58 | 35108.58
| C0060776 | POT- Polisher Valves Solenoid Panel Replacement | 321140 | 395767 | 329714.29 | 8574.29
| 51394 | LIN3&4 Operator Control Panel Button Upgrade | 218791 | 226747 | -8749.44 | -227540.44
| C0063405 | ICP Locomotive Refurbishment 2024 | 153137 | 374927 | 166558.42 | 13421.42
| C0067444 | HYD COW Stop Log Replacements | 25797 | 374529 | 4729.95 | -21067.05
| C0030549 | CT - VJ2 - Gen Control and Protect | 260182 | 363016 | 40859.83 | -219322.17
| C0021608 | TUC Shoreline Sheetpile Refurbishment | 191264 | 357211 | 84130.77 | -107133.23
| C0062063 | HYD - Dam Generator Procurement | 77195 | 336306 | 219071.66 | 141876.66
| C0058062 | HYD Avon 2 Station Service Upgrade | 317253 | 335271 | 0 | -317253
| C0060781 | POT – Fuel Delivery Control & Instrumentation Refurbishment 2024 | 310249 | 331670 | 64155.62 | -246093.38
| C0065823 | TUC1 HP Gov Valve Replace 2024 | 221928 | 330639 | 6928.91 | -214999.09
| C0049456 | HYD ANN Safety Boom Replacement | 123634 | 329365 | 77103.54 | -46530.46
| C0068308 | TUC3 4kv600v Breaker Replace 2025 | 321376 | 322176 | 283639.12 | -37736.88
| C0067405 | LIN4 UU FAC Refurbishment 2024 | 25286 | 308992 | 9223.48 | -16062.52
| C0050648 | CT LM6000 Air Compressor | 151822 | 301626 | 916.97 | -150905.03
| C0039028 | LIN1 Ash Incline Refurbishment 2025 | 279244 | 281473 | 3351.87 | -275892.13
| C0030702 | LIN Bottom Ash Incline Belt Refurbishment | 237158 | 281268 | 102344.7 | -134813.3
| C0060812 | POT- Water Treatment Plant MCC Upgrade | 109251 | 271950 | 164114.06 | 54863.06
| C0010331 | TRE6 Precipitator Controls Upgrade | 231405 | 268213 | 29951.78 | -201453.22
| C0042526 | HYD ULF2 Stator Refurbishment | 15915 | 254301 | 92253.32 | 76338.32
| C0039446 | HYD - EVH Door Replacements | 78993 | 248183 | 2941.79 | -76051.21
| C0026862 | LIN1 CW Pipe Refurbishment | 195077 | 243064 | 1857.99 | -193219.01
| C0067747 | ANN Tidal - MCC Replacement | 66589 | 236947 | 209135.18 | 142546.18
| C0061327 | LIN Fly Ash Hopper Vibrator Replacement | 158861 | 230392 | 75413.94 | -83447.06
| C0039166 | LIN CW Valve Refurbishment 2022 | 169826 | 220549 | 45856.31 | -123969.69
| C0040186 | TRE PCB Equipment Replacement | 189164 | 217656 | 37782.13 | -151381.87
| C0046830 | HYD - Mersey Jordan Lake Communication Upgrades | 101169 | 192514 | 29441.76 | -71727.24
| C0059624 | AMO LIN1 Enhanced Monitoring | 46409 | 186748 | 151316.7 | 104907.7
| C0052113 | ICP Main Storage Area Stormwater Management | 99489 | 185889 | 129408.27 | 29919.27
| C0060578 | TUC2 Replace Air Foils | 150118 | 173297 | 926.64 | -149191.36
| C0021882 | LIN CW Control Panel Upgrades | 160260 | 171423 | 0 | -160260
| C0060576 | TUC1 Condensate Extract Pump Refurbishment | 134877 | 164569 | -801.85 | -135678.85
| C0063552 | ICP Pier Hydraulics & Elec Refurbishment | 149340 | 154144 | 293310.81 | 143970.81
| C0042466 | HYD STM Garage Refurbishment | 133437 | 147067 | 3892.96 | -129544.04
| 49657 | TUC Sequence of Events Recorder Upgrade | 108707 | 133979 | 0 | -108707
| C0038346 | HYD - PAR Window Replacement | 127342 | 128373 | 0 | -127342
| C0041510 | CT VJ2 AC/DC Fuel Pump Replacement | 109170 | 124470 | 921.34 | -108248.66
| C0041053 | LIN Ladder Swing Gates 2022 | 49944 | 121572 | 53371.68 | 3427.68
| C0069030 | TUC Person Door Replacement | 100022 | 116291 | 23162.57 | -76859.43
| C0028123 | LIN UU Dry Ash Unloading Refurb. | 66394 | 105180 | 0 | -66394
| C0030482 | LIN Wastewater System Instrumentation Replacement | 46662 | 77249 | 7123.11 | -39538.89
| C0067443 | HYD LGB Wall Bushing Replacement | 55219 | 69909 | 27118.81 | -28100.19
| C0041522 | CT - Harden Control System Grounding | 11936 | 66372 | 8820.6 | -3115.4
| C0050652 | CT VJ Unit 2 Vibration Monitoring and Protection | 34973 | 60342 | 1528.15 | -33444.85
| C0050651 | CT VJ Unit 1 Vibration Monitoring and Protection | 34973 | 60342 | 1530.02 | -33442.98
| C0041548 | AMO TUC Relay Connectivity | 48690 | 51832 | 163.71 | -48526.29
| C0028686 | LIN1 Steam Drum Level Controls Upgrade | 41991 | 43001 | 0 | -41991
|  | Generation Total | 71963237 | 315584406 | 53510851.3944 | -18452385.6056
0
Transmission
| C0045132 | Battery Energy Storage System Project | 133567294 | 237777742 | 167944718.94 | 34377424.94
| C0053316 | Transmission Customer Performance Regulations Compliance Project – Michelin Waterville Dynamic Voltage Restorer | 654117 | 31919745 | 2828005 | 2173888
| C0062123 | 143H-Mount Uniacke Substation | 2122576 | 9038229 | 6618511.55 | 4495935.55
| C0041788 | L6516 Replacements and Upgrades Phase 2 | 1928774 | 5459214 | 464621.08 | -1464152.92
| C0061545 | L6006 Replacements and Upgrades | 1113189 | 5189212 | 1984237.47 | 871048.47
| C0061550 | L5031 Replacements and Upgrades - Hubbards to East Chester | 1274730 | 4562284 | 3691728.96 | 2416998.96
| C0056240 | 2024/2025 Transmission Switch and Breaker Replacements | 270595 | 3972923 | 629970.68 | 359375.68
| C0055796 | 2023 EHV Breaker Replacements | 1541182 | 3521673 | 1414368.73 | -126813.27
| C0061551 | L7009 Replacements and Upgrades | 1389540 | 3195675 | 1151296.96 | -238243.04
| C0031122 | L6539 Replacements and Upgrades | 1529843 | 2771864 | 167949.64 | -1361893.36
| C0061403 | 2024 2025 Sacrificial Anode Installation Program | 788891 | 2494365 | 720515.51 | -68375.49
| C0052299 | 2023/2024 Steel Tower Life Extension | 898085 | 2273105 | 1215244.47 | 317159.47
| C0050842 | 2024 Bulk Oil Breaker Replacement Program | 950241 | 2119992 | 579227.51 | -371013.49
| C0061547 | L7022 Replacements and Upgrades | 1015899 | 2109773 | 861440.6 | -154458.4
| C0041791 | L6551 Replacements and Upgrades | 808668 | 2059239 | 845166.53 | 36498.53
| C0050835 | 2023/2024 Steel Tower Refurbishment | 875812 | 2049100 | 250295.18 | -625516.82
| C0061546 | L6514 Replacements and Upgrades | 800114 | 1792249 | 391047.64 | -409066.36
| C0041807 | L5534 Replacements and Upgrades | 277404 | 1744926 | 2945.8 | -274458.2
| C0057882 | 2024 Pennsylvania Breaker Replacements | 142591 | 1345127 | 150257.24 | 7666.24
| C0041804 | 2022 Line Retirement Program | 910874 | 1251786 | -737.58 | -911611.58
| C0061387 | 2024 2025 Wood Pole Retreatment Program | 511730 | 1172558 | 5591.34 | -506138.66
| C0067112 | L5012 Replacements and Upgrades | 112598 | 986828 | -300282.28 | -412880.28
| C0052654 | L5541 Water Crossing Upgrades | 599013 | 898519 | 0 | -599013
| C0061743 | L6038 Realignment | 468823 | 856543 | 980448.64 | 511625.64
| C0067111 | L5023 Rebuild | 147876 | 826981 | 65629 | -82247
| C0061883 | 129H - Kearney Lake Substation Rebuild | 113241 | 797034 | 40745.86 | -72495.14
| C0041812 | L6040 Replacements and Upgrades | 445437 | 677291 | 399.86 | -445037.14
| C0043010 | 2022/2023 Wood Pole Retreatment Program | 79470 | 656597 | 0 | -79470
| C0031268 | AMO Critical Equipment Online Monitoring | 34543 | 432380 | 53850.08 | 19307.08
| C0031044 | 67N-713 230 kV Breaker Replacement | 430000 | 430622 | 0 | -430000
|  | Transmission Total | 155803150 | 334383576 | 192757194.41 | 36954044.41
Distribution | [5 empty] | 0
| 47124 | Advanced Metering Infrastructure | 749120 | 143899252 | 2673.42 | -746446.58
| C0061521 | New Distribution Rights-of-Way Phase 10 | 16372529 | 20710059 | 18432929.5704 | 2060400.5704
| C0008638 | D-Cogswell HRM Redevelopment Program | 1667138 | 6434685 | 1722793.4959 | 55655.4959
| C0022662 | 22C-404GA Lennox Passage Rebuild | 259698 | 2499859 | 854298.92 | 594600.92
| C0031117 | 2H-411-Prospect Rd Phase Extension | 410157 | 1041838 | 156073.85 | -254083.15
| 41350 | 16W-301 Hebron Rebuild Phase 2 | 268429 | 922340 | 583715.81 | 315286.81
| C0060749 | 2024 Padmount Replacement Program | 272486 | 879342 | 1282053.47 | 1009567.47
| 52184 | 37N-412 Glooscap Trail Rebuild Phase 2 | 243181 | 859670 | 3556.71 | -239624.29
| C0033444 | 63V-312 Stronach Mountain Phase Extension | 458333 | 805305 | 16211.06 | -442121.94
| 49841 | 23H-Rockingham Voltage Conversion-Phase 2 | 96791 | 764927 | 8056.33 | -88734.67
| C0043490 | 2022 Downline Asset PCB Replacements | 372622 | 661162 | 2013.08 | -370608.92
| C0061384 | 512W-311-Lake Torment Loading Issue | 512051 | 616463 | 696973.14 | 184922.14
| C0042846 | 15C-211 - Deepdale Conversion | 490752 | 549255 | 470629.88 | -20122.12
| C0011189 | 2H-411 - Cowie Hill UG System Replacements Part 3 | 315834 | 508664 | 18179.92 | -297654.08
| C0042186 | 100C-421 - Harvre Boucher Rebuild | 455047 | 506707 | 311497.17 | -143549.83
| C0031402 | 559W-331 Molega Lake Rd Conversion | 438722 | 482078 | 400872.39 | -37849.61
| C0015198 | 50V Kentville Aluminum Light Pole Replacement | 169188 | 461949 | 17399.18 | -151788.82
| C0041955 | 2022 Hydraulic Recloser Replacements | 48216 | 434170 | 92919.78 | 44703.78
| C0041953 | 2022 Recloser Remote Connectivity | 39649 | 402691 | 132308.45 | 92659.45
| C0061385 | 5N-301-Debert Stepdown Replacement and Reconfiguration | 262489 | 369606 | 295978.09 | 33489.09
| C0061266 | 19C-204 - Durells Island Conversion | 365475 | 365475 | 367822.94 | 2347.94
| C0004138 | 50W-412GA Port Medway Line Extension | 161531 | 358063 | 431406.57 | 269875.57
| C0053517 | 9H-221 University Ave and Morris St Conversion | 67099 | 355319 | 26089.75 | -41009.25
| C0060750 | 2024 Vault Replacement | 90706 | 326096 | 101689.4 | 10983.4
| C0033507 | Underground Switch Replacements | 125510 | 291106 | -6.72 | -125516.72
| C0031300 | 9H-223 North St Conversion | 226688 | 245420 | 225556.41 | -1131.59
| C0050846 | 2023 Hydraulic Recloser Replacements | 147578 | 231712 | 0 | -147578
| C0060751 | 2024 Manhole Automatic Pumps | 18495 | 94443 | 74285.1076 | 55790.1076
|  | Distribution Total | 25105514 | 186077656 | 26727977.1739 | 1622463.1739
General Plant | [5 empty] | 0
| C0065685 | AMO Enhanced Substation Analytics | 99650 | 221339 | 78711.95 | -20938.05
| C0067899 | AMO Wildfire Risk Mapping | 102595 | 194676 | 143286.28 | 40691.28
| C0029928 | AMO Weymouth Telecom Upgrade | 106874 | 256950 | 132482.68 | 25608.68
| C0068105 | AMO - Hydro EMS Automation | 69388 | 95899 | 33164.33 | -36223.67
| C0020339 | AMO - Risk Repository Tool | 73518 | 173651 | 80670.81 | 7152.81
| C0064663 | AMO Rounds Pro Upgrade | 86150 | 117116 | 18036.43 | -68113.57
| 47751 | ECC Dynamic Line Rating Implementation | 716102 | 968222 | 1606373.48 | 890271.48
| C0061525 | ECC Facility Ratings | 169649 | 964316 | 308431.16 | 138782.16
| C0032664 | Energy Control Centre - Optimization Tools | -2537936 | 895115 | 11768337.4864 | 14306273.4864
| C0032143 | GIS Underground Asset Modelling | 433399 | 511982 | 0 | -433399
| C0062524 | Damage Assessment Enhancements 5.0 | 307139 | 386929 | -387.05 | -307526.05
| C0021133 | SCADA Mobile Application | 56120 | 160555 | 0 | -56120
| C0049619 | IT - ERP Upgrade (EBS, PS, PP, OBIA) | 1102097 | 5316174 | 1321856.1 | 219759.1
| C0047277 | IT - GIS Utility Network Upgrade | 2646483 | 4922983 | 1329968.35 | -1316514.65
| C0056461 | IT - Contact Centre Cloud Migration | 1499989 | 3118055 | 1496538.57 | -3450.43
| C0054755 | IT - Connect My Data (Green Button) | 141510 | 2557828 | 576505.29 | 434995.29
| C0061323 | IT - Data Storage Arrays | 783929 | 986620 | 723339.4 | -60589.6
| C0047190 | IT - Drupal Upgrade | 113753 | 968303 | 288696.04 | 174943.04
| C0042169 | IT - Arc FM Designer Upgrade | 369004 | 964211 | 247035.07 | -121968.93
| C0022002 | IT- Storm Centre Upgrade | 637238 | 846656 | 53545.78 | -583692.22
| C0069309 | IT - PI & Designer XI Licenses | 513362 | 794931 | 0 | -513362
| C0067703 | IT - Prov Community Solar | 243790 | 612548 | 84662 | -159128
| C0061345 | IT - Windows 11 Version Upgrade | 400000 | 594371 | 168608.15 | -231391.85
| C0047296 | IT - Microsoft SQL Consolidation | 76074 | 519520 | 125151.46 | 49077.46
| C0011159 | IT - Plant Information System Upgrade | 149058 | 306592 | 978983.15 | 829925.15
| C0061295 | IT - Switch Replacement Management | 171025 | 228097 | 44825.77 | -126199.23
| C0047299 | IT - Replacement of Cisco Endpoint | 134775 | 223763 | 21294.82 | -113480.18
| C0021109 | 2020 RTU Deployment Project | 342065 | 7277404 | 894109.37 | 552044.37
| C0011378 | Route Network Upgrade | 454331 | 6218148 | 221189.94 | -233141.06
|  | General Plant Total | 9461131 | 41402954 | 22745416.8164 | 13284285.8164
| Grand Total |  | 262333032 | 877448592 | 295741439.7948 | 33408407.7948

## R10 - Retirements >$1M
2025 Asset Retirement Values Greater than $1M by Capital Item
This report includes retirements in excess of $1,000,000, where NS Power has not sought or received explicit Board approval for the retirement of original cost. This report is included pursuant to the Board’s directive relating to M09229 dated May 5, 2020.
Project | Retirement Amount | Percentage of GBV of Asset Pool Retired | Nature of Retirement and Life Cycle | Policy | Accounting Treatment of Retirement Amount
Distribution Plant - D
D004 NEW CUSTOMER REPLACEMENTS ROUTINE | -1515745.77 | 0.07% of Total Distribution Asset Pool | Retirements among various classes and of assets at various stages of life cycle. | 6420 - Retirement and Disposal of Capital Assets | No gains or losses were recognized. Retirement amount debited to Accumulated Depreciation
D005 REPLACE DETERIORATED PLANT ROUTINE | -4384593.59 | 0.19% of Total Distribution Asset Pool | Retirements among various classes and of assets at various stages of life cycle. | 6420 - Retirement and Disposal of Capital Assets | No gains or losses were recognized. Retirement amount debited to Accumulated Depreciation
D007 CONTRACTUAL REPLACEMENTS ROUTINE | -1888647.85 | 0.08% of Total Distribution Asset Pool | Retirements among various classes and of assets at various stages of life cycle. | 6420 - Retirement and Disposal of Capital Assets | No gains or losses were recognized. Retirement amount debited to Accumulated Depreciation
D055-Identified Deteriorated Plant | -3333390.6 | 0.14% of Total Distribution Asset Pool | Retirements among various classes and of assets at various stages of life cycle. | 6420 - Retirement and Disposal of Capital Assets | No gains or losses were recognized. Retirement amount debited to Accumulated Depreciation
D061-New Customers - Residential | -2744259.77 | 0.12% of Total Distribution Asset Pool | Retirements among various classes and of assets at various stages of life cycle. | 6420 - Retirement and Disposal of Capital Assets | No gains or losses were recognized. Retirement amount debited to Accumulated Depreciation
General Plant - P
P061-Transportation Vehicle Replace | -1266566 | 3.19% of Total Transportation Vehicle Pool | Retirements of work vehicles that went into service in prior years. | 6420 - Retirement and Disposal of Capital Assets | No gains or losses were recognized. Retirement amount debited to Accumulated Depreciation
P062-Work Vehicle Replacement Rout. | -2637382 | 3.2% of Total Work Vehicle Pool | Retirements of work vehicles that went into service in prior years. | 6420 - Retirement and Disposal of Capital Assets | No gains or losses were recognized. Retirement amount debited to Accumulated Depreciation