## Substation2021-2025
fp_number | fp_description | Substation | Region | Reliability Category | special_or_parent_routine | work_order_status | work_order_number | 2021-2025 Spend
49929-T945 | Tap Changer Replacements | Provincial | Provincial | Equipment Replacement and Upgrades | Special | posted to CPR | T945 | -963.81
49957-D832 | 93V Feeder Expansion | 93V | West | Equipment Replacement and Upgrades | Special | in service | D832 | 132853.62
C0013978 | 11S Keltic Dr Substation Animal | 11S | Cape Breton | Equipment Replacement and Upgrades | Special | in service | C0017034 | 1616.25
C0011851 | T - 2019 Tap Changer Replacement | Provincial | Provincial | Equipment Replacement and Upgrades | Special | in service | C0018499 | 228804.83
C0022742 | Retire 6S-Terrace Street | 6S | Cape Breton | Equipment Replacement and Upgrades | Special | in service | C0025822 | 110.93
C0017138 | Feeders 1H-405 and 1H-431 Protectio | 1H | Metro | Equipment Replacement and Upgrades | Special | in service | C0022703 | 10274.51
C0022247 | 1N-Onslow 138 kV Add Second 42 MVA | 1N | Northeast | Equipment Replacement and Upgrades | Special | open | C0028042 | 2324052.09
C0021136 | 6P New High Side Circuit Switcher | Provincial | Provincial | Equipment Replacement and Upgrades | Special | open | C0027463 | 56728.2
C0021142 | 19W-T51 Transformer Replacement | 19W | West | Equipment Replacement and Upgrades | Special | in service | C0028866 | 1418800.03
C0031267 | 2022 Oil Containment Program | Provincial | Provincial | Equipment Replacement and Upgrades | Special | open | C0048950 | 36090.34
C0031283 | 2021 Substation Theft Prevention | Provincial | Provincial | Equipment Replacement and Upgrades | Special | in service | C0039967 | 466860.75
C0044431 | 2022 - 2023 Capacitor Bank Breaker | Provincial | Provincial | Equipment Replacement and Upgrades | Special | in service | C0045748 | 305380.47
C0059403 | 62H Low Voltage Switchgear Replacem | 62H | Metro | Equipment Replacement and Upgrades | Special | in service | C0064283 | 1522379.2
C0055539 | 10H-T1 Transformer Replacement | 10H | Metro | Equipment Replacement and Upgrades | Special | open | C0056123 | 95289.81
C0070451 | 2026 Switch and Breaker Replacement | Provincial | Provincial | Equipment Replacement and Upgrades | Special | open | C0074169 | 118391.69
C0075508 | 88W Pleasant St Transformer Refurbi | 88W | West | Equipment Replacement and Upgrades | Special | in service | C0076613 | 398102.45
51956 | 6P Mobile Substation Rewind | Provincial | Provincial | Equipment Replacement and Upgrades | Special | in service | C0024403 | -108.26
51400 | D-2018 Substation Recloser Replacem | Provincial | Provincial | Equipment Replacement and Upgrades | Special | in service | C0006699 | 218940.65
C0027162 | 129H Kearney Lake Substation Relo | 129H | Metro | Equipment Replacement and Upgrades | Special | open | C0028468 | 194058.29
C0024486 | 2S-T1 Transformer Replacement | 2S | Cape Breton | Equipment Replacement and Upgrades | Special | in service | C0024829 | 131387.08
C0022783 | 2020/2021 Gen Power Trans Refurb | Provincial | Provincial | Equipment Replacement and Upgrades | Special | open | C0026662 | 5750.11
C0021123 | 2020/2021 Substation PCB Equipment | Provincial | Provincial | Equipment Replacement and Upgrades | Special | in service | C0024523 | 1684084.24
C0021140 | New 138KV-25KV Substation Stellarto | 98N | Northeast | Load Growth | Special | open | C0044493 | 5908160.39
C0041833 | 2022 2023 Bulk Oil Breaker Replace | Provincial | Provincial | Equipment Replacement and Upgrades | Special | in service | C0046230 | 934666.9
C0031263 | 2021/2022 Substation Polychlorinate | Provincial | Provincial | Equipment Replacement and Upgrades | Special | in service | C0037307 | 7061872.02
C0031298 | 88S-T72 New Radiators | 88S | Cape Breton | Equipment Replacement and Upgrades | Special | in service | C0039866 | 199635.36
C0031048 | 91H-T11 Transformer Replacement | 91H | Metro | Equipment Replacement and Upgrades | Special | open | C0064093 | 238388.45
C0031050 | New Spare Large Autotransformer | Provincial | Provincial | Equipment Replacement and Upgrades | Special | in service | C0044410 | 2374092.32
C0061046 | 2024 Merlin Gerin Breaker Replaceme | Provincial | Provincial | Equipment Replacement and Upgrades | Special | in service | C0061886 | 353878.19
C0072609 | 2024 Substation Fence Upgrades | Provincial | Provincial | Equipment Replacement and Upgrades | Special | in service | C0073088 | 820231.63
51956 | 6P Mobile Substation Rewind | Provincial | Provincial | Equipment Replacement and Upgrades | Special | in service | C0030863 | 51768
44985-T807 | Replace 230kV Kearney Disconnect Sw | 129H | Metro | Equipment Replacement and Upgrades | Special | in service | T807 | 974.98
49928-T949 | 3S Gannon Rd. Bus Reconfiguration | 3S | Cape Breton | Equipment Replacement and Upgrades | Special | in service | T949 | 948.96
48061-T884 | New Mobile Substation 7.5MVA | Provincial | Provincial | Equipment Replacement and Upgrades | Special | posted to CPR | T884 | 562.03
51406 | 2018/2019 Transmission Switch & Bre | Provincial | Provincial | Equipment Replacement and Upgrades | Special | in service | C0009660 | 99500.02
52305 | 2018 Substation Insulator Replc | Provincial | Provincial | Equipment Replacement and Upgrades | Special | posted to CPR | C0004925 | 117042.76
C0021145 | Mobile Substation Low Voltage Cable | Provincial | Provincial | Equipment Replacement and Upgrades | Special | posted to CPR | C0027602 | 291943.72
C0031262 | 2021-22 Transmission Switch & Break | Provincial | Provincial | Equipment Replacement and Upgrades | Special | in service | C0037306 | 1456539.46
C0040566 | AMO 69kV System Assessment | Provincial | Provincial | Equipment Replacement and Upgrades | Special | open | C0044630 | 89232.51
C0031047 | 85S New Generator Breakers | 85S | Cape Breton | Equipment Replacement and Upgrades | Special | in service | C0070466 | 242765.01
C0059046 | 101S and 79N Reactor Replacements | 101S, 79N | Cape Breton | Equipment Replacement and Upgrades | Special | in service | C0061627 | 827303.24
C0050834 | Spare EHV Breaker Replacements | Provincial | Provincial | Equipment Replacement and Upgrades | Special | open | C0064491 | 164.18
C0050842 | 2024 Bulk Oil Breaker Replacement | Provincial | Provincial | Equipment Replacement and Upgrades | Special | in service | C0059343 | 1142609.86
C0053234 | 96H-T1 Transformer Replacement | 96H | Northeast | Equipment Replacement and Upgrades | Special | open | C0069648 | 37090.59
C0055557 | 76V-T1 Transformer Replacement | 76V | West | Equipment Replacement and Upgrades | Special | open | C0056124 | 2354694.76
C0068966 | 2026 Merlin Gerin Breaker Repl | Provincial | Provincial | Equipment Replacement and Upgrades | Special | open | C0076451 | -104.61
46811-T872 | 2H Armdale Transformer Addition | 2H | Metro | Equipment Replacement and Upgrades | Special | posted to CPR | T872 | -1083.88
51797 | 2018 Oil Containment Program | Provincial | Provincial | Equipment Replacement and Upgrades | Special | in service | C0005049 | 762.55
C0001900 | Mount Hope 69-25kV Substation | 141H | Metro | Equipment Replacement and Upgrades | Special | in service | C0008899 | 2438152.47
C0041830 | Spare Power Prod Unit Transformer | Provincial | Provincial | Equipment Replacement and Upgrades | Special | in service | C0045713 | 1257331.4
C0041837 | 2022 2023 Substation PCB Equip Remo | Provincial | Provincial | Equipment Replacement and Upgrades | Special | in service | C0046571 | 4013356.05
C0034209 | 1C-GT2 Transformer Failure | 1C | Cape Breton | Equipment Replacement and Upgrades | Special | open | C0034790 | -1817888.66
C0034209 | 1C-GT2 Transformer Failure | 1C | Cape Breton | Equipment Replacement and Upgrades | Special | open | C0040091 | 143307.12
C0031052 | Replenish Spare used at 58C | Provincial | Provincial | Equipment Replacement and Upgrades | Special | in service | C0040030 | 1188276.71
C0030142 | L6515, L6516 Structures Replacement | 2C | Cape Breton | Equipment Replacement and Upgrades | Special | posted to CPR | C0034067 | 18045.64
C0045510 | 20V-T52 Transformer Replacement | 20V | West | Equipment Replacement and Upgrades | Special | in service | C0047751 | 1520530.22
C0059483 | 83V L5017 and L5046 Rebuild Tap | 83V | West | Equipment Replacement and Upgrades | Special | open | C0061628 | 234390.6
C0061023 | 2024 EHV Breaker Replacements | Provincial | Provincial | Equipment Replacement and Upgrades | Special | open | C0061885 | 701.66
C0055796 | 2023 EHV Breaker Replacements | Provincial | Provincial | Equipment Replacement and Upgrades | Special | in service | C0056125 | 1477032.66
C0070909 | 70W-T51 Transformer Replacement | 70W | West | Equipment Replacement and Upgrades | Special | open | C0071650 | 14852.34
51956 | 6P Mobile Substation Rewind | Provincial | Provincial | Equipment Replacement and Upgrades | Special | in service | C0032404 | 252231.85
43267-T835 | 13V Gulch Replace 13V-GT1 & 13V-VR1 | 13V | West | Equipment Replacement and Upgrades | Special | in service | T835 | 57.38
23120-T003-820 | PROVINCIAL-TRANS SUBSTATION PRIMARY | Provincial | Provincial | Equipment Replacement and Upgrades | T003-TRANSMISSION SUBSTATION REPLAC | open | T003-820 | 15960759.36
50341-D841 | 2017 Substn Recloser Replacements | Provincial | Provincial | Equipment Replacement and Upgrades | Special | posted to CPR | D841 | 27651.9
48062-T878 | 2016 Reactor Breaker Replacements | Provincial | Provincial | Equipment Replacement and Upgrades | Special | posted to CPR | T878 | -9965.13
51975 | 5P Mobile Substation Replacement | Provincial | Provincial | Equipment Replacement and Upgrades | Special | in service | C0006219 | 1664367.82
C0011918 | T-2019 Oil Containment Program | Provincial | Provincial | Equipment Replacement and Upgrades | Special | in service | C0017978 | 310258.93
C0011261 | 101W Port Mersey Expansion | 101W | West | Equipment Replacement and Upgrades | Special | in service | C0022562 | 4551717.8
C0011850 | T - 2019 Substation Insulator Repla | Provincial | Provincial | Equipment Replacement and Upgrades | Special | in service | C0018500 | 7192.62
C0026102 | 2020 Substation Theft Prevention | Provincial | Provincial | Equipment Replacement and Upgrades | Special | in service | C0027202 | -51312.08
C0043571 | 2022-2023 Transmission Switch & B | Provincial | Provincial | Equipment Replacement and Upgrades | Special | in service | C0046592 | 1874829.4
C0041828 | Auto-Regen Breather Retrofit Progra | Provincial | Provincial | Equipment Replacement and Upgrades | Special | in service | C0045710 | 102494.24
C0031274 | 2021 Cap Bank Breaker Replacements | Provincial | Provincial | Equipment Replacement and Upgrades | Special | in service | C0035949 | 342932.55
C0034209 | 1C-GT2 Transformer Failure | 1C | Cape Breton | Equipment Replacement and Upgrades | Special | open | C0038290 | 25189.86
C0032382 | Susie Lake Substation Addition | N/A | Provincial | Load Growth | Special | open | C0033126 | 3309289.04
C0031042 | 5P-MS Rewind | Provincial | Provincial | Equipment Replacement and Upgrades | Special | open | C0037407 | 83017.52
C0031044 | 67N-713 230 kV Breaker Replacem | 67N | Northeast | Equipment Replacement and Upgrades | Special | in service | C0055384 | 622.05
C0050852 | 10V-T1 Transformer Replacement | 10V | West | Equipment Replacement and Upgrades | Special | in service | C0064092 | 1621390.24
C0071888 | 92H-T61 Transformer Replacement | 92H | Metro | Equipment Replacement and Upgrades | Special | open | C0073111 | 188052.92
C0075911 | 2025 Substation Fence Upgrades | Provincial | Provincial | Equipment Replacement and Upgrades | Special | in service | C0076474 | 384776.31
C0080258 | 62N-T1 Transformer Replacement | 62N | Northeast | Equipment Replacement and Upgrades | Special | open | C0082528 | 552837.59
49838-T924 | 2017 Substation PCB Equip Rplcmnt | Provincial | Provincial | Equipment Replacement and Upgrades | Special | posted to CPR | T924 | -5228.06
51403 | T-2018 PCB Removal Program | Provincial | Provincial | Equipment Replacement and Upgrades | Special | in service | C0007439 | 124962.8
52314 | 1C-GT1/UT1 Replacement | 1C | Cape Breton | Equipment Replacement and Upgrades | Special | posted to CPR | C0008900 | 172350.75
48131 | 48H-T1 Replacement | 48H | Metro | Equipment Replacement and Upgrades | Special | posted to CPR | C0008918 | 13292.04
C0011039 | 5V-GT1 Generating Transformer | 5V | West | Equipment Replacement and Upgrades | Special | posted to CPR | C0026642 | 718002.92
C0010956 | 78W-Martins Brook Substation Reloc | 78W | West | Equipment Replacement and Upgrades | Special | in service | C0023022 | 4385866.17
C0010978 | T-2019/2020 Tran Switch & Breaker R | Provincial | Provincial | Equipment Replacement and Upgrades | Special | in service | C0014779 | 386072.56
C0011358 | New Bridgewater Substation | N/A | Provincial | Load Growth | Special | open | C0064088 | 2257632.66
C0022283 | 58C-T1 Margaree Failed Transformer | 58C | Cape Breton | Equipment Replacement and Upgrades | Special | posted to CPR | C0026446 | 47035.73
C0037907 | 5V-501 Switch & Structure Replace | 5V | West | Equipment Replacement and Upgrades | Special | posted to CPR | C0046321 | 783031.12
C0031051 | Pennsylvania Breaker Replacements | Provincial | Provincial | Equipment Replacement and Upgrades | Special | open | C0046314 | 297461.04
C0056240 | 2024-2025 Transmission Switch & Bre | Provincial | Provincial | Equipment Replacement and Upgrades | Special | in service | C0061629 | 3156825.05
C0053158 | 77V-T52 Transformer Replacement | 77V | West | Equipment Replacement and Upgrades | Special | open | C0064091 | 16475.7
C0062123 | 143H-Mount Uniacke Substation | 143H | Metro | Load Growth | Special | in service | C0064085 | 7159859.2
C0057682 | Spare Transformer Replacement | Provincial | Provincial | Equipment Replacement and Upgrades | Special | open | C0064086 | 2041602.45
C0067866 | 2024 Substation Recloser Replacemen | Provincial | Provincial | Equipment Replacement and Upgrades | Special | open | C0069906 | 228422.01
C0076251 | 2025 Substation Theft Prevention | Provincial | Provincial | Equipment Replacement and Upgrades | Special | in service | C0076431 | 408499.21
C0080092 | Stillwater Lake Substation Addition | N/A | Metro | Equipment Replacement and Upgrades | Special | open | C0080093 | 2181.38
49818-T923 | 2017/2018 Tx Switch & Breaker Rplmt | Provincial | Provincial | Equipment Replacement and Upgrades | Special | posted to CPR | T923 | 51619.8
23121-T004-820 | PROVINCIAL- SUBSTATION ADDITIONS & | Provincial | Provincial | Equipment Replacement and Upgrades | T004-TRANSMISSION SUBSTATION ADDITI | open | T004-820 | 4386040.13
14973-T018-820 | PRIMARY EQUIPMENT SPARES | Provincial | Provincial | Equipment Replacement and Upgrades | T018-PRIMARY EQUIP.SPARES-ROUTINES | open | T018-820 | 726825.05
14841-T016-630 | PROTECTION MODIFICATIONS AND REPLAC | Provincial | Provincial | Protection and Control System Improvement | T016-PROTECTION MOD.& REPL.1994 | open | T016-630 | 4256534.92
52328 | 56N-T1 Transformer Upgrades | 56N | Northeast | Equipment Replacement and Upgrades | Special | in service | C0008358 | 160473.25
52238 | 2018/2019 Capacitor Bank Breaker Re | Provincial | Provincial | Equipment Replacement and Upgrades | Special | in service | C0004936 | 102925.71
49879-T928 | 77V-T52 Replacement | 77V | West | Equipment Replacement and Upgrades | Special | posted to CPR | T928 | 1226.27
48057-T965 | Replace 69kV cables between 2S& 83S | 2S, 83S | Cape Breton | Equipment Replacement and Upgrades | Special | posted to CPR | T965 | -5508.26
C0023182 | 101S Woodbine Reactor Replacement | 101S | Cape Breton | Equipment Replacement and Upgrades | Special | in service | C0027502 | 64472.45
C0021323 | 50N-Trenton Replace 50N-T13 | 50N | Northeast | Equipment Replacement and Upgrades | Special | in service | C0028043 | 1276713.23
C0021122 | 2020-21 Transmission Switch and Br | Provincial | Provincial | Equipment Replacement and Upgrades | Special | in service | C0024562 | 859328.91
C0021130 | 48H Metalclad Switchgear Replacemen | 48H | Metro | Equipment Replacement and Upgrades | Special | posted to CPR | C0029605 | 100815.81
C0032745 | 89H Oil Spill Remediation | 89H | Metro | Equipment Replacement and Upgrades | Special | posted to CPR | C0033667 | 93772.23
C0061883 | 129H - Kearney Lake Substation Rebu | 129H | Metro | Equipment Replacement and Upgrades | Special | open | C0068698 | 55532.73
C0058902 | Substation Engineering Standards Up | Provincial | Provincial | Equipment Replacement and Upgrades | Special | open | C0063843 | 417845.02
C0053214 | 76W-T1 Transformer Replacement | 76W | West | Equipment Replacement and Upgrades | Special | open | C0064087 | 2077282.59
C0057882 | 2024 Pennsylvania Breaker Replace | Provincial | Provincial | Equipment Replacement and Upgrades | Special | in service | C0059345 | 531098.66
C0071889 | 77V-T1 Transformer Replacement | 77V | West | Equipment Replacement and Upgrades | Special | open | C0073110 | 10571.02
C0073188 | Replacement of 87S GT1 H3 Bushing | 87S | Cape Breton | Equipment Replacement and Upgrades | Special | in service | C0073510 | 466606.21
C0069394 | 16N-T1 Transformer Replacement | 16N | Northeast | Equipment Replacement and Upgrades | Special | open | C0069647 | 2949.7
C0068868 | 145H - Wellington Substation | 145H | Metro | Load Growth | Special | open | C0069988 | 76785.69
C0068961 | 2025 PCB Subst Sampling and Replace | Provincial | Provincial | Equipment Replacement and Upgrades | Special | in service | C0080583 | 52461.55
51956 | 6P Mobile Substation Rewind | Provincial | Provincial | Equipment Replacement and Upgrades | Special | in service | C0031324 | 436.29
43268 | 9W-B53 Tusket Replace Structure | 9W | West | Equipment Replacement and Upgrades | Special | open | C0005139 | 38.18
48059-T877 | 2016 Switch and Breaker Replacement | Provincial | Provincial | Equipment Replacement and Upgrades | Special | posted to CPR | T877 | 596.9
C0014019 | 2019 Substation Recloser Replace | Provincial | Provincial | Equipment Replacement and Upgrades | Special | in service | C0017033 | 980388.19
C0010952 | 2019/20 Substation PCB Equip Replac | Provincial | Provincial | Equipment Replacement and Upgrades | Special | in service | C0014778 | 382528.76
C0022744 | 2020 Oil Containment Program | Provincial | Provincial | Equipment Replacement and Upgrades | Special | open | C0026523 | 59587.51
C0027362 | 2020 Petroleum Storage Tank Replace | Provincial | Provincial | Equipment Replacement and Upgrades | Special | in service | C0028543 | 554354.83
C0021026 | Replace Willow Lane Power Transform | 15N | Northeast | Equipment Replacement and Upgrades | Special | in service | C0028063 | 1124209.27
C0048114 | 88S-301 Switchgear Replacement | 88S | Cape Breton | Equipment Replacement and Upgrades | Special | in service | C0049113 | 922550.55
C0058103 | 2023 Merlin Gerin Breaker Replaceme | Provincial | Provincial | Equipment Replacement and Upgrades | Special | in service | C0059346 | 521012.92
C0063266 | Porter’s Lake Feeder Addition | 126H | Metro | Equipment Replacement and Upgrades | Special | in service | C0064083 | 301893.29
C0072089 | 2P Mobile Transformer Replacement | Provincial | Provincial | Equipment Replacement and Upgrades | Special | open | C0073109 | 18564.56
C0068969 | 2026 Pennsylvania Breaker Replaceme | Provincial | Provincial | Equipment Replacement and Upgrades | Special | open | C0073112 | 37661.61
C0069392 | 12V-T1 Transformer Replacement | 12V | West | Equipment Replacement and Upgrades | Special | open | C0069646 | 17601.04
C0070086 | 10H-T2 Transformer Replacement | 10H | Metro | Equipment Replacement and Upgrades | Special | open | C0071648 | 24359.59
C0070586 | 22N-603 and 604 Switch Repl L6536 | 22N | Northeast | Equipment Replacement and Upgrades | Special | open | C0071649 | 94309.19
C0072308 | 147H Windmill Road Substation Addit | 147H | Metro | Load Growth | Special | open | C0080091 | 17538.99