## Sheet1
Feeder | Region | Depot | Targeted Equipment Replacements | Protection Upgrade | Load Growth | Bring to Roadside | Vegetation Work | 2026 Priority Feeder (Y/N) | 2025 Investment | 2026 Planned Investment Projects
100C-421 | Cape Breton | PHA |  |  |  | C | C | N | 1.5 km BTR, 4.5 km reconductoring (Harve Boucher Rebuild), 22.5 km of vegetation management | 18.5 km of vegetation management
103C-314 | Cape Breton | CHC | C |  |  |  |  | Y | Poletop transformer replacements, pole replacements, neutral repairs | Grand Etang Water Crossing (0.9 km BTR, 0.92 reconductoring), 0.9 km of vegetation management
11S-411 | Cape Breton | SYD |  |  |  |  | C | N | 1.4 km of vegetation management | FLISR project, 9.6 km of vegetation management
22C-403 | Cape Breton | PHA |  | In Progress |  |  |  | N | RTU addition - commissiong in May 2026 | 7.9 km of vegetation management
22C-404 | Cape Breton | PHA |  | C |  |  |  | Y | Recloser installed, RTU addition - commissioning in May 2026, Lennox passage project servicing Isle Madame | 14C-211 Boudreauville Rd Conversion (2.13 km of reconductoring), 9.5 km of vegetation management
3S-403 | Cape Breton | SYD |  |  |  |  | C | N | 17.2 km of vegetation management | 30.2 km of vegetation management
57S-401 | Cape Breton | SYD | C | C |  |  |  | N | Trip Saver installation, pin insulator replacements, cutout replacements, pole replacements | 4.4 km of vegetation management
57S-402 | Cape Breton | SYD | C |  |  |  |  | N | Pin insulator replacements, cutout replacements, pole replacements | 12.6 km of vegetation management
58C-403 | Cape Breton | CHC | C | C | C |  | C | Y | RTU installed, pole replacements, neutral repairs, completed Deepdale conversion project (5.86 km of conductor replacement), 5.9 km of vegetation management | 3.0 km of vegetation management
59C-402 | Cape Breton | RIB |  |  |  |  | C | N | 1.3 km of vegetation management
81S-305 | Cape Breton | SYD | C |  |  |  |  | N | Pole replacements
81S-307 | Cape Breton | SYD | C |  |  |  |  | N | Pole replacements
85S-401 | Cape Breton | ING |  | C |  |  | C | Y | Trip Saver installation, 5.3 km of vegetation management | FLISR project, Wreck Cove Rebuild (0.4 km or BTR and 1.28 km reconductoring), 20.1 km of vegetation management
104H-421 | Metro | HFX | C |  |  |  |  | N | Pole replacments
113H-433 | Metro | DAR | C | C |  |  | C | N | Trip Saver Installed, pole replacements, 1.3 km of vegetation management | 5.0 km of vegetation management
126H-311 | Metro | DAR | C |  | C |  | C | N | Pole replaced, New feeder exit(126H), 3.1 km of vegetation management | 20.4 km of vegetation management
137H-412 | Metro | BAY | C |  |  |  | C | N | Pole replacements, load balancing work, new regulators installed, 0.9 km of vegetation management | 7.9 km of vegetation management
82V-402 | Metro | SAC | C |  |  |  | C | Y | Pole replacements, pin insulator replacements, autosleeve replacements, 6.8 km of vegetation management | New build on Aerotech Connector (2026/2027), 6.7 km of vegetation management
24C-442 | Northeast | GUY |  | C |  |  |  | N | Recloser replacement
30N-412 | Northeast | AMH | C |  |  |  | C | N | Replaced stepdown, 12.3 km of vegetation management | 0.8 km of vegetation management
37N-411 | Northeast | PAR |  |  |  |  | C | N | 17.0 km of vegetation management | Pole replacments and reconductoring project
4C-430 | Northeast | ANT | C |  |  |  | C | Y | Pole replacements, 30.4 km of vegetation management | Voltage regulator replacement, 17.7 km of vegetation management
4C-441 | Northeast | ANT | C |  | C |  | C | N | Pole replacements (Trans Canada Highway 104 Twinning project), 3.2 km of vegetation management | Highway 104 Twinning Project (ongoing), 13.9 km of vegetation management
4N-313 | Northeast | AMH | C | C |  |  |  | N | Trip Saver installation, pole replacements, RTU complete | 9.2 km of vegetation management
50N-410 | Northeast | STE | C |  |  |  | C | N | Recloser installation, pole replacements, 12.4 km of vegetation management | Ongoing work to service Big Island
56N-414 | Northeast | STE | C | C |  |  | C | N | Tripsaver installation, pole replacements, 15.7 km of vegetation management | 11.2 km of vegetation management
57C-426 | Northeast | GUY | C |  |  |  | C | Y | 57C-426 Stillwater Phase Extension (3.30km single phase to 3phase upgrade), 0.3 km of vegetation management | Melrose Country Harbour Rd Rebuild (0.5 km of reconductoring, 5.2 km phase extension), 21.9 km of vegetation management
6N-302 | Northeast | AMH | C |  |  |  |  | N | Pole replacements | 0.4 km of vegetation management
82V-401 | Northeast | SAC | C |  |  |  | C | N | Pin insulator replacments, cutout replacements, 0.5 km of vegetation management
88H-401 | Northeast | TRU | C |  |  |  | C | N | Pole replacments, 0.3 km of vegetation management
96H-411 | Northeast | TRU |  |  | C |  |  | N | 3.2 km of reconductoring (Beaver Harbout Rd Phase Extension) | 14.8 km of vegetation management
96H-412 | Northeast | TRU |  |  | C |  |  | N | Phase 1 complete to be able to eliminate majority of offroad section (to be completed in future phase). | 11.0 km of vegetation management
16W-301 | West | YAR | C |  |  |  | C | N | Hebron Phase 2 (4.2 km BTR, 9.13 km reconductor), Highway 1 rebuild (0.37 BTR, 1.46 reconductor), Pembroke Rd Rebuild (2.838 km reconductor), 0.2 km of vegetation management | 1.5 km of vegetation management
23W-302 | West | SHE | C |  |  |  | C | N | Pin insulator and cutouts, pole replacements, 0.3 km of vegetation management | 0.2 km of vegetation management
25W-301 | West | SHE | C | C |  |  | C | Y | Pole replacements, Poletop TX replacmenets, RTU completed, 27.4 km of vegetation management | Welshtown phase extension (4.3 km), 6.2 km of vegetation management
57W-401 | West | LIV |  | C | C |  | C | N | 2 Tripsavers installed, New Elm Rd conversion (BTR - 0.2, reconductor - 0.30), 0.3 km of vegetation management | 4.6 km of vegetation management
57W-402 | West | LIV | C |  |  |  | C | N | Pole replacement, 0.4 km of vegetation management | 0.9 km of vegetation management
70W-311 | West | DIG | C | C |  |  | C | N | Tripsaver installation, pole replacements , 5.3 km of vegetation management | 3.8 km of vegetation management
70W-313 | West | DIG | C |  |  |  | C | N | Pole replacements, tree trimming to support pole replacements, 1.6 km of vegetation management | 13.8 km of vegetation management
73W-411 | West | BRW | C |  |  |  | C | N | Pole replacements, 24.1 km of vegetation management | 25.7 km of vegetation management
76V-301 | West | LIV |  |  |  | C | C | N | 0.9 km BTR (Maitland Bridge Build to Roadside), 0.4 km of vegetation management | Substation transformer replacement, 0.2 km of vegetation management
78W-301 | West | BRW |  | C | C |  |  | N | Tripsaver installation, Added second phase to Heckman island (0.5 km reconductoring) | 9.6 km of vegetation management
78W-302 | West | BRW | C |  | C |  |  | N | Pole replacement, New Substation
80W-301 | West | BRW | C | C |  |  |  | N | Tripsaver installation, RTU addition | 10.5 km of vegetation management
91W-411 | West | LIV |  | C |  |  |  | Y | 4 Tripsaver installations | 91W-411 Labelle Phase Extension (15.87km reconductoring, 5.29 km phase extension), 15.6 km of vegetation management
93V-313 | West | CLA | C |  |  |  |  | N | Pole replacements | 3.9 km of vegetation management