## R1 - Summary
NS Power 2026 Capital Spend Detail - As per 2026 ACE Plan
2nd Quarter Overview - as of June 30, 2026
| Generation | Distribution | Transmission | General Property | Total NS Power
2026 ACE Plan Total
2026 Submitted ACE Total | 178201702 | 190470777 | 241059096 | 92358890 | 702090465
Total YTD Spend | 77304577.5863 | 97844221.8092 | 25747691.509 | 18413786.22 | 219310277.1246
Variance YTD/ACE Spend | -100897124.4137 | -92626555.1908 | -215311404.491 | -73945103.78 | -482780187.8754
Percentage of ACE Spent as of June 30, 2026 | 43.38% | 51.37% | 10.68% | 19.94% | 31.24%
Add:
ATOs | -508489 | 0 | 7962232.6002 | 0 | 7453743.6002
U&Us/P&As | 302488 | 1545084 | -42079 | 0 | 1805493
Changes to ACE Items for Subsequent Approval | 42352 | 2194370 | 1758103 | 460230.97 | 4455055.97
Total Increase | -163649 | 3739454 | 9678256.6002 | 460230.97 | 13714292.5702
Less:
Projects cancelled | -2884093.0138 | 0 | 0 | -140000 | -3024093.0138
Projects deferred | -7254297.5977 | -1092310.2895 | -256374.4538 | -5541986 | -14144968.341
Total Decrease | -10138390.6115 | -1092310.2895 | -256374.4538 | -5681986 | -17169061.3548
2026 Potential Capital Spend* | 167899662.3885 | 193117920.7105 | 250480978.1464 | 87137134.97 | 698635696.2154
* Amounts do not reflect the reforecast of capital projects since the 2026 ACE Plan submission, or reforecasting of subsequent items filed.

## R2 - Capital Items Status
NS Power Capital Item Status Update
2nd Quarter Overview - as of June 30, 2026
This report includes all projects submitted to the NSEB and remain active, as well as ACE Plan subsequent submittal projects. Projects are removed from this report once the project has been final costed (internal or external), cancelled, or falls below $1M.
Status | Category | CI Number | Title | ACE Plan Reference (or U&U and P&A) | Submission/Date | ACE Amount | Submission or Approved Amount | Actual Spend | FIN Submission Date | FIN Amount | Variance
Deferred | Generation | 39472 | HYD - Mersey Redevelopment Phase 1 | 2022 ACE Plan (for Subsequent Approval) |  | 189447075.51 |  | 20794651.2
Approved | General Plant | 47751 | ECC Dynamic Line Rating Implementation | 2022 ACE Plan (for Subsequent Approval) | OTQ - December 1, 2025 | 5144525.08 | 2148364 | 2293018.09
Approved | Generation | 49634 | HYD - Trout River Diversion Structure Replacement | 2022 ACE Plan (for Subsequent Approval) | Q1 - May 13, 2024 | 1822299.7 | 3402776 | 3309527.65
Approved | Distribution | 49919 | 2017 PCB Pole Top Transformer Replacement | 2017 ACE Plan | 2017 ACE Plan | 2446051.2 | 2446051.2 | 2550546.67
Approved | Transmission | 43267 | 13V Gulch Hydro Replace 13V-GT1 and 13V-VR1 | 2015 ACE Plan | 2015 ACE Plan | 1061901.92 | 1061901.92 | 1011993.16
Approved | Transmission | 49815 | 2017 / 2018 Steel Tower Refurbishment | 2017 ACE Plan | 2017 ACE Plan | 2003316.81 | 2003316.81 | 1937432.56
Approved | Distribution | 47787 | 2H Armdale New Feeders | 2017 ACE Plan (for Subsequent Approval) | OTQ - April 6, 2020 | 1285679 | 1734221 | 1723920.45
Approved | Distribution | 47124 | Advanced Metering Infrastructure | 2017 ACE Plan (for Subsequent Approval) | OTQ - February 17, 2023 | 8274738 | 143495843.8622 | 142957143.03
Approved | Transmission | 51403 | 2018 PCB Removal Program | 2018 ACE Plan | 2018 ACE Plan | 4402342 | 4402342 | 3533546.34
Approved | Transmission | 52258 | 2018/2019 Isolated Structure Replacement | 2018 ACE Plan | 2018 ACE Plan | 4818521 | 4818521 | 294849.4
Approved | Transmission | 51398 | 2018/2019 Steel Tower Refurbishment | 2018 ACE Plan | 2018 ACE Plan | 1992692 | 1992692 | 2055803.57
Approved | Distribution | 51493 | 2018 PCB Pole Top Transformer Replacement | 2018 ACE Plan | 2018 ACE Plan | 1360354 | 1360354 | 1384292.41
Approved | Transmission | 52328 | 56N-T1 Transformer Upgrades | 2018 ACE Plan | 2018 ACE Plan | 1279271 | 1279271 | 1307910.2
Approved | Transmission | 51975 | 5P Mobile Substation Replacement | 2018 ACE Plan | 2018 ACE Plan | 4829458 | 4829458 | 2982405.69
Approved | Distribution | C0011208 | 2019 Padmount Replacement Program | 2019 ACE Plan | 2019 ACE Plan | 1413544 | 1413544 | 1496465.72
Approved | Generation | 48914 | HYD - Malay Falls Facility Repair | 2017 ACE Plan (for Subsequent Approval) | Q3 2017 - October 30, 2017 | 446237 | 1034045 | 1311457.38
Approved | Generation | 47551 | HYD - SHH Controls Upgrade | 2016 ACE Plan (for Subsequent Approval) | Q4 2015 - January 29, 2016 | 1092850.61 | 1749212 | 1956464.95
Deferred | Generation | 49942 | HYD - Tidewater Facility Refurbishment | 2018 ACE Plan | 2018 ACE Plan | 1234178 | 1234178 | 1445671
Withdrawn | Generation | 29807 | HYD - Tusket Falls Main Dam | 2017 ACE Plan (for Subsequent Approval) | OTQ - July 23, 2021 | 9940664 | 36826119 | 26481378.21
Approved | Generation | 51234 | HYD - WRC HVAC Upgrade | 2018 ACE Plan | 2018 ACE Plan | 1876537 | 1876537 | 1883160.61
Approved | Generation | 48791 | HYD - WRC Safety Standards Upgrades | 2018 ACE Plan (for Subsequent Approval) | OTQ - June 4, 2018 | 1019927.73 | 1760570 | 1919440.54
Approved | Generation | 51236 | HYD - WRC Tailrace Rock Bolting | 2018 ACE Plan | 2018 ACE Plan | 8861996 | 8861996 | 7853800.09
Approved | Generation | 48052 | HYD Annapolis HVAC Upgrade | 2017 ACE Plan (for Subsequent Approval) | OTQ - March 8, 2017 | 1498367 | 1573596 | 1854917.5
Approved | Generation | 44978 | HYD-Wreck Cove Automation | 2015 ACE Plan (for Subsequent Approval) | Q2 2015 - July 31, 2015 | 2379999.4 | 3802446.04 | 4027159.78
Deferred | General Plant | 49600 | IT - Network Architecture Redesign | 2017 ACE Plan (for Subsequent Approval) |  | 1183826 |  | 0
Approved | General Plant | 49855 | IT Desktop SW Modernization | 2017 ACE Plan (for Subsequent Approval) | Q3 2017 - October 30, 2017 | 2013034 | 4620515.89 | 4501620.94
Approved | Transmission | 47950 | L5017 Replacements & Upgrades | 2016 ACE Plan | Q1 2018 - May 7, 2018 | 2182142.33 | 3062664 | 3012632.2
Approved | Transmission | 47949 | L5028 Replacements and Upgrades | 2016 ACE Plan | 2016 ACE Plan | 1144354.64 | 1144354.64 | 943265
Approved | Transmission | 49778 | L5535 Replacements and Upgrades | 2017 ACE Plan | OTQ - April 16, 2018 | 1261920.05 | 2590269 | 2837177.2
Approved | Transmission | 49779 | L6537 Replacements and Upgrades | 2018 ACE Plan | OTQ - March 4, 2019 | 1255220 | 2331474.13 | 2284615.84
Approved | Transmission | 52320 | L6549 2018 Replacements & Upgrades | 2018 ACE Plan | 2018 ACE Plan | 1406535 | 1406535 | 1452522.7
Approved | Transmission | 44987 | L7003 Lidar Upgrades | 2015 ACE Plan (for Subsequent Approval) | OTQ - August 31, 2015 | 6885816.76 | 11032275 | 10907019.52
Approved | Transmission | 49793 | L7011 Replacements and Upgrades | 2017 ACE Plan | OTQ - April 1, 2019 | 3343484.22 | 4810276 | 4591706.24
Approved | Transmission | 47954 | L7012 Replacements and Upgrades | 2017 ACE Plan | 2017 ACE Plan | 4428519.78 | 4428519.78 | 4392085.97
Approved | Generation | 49940 | LM6000 TUC5 Control System Upgrade | 2017 ACE Plan (for Subsequent Approval) | OTQ - July 3, 2018 | 1018769 | 1275559 | 1070496.11
Approved | Transmission | C0001900 | Mount Hope 69-25kV Substation | 2018 ACE Plan | 2018 ACE Plan | 2982338 | 2982338 | 2998217.15
Approved | Transmission | 52323 | Port Hastings 2C BPS Upgrade | P&A | Q2 - August 7, 2018 | 0 | 4201448.53 | 3997957.67
Approved | General Plant | 50153 | Self Serve Development Phase 2 | 2017 ACE Plan (for Subsequent Approval) | OTQ - September 15, 2017 | 1827720 | 1160528 | 1316269.11
Approved | Transmission | 43678 | Separate L8004/L7005 on Canso Crossing Double Circuit Tower(DCT) | 2017 ACE Plan (for Subsequent Approval) | OTQ - January 27, 2022 | 16183691 | 20387278 | 20387277.51
Approved | Transmission | 45066 | Upgrade L6511 and L7019 Thermal Rating | 2015 ACE Plan (for Subsequent Approval) | OTQ - January 27, 2022 | 3693032.91 | 2691017 | 2691016.62
Approved | Transmission | 43324 | Replace L6513 / Upgrade Line Terminals | 2015 ACE Plan (for Subsequent Approval) | OTQ - January 27, 2022 | 23429902 | 18626428 | 18625268.15
Approved | Transmission | 45067 | 67N Onslow 345 KV Node Swap | 2014 ACE Plan (for Subsequent Approval) | OTQ - January 27, 2022 | 3006487 | 2982714 | 2982585.13
Approved | Transmission | 48022 | Spider Lake Substation Addition | 2016 ACE Plan (for Subsequent Approval) | OTQ - March 4, 2019 | 6348980.72 | 9158260 | 9066397.53
Approved | Generation | 50518 | HYD - Ruth Falls Main Dam Refurbishment | 2019 ACE Plan | OTQ - October 11, 2024 | 7244422 | 14839116 | 16201679.8
Approved | Transmission | C0010042 | 2019 Transmission Right-of-Way Widening 69kV | 2019 ACE Plan | 2019 ACE Plan | 5650794 | 5650794 | 5634125.15
Approved | Transmission | C0010948 | 2019/2020 Sacrificial Anode Installation Program | 2019 ACE Plan | 2019 ACE Plan | 3099862 | 3099862 | 3244208.44
Approved | Transmission | C0010952 | 2019/2020 Substation Polychlorinated Biphenyl (PCB) Equipment Removal | 2019 ACE Plan | 2019 ACE Plan | 2786245 | 2786245 | 2805720.1
Approved | Transmission | C0010949 | 2019/2020 Steel Tower Life Extension | 2019 ACE Plan | 2019 ACE Plan | 2414140 | 2414140 | 2178231.16
Approved | Transmission | C0011339 | L6549 - Replacements and Upgrades Phase 2 | 2019 ACE Plan | Q1 - May 13, 2024 | 2209907 | 3993973.66 | 3912347.44
Approved | Transmission | C0011241 | L5026 - Replacements and Upgrades | 2019 ACE Plan | 2019 ACE Plan | 1498789 | 1498789 | 1379562.67
Approved | Transmission | C0010978 | 2019/2020 Transmission Switch & Breaker Replacement | 2019 ACE Plan | 2019 ACE Plan | 1044148 | 1044148 | 1029498.49
Approved | Transmission | C0011243 | L5551 - Replacements and Upgrades | 2019 ACE Plan | 2019 ACE Plan | 1014077 | 1014077 | 1115386.39
Approved | Distribution | C0006319 | 2019 PCB Pole Top Transformer Replacements | 2019 ACE Plan | 2019 ACE Plan | 1177592 | 1177592 | 1418556.64
Approved | Distribution | C0020623 | New Distribution Rights-of-Way Phase 5 | 2020 ACE Plan | 2020 ACE Plan | 10015266.14 | 10015266.14 | 9930357.98
Approved | General Plant | C0013438 | IT - T&D WAM Phase 1 - GIS and Field Design System | 2019 ACE Plan (2018 Pending Submission) | OTQ - December 7, 2018 | 7978434 | 7978434 | 8098332.98
Partial Approval | Generation | C0013838 | HYD WRC LEM Unit Rehabilitation | 2020 ACE Plan (2019 Pending Submission) | OTQ - February 21, 2020 | 109691966.51 | 101787264 | 103794143.21
Approved | Distribution | C0020835 | 2020 Padmount Replacement Program | 2020 ACE Plan | 2020 ACE Plan | 1612389.23 | 1612389.23 | 1519347.68
Approved | General Plant | C0011378 | Route Network Upgrades | 2020 ACE Plan (2019 Pending Submission) | OTQ - December 2, 2019 | 5724239.86 | 5717751.93 | 5957115.29
Approved | General Plant | 49480 | IT - Data Centre Disaster Recovery | 2020 ACE Plan (2019 Pending Submission) | OTQ - December 2, 2019 | 6103797.71 | 6335161.85 | 6249505.23
Approved | General Plant | C0010838 | MCC - HVAC Replacement | 2019 ACE Plan (for Subsequent Approval) | OTQ - October 4, 2021 | 1071364 | 1606253.82 | 1531909.94
Approved | General Plant | C0002137 | ECC - Map Board and Technology Modernization | 2019 ACE Plan (for Subsequent Approval) | Q3 - November 4, 2019 | 2568789 | 2506267.89 | 2274252.27
Approved | Transmission | C0021105 | L7002 Replacements and Upgrades Phase 2 | P&A | Q3 - November 4, 2019 | 0 | 3121441.58 | 3320026.92
Approved | Distribution | C0020834 | 2020/2021 Inaccessible PCB Transformer Replacements | 2020 ACE Plan | 2020 ACE Plan | 2950294.39 | 2950294.39 | 3098664.09
Approved | Transmission | C0020627 | 2020 Transmission Right-of-Way Widening 69kV | 2020 ACE Plan | 2020 ACE Plan | 5489820 | 5489820 | 5617281.86
Approved | Transmission | C0011261 | 101W Port Mersey Substation Expansion | 2020 ACE Plan | 2020 ACE Plan | 4651384 | 4651384 | 4740341.05
Approved | Transmission | C0021123 | 2020/2021 Substation Polychlorinated Biphenyl (PCB) Equipment Removal | 2020 ACE Plan | 2020 ACE Plan | 5197371.63 | 5197371.63 | 5445009.73
Approved | Generation | 49949 | LM6000 TUC4 Control System Replacement | 2020 ACE Plan | 2020 ACE Plan | 1149996.27 | 1149996.27 | 901773.45
Approved | Transmission | C0011321 | L5031 Replacements and Upgrades Phase 1 | 2020 ACE Plan | 2020 ACE Plan | 2147211.75 | 2147211.75 | 368503.89
Approved | Transmission | C0021107 | L8001 Replacements and Upgrades Phase 1 | 2020 ACE Plan | 2020 ACE Plan | 2292092.86 | 2292092.86 | 2517260.08
Approved | Distribution | C0021182 | 93V-313-Meteghan Rebuild | 2020 ACE Plan | 2020 ACE Plan | 1075624.51 | 1075624.51 | 932729.86
Approved | Transmission | C0021122 | 2020/2021 Transmission Switch & Breaker Replacement | 2020 ACE Plan | 2020 ACE Plan | 1312642.8 | 1312642.8 | 1528837.36
Approved | Distribution | C0010778 | Smart Grid Nova Scotia Project | 2020 ACE Plan (for Subsequent Approval) | OTQ - December 5, 2019 | 6740589.05 | 7053622 | 6661381.46
Approved | General Plant | C0021109 | New RTU Deployment Project | 2020 ACE Plan | 2020 ACE Plan | 8028097.17 | 8028097.17 | 8016288.65
Approved | Transmission | 52303 | L7019 Replacements and Upgrades | 2020 ACE Plan | 2020 ACE Plan | 1374091.91 | 1374091.91 | 1383195.98
Approved | Transmission | C0021026 | Willow Lane 15N-T3 Replacement | 2020 ACE Plan | 2020 ACE Plan | 1326646.57 | 1326646.57 | 1179586.14
Approved | Generation | 49756 | HYD - Marshall Falls Main Dam Refurbishment | 2020 ACE Plan | 2020 ACE Plan | 5452793.82 | 5452793.82 | 784634.56
Approved | Transmission | C0021142 | 19W-T51 Transformer Replacement | 2020 ACE Plan | 2020 ACE Plan | 1512336.33 | 1512336.33 | 1473278.51
Approved | Distribution | C0019379 | 50N-410 - 4C-430 Highway 104 Twinning | 2020 ACE Plan (for Subsequent Approval) | OTQ - June 1, 2020 | 1361237.37 | 1137222.61 | 1228890.76
Approved | Distribution | C0031083 | New Distribution Rights-of-Way Phase 6 | 2021 ACE Plan | 2021 ACE Plan | 9762734.52 | 9762734.52 | 9705372.68
Approved | Distribution | C0031145 | 2021 Padmount Replacement Program | 2021 ACE Plan | 2021 ACE Plan | 1636152.76 | 1636152.76 | 1387171.24
Approved | General Plant | C0023622 | AMO Substation and Transmission APM Program | 2020 ACE Plan (for Subsequent Approval) | OTQ - April 6, 2020 | 2087848.28 | 2217589 | 2369151.05
Partial Approval | Generation | C0014218 | HYD WRC LEM Balance of Plant | 2021 ACE Plan (2020 Pending Submission) | OTQ - April 30, 2021 | 21186378.42 | 27637896 | 20356662.85
Approved | General Plant | C0023623 | AMO Distribution APM Program | 2020 ACE Plan (for Subsequent Approval) | OTQ - April 6, 2020 | 1708239.85 | 1721484.45 | 1817941.65
Approved | Generation | 16374 | HYD Gaspereau Dam Safety | 2008 ACE Plan | OTQ - February 23, 2020 | 4354889 | 22703451 | 12632274.78
Approved | Distribution | 47794 | Heckman's Island Submarine Cable Replacement | 2021 ACE Plan (for Subsequent Approval) | Q1 2021 - May 3, 2021 | 1296112.43 | 1338363.88 | 1554825.72
Approved | Transmission | C0031263 | 2021/2022 Substation Polychlorinated Biphenyl (PCB) Equipment Removal | 2021 ACE Plan | 2021 ACE Plan | 7512225.73 | 7512225.73 | 7063077.68
Approved | Transmission | C0031089 | 2021/2022 Transmission Right-of-Way Widening 69kV | 2021 ACE Plan | 2021 ACE Plan | 5288520 | 5288520 | 5512846.46
Approved | Transmission | C0031122 | L6539 Replacements and Upgrades | 2021 ACE Plan | OTQ - April 7, 2025 | 2821842.28 | 5584042.12 | 2288119.74
Approved | Transmission | C0031085 | L6516 Line Replacement and Upgrades | 2021 ACE Plan | 2021 ACE Plan | 2730591.81 | 2730591.81 | 2544182.7
Approved | Transmission | C0031050 | New Spare Large Autotransformer | 2021 ACE Plan | 2021 ACE Plan | 2398564.03 | 2398564.03 | 2374092.32
Approved | Transmission | C0033644 | 2021/2022 Steel Tower Life Extension | 2021 ACE Plan | 2021 ACE Plan | 2332745.87 | 2332745.87 | 1831087.15
Approved | Transmission | C0033645 | 2021/2022 Steel Tower Refurbishment | 2021 ACE Plan | 2021 ACE Plan | 1944004.84 | 1944004.84 | 2186409.35
Approved | Distribution | C0041892 | New Distribution Rights-of-Way Phase 7 | 2022 ACE Plan | 2022 ACE Plan | 9854290.53 | 9854290.53 | 10222016.49
Approved | Transmission | C0031262 | 2020/2021 Transmission Switch and Breaker Replacement | 2021 ACE Plan | 2021 ACE Plan | 1483047.6 | 1483047.6 | 1456536.81
Approved | Transmission | C0031064 | L5054 Replacements and Upgrades | 2021 ACE Plan | 2021 ACE Plan | 1134737.48 | 1134737.48 | 996871.76
Approved | Generation | 46483 | CT - TUS Control System Upgrade | 2021 ACE Plan | 2021 ACE Plan | 1046322.12 | 1046322.12 | 1095272.71
Approved | Generation | C0026285 | TRE Heavy Fuel Oil Tank Refurbishment | 2021 ACE Plan (for Subsequent Approval) | OTQ - June 10, 2021 | 1732920.72 | 2979545.51 | 2463573.91
Approved | General Plant | C0030987 | IT - NERC CIP Environment Refresh | 2022 ACE Plan (2021 Pending Submission) | OTQ - March 7, 2022 | 1446131 | 1259927 | 1309292.99
Approved | Distribution | C0043130 | 2022 Padmount Replacement Program | 2022 ACE Plan | 2022 ACE Plan | 1807359.37 | 1807359.37 | 1970143.99
Approved | Transmission | C0041893 | 2022/2023 Transmission Right-of-Way Widening 69kV | 2022 ACE Plan | 2022 ACE Plan | 5312315 | 5312315 | 5187077.9
Approved | Transmission | C0041837 | 2022/2023 Substation Polychlorinated Biphenyl (PCB) Equipment Removal | 2022 ACE Plan | 2022 ACE Plan | 3805434.21 | 3805434.21 | 4030363.97
Approved | Transmission | C0041793 | L7002 Replacements and Upgrades Phase 2 | 2022 ACE Plan | 2022 ACE Plan | 3640960.16 | 3640960.16 | 3856222.93
Approved | Transmission | C0041989 | 2022/2023 Sacrificial Anode Installation Program | 2022 ACE Plan | 2022 ACE Plan | 3015106.56 | 3015106.56 | 2773422.66
Approved | Transmission | C0041791 | L6551 Replacements and Upgrades | 2022 ACE Plan | 2022 ACE Plan | 1988245.66 | 1988245.66 | 1644803
Approved | Distribution | C0008638 | Cogswell HRM Redevelopment Program | 2022 ACE Plan (for Subsequent Approval) | OTQ - June 6, 2022 | 6982854.44 | 6617148.24 | 7352165.1
Approved | Transmission | C0043571 | 2022/2023 Transmission Switch & Breaker Replacement | 2022 ACE Plan | 2022 ACE Plan | 1612637.79 | 1612637.79 | 1807566.06
Approved | Generation | C0036368 | HYD - Lower Great Brook Switchgear Replacement | 2022 ACE Plan | 2022 ACE Plan | 1362281.36 | 1362281.36 | 1408559.63
Approved | Transmission | C0041804 | 2022 Line Retirement Program | 2022 ACE Plan | 2022 ACE Plan | 1242178.29 | 1242178.29 | 404428.57
Approved | Generation | C0024484 | HYD - Fourth Lake Switchgear Replacement | 2022 ACE Plan | 2022 ACE Plan | 1145245.46 | 1145245.46 | 1534862.33
Approved | Generation | C0029691 | CT - VJ1 Control System Upgrade | 2022 ACE Plan | 2022 ACE Plan | 1016224.92 | 1016224.92 | 1002085.09
Approved | Transmission | C0045132 | ECEI - Battery Energy Storage System Project | 2022 ACE Plan (for Subsequent Approval) | OTQ - January 25, 2024 | 171207919.79 | 237772259 | 209043401.57
Deferred | Generation | C0044392 | Eastern Clean Energy Initiative (ECEI) - Coal Conversion | 2022 ACE Plan (for Subsequent Approval) |  | 32341324.51 |  | 1810843.13
Deferred | Generation | C0034486 | HYD - WRC LEM Penstock intake | 2022 ACE Plan (for Subsequent Approval) |  | 11239850.61 |  | 1212689.4
Approved | Generation | C0000979 | HYD - Governor Dam Refurbishment | 2022 ACE Plan (for Subsequent Approval) | OTQ - November 6, 2023 | 2696629.84 | 4844345.32 | 4959267.89
Approved | Distribution | C0022662 | 22C-404GA Lennox Passage Rebuild | 2022 ACE Plan (for Subsequent Approval) | OTQ - July 4, 2022 | 2352190.78 | 2609595.48 | 2737982.6
Deferred | Transmission | C0036826 | L8004 Parallel Canso Strait Crossing | 2022 ACE Plan (for Subsequent Approval) |  | 2139081.25 |  | 0
Approved | General Plant | C0041994 | NERC CIP 2022 | 2022 ACE Plan (for Subsequent Approval) | OTQ - April 4, 2022 | 1379473.59 | 1247663 | 1185536.49
Approved | Generation | C0041651 | TUC HFO Tank 4 Refurbishment | 2022 ACE Plan (for Subsequent Approval) | Q4 - February 6, 2023 | 1110292.77 | 2734313 | 2756903.42
Approved | Transmission | C0010956 | 78W-Martin’s Brook Substation Relocation | P&A | OTQ - March 3, 2025 | 0 | 5122761 | 4644543.66
Approved | Transmission | C0045510 | 20V-T52 Transformer Replacement | U&U | Q3 - November 7, 2022 | 0 | 1506565.52 | 1520670.88
Approved | Transmission | C0041807 | L5534 Replacements and Upgrades | P&A | OTQ - December 5, 2022 | 0 | 1426418.29 | 1834031.47
Approved | Transmission | C0049212 | L8001 Replacements and Upgrades Phase 3 | P&A | OTQ - December 5, 2022 | 0 | 1263906.4 | 1234810.94
Approved | Transmission | C0050835 | 2023/2024 Steel Tower Refurbishment | P&A | OTQ - December 5, 2022 | 0 | 2056634.87 | 1682553.34
Approved | Transmission | C0052055 | 2023/2024 Transmission Right-of-Way Widening 69kV | P&A | OTQ - December 5, 2022 | 0 | 5332315 | 5336846.68
Approved | Distribution | C0042687 | 15N-202 Arthur St Conversion | 2022 ACE Plan (Less than $1M) | OTQ - April 7, 2025 | 718195 | 1399459 | 1218300.3
Approved | Transmission | C0052634 | L5016 Replacements and Upgrades | P&A | OTQ - December 5, 2022 | 0 | 2697636.73 | 2928322.3
Approved | Distribution | C0052056 | New Distribution Rights-of-Way Phase 8 | P&A | OTQ - December 5, 2022 | 0 | 9796663.1 | 9088167.29
Approved | Generation | C0001222 | CT BGT1 Engine Exchange | P&A | OTQ - January 9, 2023 | 0 | 2338747 | 2350941.06
Approved | Generation | C0055376 | TUC1 - LP Blade Refurbishment U&U | U&U | Q4 - February 6, 2023 | 0 | 2025440.22 | 1910054.3
Approved | Generation | C0041506 | LM6000 Engine 191-253 Refurbishment | 2023 ACE Plan | OTQ - March 7, 2024 | 8740978.85 | 13473407 | 13033734.84
Approved | Generation | C0012838 | HYD - Lequille Canal Dyke, Gates and Tailrace Refurbishment | 2023 ACE Plan | 2023 ACE Plan | 7058816.14 | 7058816.14 | 5978049.55
Approved | Generation | C0029682 | CT VJ2 - Replace Generator Assembly | 2023 ACE Plan | 2023 ACE Plan | 5397737.93 | 5397737.93 | 4500647.92
Approved | Generation | C0051134 | TUC2 - L-0 Blade Replacement | 2023 ACE Plan | 2023 ACE Plan | 4157503.35 | 4157503.35 | 4171422.09
Approved | Transmission | C0041788 | L6516 Replacements and Upgrades Phase 2 | 2023 ACE Plan | OTQ July 2, 2024 | 3123474.28 | 5442793.92 | 4673704.13
Approved | Transmission | C0055539 | 10H-T1 Transformer Replacement | 2023 ACE Plan | 2023 ACE Plan | 2420891.67 | 2420891.67 | 1651316.71
Approved | Transmission | C0052299 | 2023/2024 Steel Tower Life Extension | 2023 ACE Plan | 2023 ACE Plan | 2195463.46 | 2195463.46 | 1963099.63
Approved | Transmission | C0055796 | 2023 EHV Breaker Replacements | 2023 ACE Plan | OTQ - October 2, 2023 | 2048410.56 | 3463488.74 | 2980152.53
Approved | Transmission | C0055696 | L5031 Replacement and Upgrades Robinson Corner Tap | 2023 ACE Plan | 2023 ACE Plan | 1357477.23 | 1357477.23 | 1388629.34
Approved | Distribution | C0050836 | 2023 Padmount Replacement Program | 2023 ACE Plan | 2023 ACE Plan | 1309551.39 | 1309551.39 | 1350020.88
Approved | Generation | C0051135 | TUC2 - Turbine Valves Refurbishment 2023 | 2023 ACE Plan | 2023 ACE Plan | 1048924 | 1048924 | 966694.39
Awaiting Approval | Transmission | C0052654 | L5541 Water Crossing Upgrades | 2023 ACE Plan | OTQ - July 13, 2026 | 1047073.87 | 2265295 | 43865.45
Approved | Transmission | C0053316 | Michelin Voltage Sag Reduction DVR | 2023 ACE Plan (for Subsequent Approval) | OTQ - April 12, 2024 | 21007507.1 | 31170675 | 32673501.99
Approved | General Plant | C0042166 | IT - Data Loss Prevention (DLP) Platform | 2023 ACE Plan (for Subsequent Approval) | OTQ - June 7, 2023 | 3233905.29 | 4261239.1945 | 3944258.36
Approved | Generation | C0051894 | TUC - HFO Tank 3 Refurbishment | 2023 ACE Plan (for Subsequent Approval) | OTQ - March 7, 2024 | 2053937.48 | 2218012 | 2249814.18
Approved | Generation | C0044030 | WIN - DIG Haight's Brook Crossing Replacement | 2023 ACE Plan (for Subsequent Approval) | OTQ - November 6, 2023 | 2046984.81 | 2024051.53 | 304985.51
Approved | Transmission | C0055557 | 76V-T1 Transformer Replacement | 2023 ACE Plan (for Subsequent Approval) | OTQ - April 7, 2025 | 1751258.26 | 3244386 | 3647383.69
Approved | General Plant | C0011167 | IT - Backup Infrastructure Upgrade | 2023 ACE Plan (for Subsequent Approval) | OTQ - June 7, 2023 | 1557470.73 | 2315457.44 | 2324003.44
Approved | Generation | C0048591 | CT VJ1 Engine P686621 Refurbishment | P&A | OTQ - March 6, 2023 | 0 | 2312509.06 | 2283878.09
Approved | Generation | C0054356 | TUC – Roof Replacement U&U | U&U | OTQ - March 6, 2023 | 0 | 1459455.09 | 1412184.76
Approved | Generation | C0053916 | CT BGT4 Engine P686630 Refurbishment | U&U | OTQ - April 3, 2023 | 0 | 1850500.99 | 1718317.45
Approved | Transmission | C0031052 | Replenish Spare Transformer Used at 58C | 2021 ACE Plan (Less than $1M) | OTQ - June 7, 2023 | 982910 | 1303826.93 | 1188276.71
Approved | Generation | 51761 | LIN2 2022/2023 Winter Capacity Requirement | U&U | OTQ - September 5, 2023 | 0 | 2512340.71 | 2526651.43
Approved | Generation | C0006418 | HYD WRC Tailrace Tunnel Rock Bolting Phase 2 | 2024 ACE Plan | 2024 ACE Plan | 15722669.17 | 15722669.17 | 12426318.95
Approved | General Plant | C0047277 | IT - GIS Utility Network Upgrade | 2024 ACE Plan | 2024 ACE Plan | 6175229.82 | 6175229.82 | 3635245.77
Approved | Generation | C0049013 | HYD - Lower Great Brook Log Hoist Replacement | 2024 ACE Plan | 2024 ACE Plan | 2158657.9 | 2158657.9 | 1864619.2
Approved | Generation | C0049032 | HYD - Cowie Falls Log Hoist Replacement | 2024 ACE Plan | 2024 ACE Plan | 2237991.11 | 2237991.11 | 1888467.06
Approved | General Plant | C0049619 | IT - ERP Upgrade (EBS, PS, PP, OBIA) | 2024 ACE Plan | 2024 ACE Plan | 6198799.37 | 6198799.37 | 5636484.11
Approved | Transmission | C0050842 | 2024 Bulk Oil Breaker Replacement Program | 2024 ACE Plan | 2024 ACE Plan | 3274755.9 | 3274755.9 | 1328604.12
Approved | Generation | C0051136 | TUC2 - HP/IP Turbine Refurbishment | 2024 ACE Plan | 2024 ACE Plan | 4264777.44 | 5965028 | 6248459.47
Approved | Transmission | C0056240 | 2024/2025 Transmission Switch and Breaker Replacements | 2024 ACE Plan | 2024 ACE Plan | 3271621.79 | 3271621.79 | 3309341.33
Approved | Distribution | C0057142 | New Distribution Rights-of-Way Phase 9 | 2024 ACE Plan | 2024 ACE Plan | 19141913.7 | 19141913.7 | 19189121.4
Approved | Transmission | C0057882 | 2024 Pennsylvania Breaker Replacements | 2024 ACE Plan | 2024 ACE Plan | 2163831.86 | 2163831.86 | 887797.69
Approved | Generation | C0058942 | WRC D11-2 Foundation Stabilization | 2024 ACE Plan | 2024 ACE Plan | 1540602.39 | 1540602.39 | 1416577.81
Awaiting Approval | Transmission | C0059046 | 101S and 79N Reactor Replacements | 2024 ACE Plan | 2024 ACE Plan | 1460062.22 | 1460062.22 | 827209.38 | Q2 - August 4, 2026 | 827209 | -632853.22
Approved | Generation | C0060608 | TUC6 Turbine Refurbishment | 2024 ACE Plan | 2024 ACE Plan | 2472311.19 | 2472311.19 | 605286.98
Approved | Generation | C0060707 | CT BGT1 Generator Refurbishment | 2024 ACE Plan | 2024 ACE Plan | 3482602.45 | 3482602.45 | 328891.82
Approved | Distribution | C0060749 | 2024 Padmount Replacement Program | 2024 ACE Plan | 2024 ACE Plan | 1288197.9 | 1288197.9 | 1369449.15
Approved | Transmission | C0061023 | 2024 EHV Breaker Replacements | 2024 ACE Plan | 2024 ACE Plan | 3638479.75 | 3638479.75 | 5140.71
Approved | Transmission | C0061046 | 2024 Merlin Gerin Breaker Replacements | 2024 ACE Plan | 2024 ACE Plan | 1169590.5 | 1169590.5 | 363157.45
Approved | Transmission | C0061387 | 2024 2025 Wood Pole Retreatment Program | 2024 ACE Plan | 2024 ACE Plan | 1209391.21 | 1209391.21 | 260431.5
Approved | Transmission | C0061403 | 2024 2025 Sacrificial Anode Installation Program | 2024 ACE Plan | 2024 ACE Plan | 2382112.6 | 2382112.6 | 2560068.92
Approved | Transmission | C0061545 | L6006 Replacements and Upgrades | 2024 ACE Plan | 2024 ACE Plan | 5032640.4 | 5032640.4 | 5241799.85
Approved | Transmission | C0061546 | L6514 Replacements and Upgrades | 2024 ACE Plan | 2024 ACE Plan | 2102666.38 | 2102666.38 | 2086020.14
Approved | Transmission | C0061547 | L7022 Replacements and Upgrades | 2024 ACE Plan | 2024 ACE Plan | 2283568.76 | 2283568.76 | 2424405.52
Awaiting Approval | Transmission | C0061550 | L5031 Replacements and Upgrades - Hubbards to East Chester | 2024 ACE Plan | OTQ - July 13, 2026 | 5297583.52 | 6957058 | 3942226.11
Approved | Transmission | C0061551 | L7009 Replacements and Upgrades | 2024 ACE Plan | 2024 ACE Plan | 3280328.4 | 3280328.4 | 1342263.19
Approved | Transmission | C0061743 | L6038 Realignment | 2024 ACE Plan | 2024 ACE Plan | 1032910.93 | 1032910.93 | 1118758.04
Approved | Transmission | C0061883 | 129H - Kearney Lake Substation Rebuild | 2024 ACE Plan | 2024 ACE Plan | 1017322.14 | 1017322.14 | 154129.4
Approved | General Plant | C0054755 | IT - Connect My Data (Green Button) | 2024 ACE Plan (for Subsequent Approval) | Q4 - February 5, 2024 | 2309350.36 | 2964237 | 3289249.43
Deferred | Transmission | C0031286 | Spare Padmounted Substation | 2024 ACE Plan (for Subsequent Approval) |  | 1319837.87 |  | 0
Approved | General Plant | C0032664 | ECC Optimization Tools Project | 2024 ACE Plan (for Subsequent Approval) | OTQ - December 1, 2025 | 4329149.97 | 7486068 | 7820418.65
Approved | Generation | C0050414 | HYD Roseway Asset Decommissioning | 2024 ACE Plan (for Subsequent Approval) | OTQ - December 20, 2024 | 4650648.04 | 4915649 | 3806214.95
Approved | Generation | C0060816 | POT - HFO Tank Refurbishment | 2024 ACE Plan (for Subsequent Approval) | OTQ - December 17, 2024 | 2012802.82 | 3684622 | 3614578.49
Deferred | General Plant | C0061287 | IT - Third Party Risk Management | 2024 ACE Plan (for Subsequent Approval) |  | 1405970.41 |  | 0
Approved | General Plant | C0061289 | IT - Network Next Generation Security Design | 2024 ACE Plan (for Subsequent Approval) | OTQ - April 7, 2025 | 2632635 | 1814215.74 | 1626318.16
Approved | Distribution | C0061521 | New Distribution Rights-of-Way Phase 10 | 2024 ACE Plan (for Subsequent Approval) | OTQ - October 7, 2024 | 18904608 | 20890176 | 21586567.69
Approved | Generation | C0038126 | HYD Cowie Falls Unit 12 Overhaul | 2024 ACE Plan (Less than $1M) | Q1 - May 13, 2024 | 964521.17 | 1274890 | 1339565.79
Approved | Generation | C0053655 | HYD Cowie Falls Unit 11 Overhaul | 2023 ACE Plan (Less than $1M) | Q1 - May 13, 2024 | 913947.02 | 1225491 | 1289638.55
Approved | Generation | C0059283 | LIN2 PE 2023/2024 Winter Capacity Requirements | U&U | Q1 - May 13, 2024 | 0 | 1661834 | 1663743.67
Approved | Transmission | C0062123 | 143H-Mount Uniacke Substation | P&A | Q2 - August 6, 2024 | 0 | 9040869 | 8173031.62
Approved | General Plant | C0056461 | IT - Contact Centre Cloud Migration | 2024 ACE Plan (for Subsequent Approval) | OTQ - September 16, 2024 | 929372 | 3237539 | 2839327.27
Approved | Transmission | C0031048 | 91H-T11 Transformer Replacement | 2025 ACE Plan | 2025 ACE Plan | 6914621.96 | 6914621.96 | 5380979.85
Approved | Generation | C0039266 | HYD - Gulch Overhaul | 2025 ACE Plan | 2025 ACE Plan | 1371379.09 | 1371379.09 | 1255121.96
Approved | Generation | C0048990 | HYD AVO 2 Switchgear Replacement | 2025 ACE Plan | 2025 ACE Plan | 1814631.36 | 1814631.36 | 1363796.73
Approved | Transmission | C0050834 | Spare EHV Breaker Replacements | 2025 ACE Plan | 2025 ACE Plan | 1178831.81 | 1178831.81 | 1328636.53
Approved | Transmission | C0050852 | 10V-T1 Transformer Replacement | 2025 ACE Plan | 2025 ACE Plan | 2113336.98 | 2113336.98 | 1701221.74
Approved | General Plant | C0051815 | RTU Replacements Program Phase 6 | 2025 ACE Plan | OTQ - July 10, 2026 | 5959915.27 | 4665372 | 1739602.18
Awaiting Approval | Transmission | C0053295 | L5004 Kearney Lake Structure Replacement | 2025 ACE Plan | Q2 - August 4, 2026 | 2478536.78 | 6836784 | 1230106.98
Approved | Transmission | C0057682 | Spare Transformer Replacement | 2025 ACE Plan | 2025 ACE Plan | 2286389.47 | 2286389.47 | 2011680.21
Awaiting Approval | Generation | C0068659 | TRE5 - IP-LP Turbine Refurbishment | 2025 ACE Plan | OTQ - July 13, 2026 | 1282669.84 | 2963160 | 3038759.71
Approved | Distribution | C0068786 | 2025 Padmount Replacement Program | 2025 ACE Plan | 2025 ACE Plan | 1354219.4 | 1354219.4 | 1019116.54
Approved | Generation | C0068882 | TUC1 Generator Refurbishment | 2025 ACE Plan | 2025 ACE Plan | 2124210.74 | 2124210.74 | 897385.83
Approved | Generation | C0068887 | TUC3 Turbine Valves Refurbishment | 2025 ACE Plan | 2025 ACE Plan | 1869103.9 | 1869103.9 | 1960910.28
Approved | Distribution | C0068952 | 2025 PCB Poletop Sampling and Replacement | 2025 ACE Plan | 2025 ACE Plan | 7158973.99 | 7158973.99 | 2743016.59
Approved | Distribution | C0068953 | 2025 PCB Light Replacement | 2025 ACE Plan | 2025 ACE Plan | 4225224.41 | 4225224.41 | 0
Approved | Distribution | C0068954 | 2025 PCB Downline Device Sampling and Replacement | 2025 ACE Plan | 2025 ACE Plan | 1716718.39 | 1716718.39 | 0
Approved | Transmission | C0068961 | 2025 PCB Substation Sampling and Replacement | 2025 ACE Plan | 2025 ACE Plan | 6650932.5 | 6650932.5 | 254560.44
Approved | Transmission | C0069227 | L6516 Replacements and Upgrades Phase 3 | 2025 ACE Plan | 2025 ACE Plan | 3104924.75 | 3104924.75 | 2212694.98
Approved | Transmission | C0069231 | L8002 Replacements and Upgrades Phase 1 | 2025 ACE Plan | 2025 ACE Plan | 3093175.63 | 3093175.63 | 2106491.39
Approved | Transmission | C0069232 | L6021 Replacements and Upgrades Phase 1 | 2025 ACE Plan | 2025 ACE Plan | 3253068.08 | 3253068.08 | 1719507.72
Deferred | Transmission | C0069238 | 2025/2026 Steel Tower Refurbishment | 2025 ACE Plan | 2025 ACE Plan | 2337250.27 | 2337250.27 | 0
Approved | General Plant | C0069270 | 2025 SCADA/EMS Upgrade | 2025 ACE Plan | 2025 ACE Plan | 1306288.06 | 1306288.06 | 283687.59
Approved | Transmission | C0070048 | L5027B Replacements and Upgrades Phase 1 | 2025 ACE Plan | 2025 ACE Plan | 2916727.9 | 2916727.9 | 1643331.54
Approved | Distribution | C0070787 | 91W-411 Labelle Road Phase Extension | 2025 ACE Plan | 2025 ACE Plan | 1150615.99 | 1150615.99 | 874778.39
Deferred | General Plant | C0070907 | MDR-8000 Microwave Radio Replacement | 2025 ACE Plan | 2025 ACE Plan | 1572477.91 | 1572477.91 | 1539.04
Deferred | Generation | 48913 | HYD - Tusket Facility Refurbishment | 2025 ACE Plan (for Subsequent Approval) |  | 12972226.16 |  | 1308167.86
Deferred | Transmission | C0011358 | New Bridgewater Substation | 2025 ACE Plan (for Subsequent Approval) |  | 18173046.53 |  | 233700.9
Approved | Transmission | C0021140 | New 138KV-25KV Substation Stellarton | 2025 ACE Plan (for Subsequent Approval) | Q1 - May 16, 2025 | 10511998.19 | 12960396 | 5180317.36
Approved | Transmission | C0041830 | Spare Power Production Unit Transformer | 2025 ACE Plan (for Subsequent Approval) | OTQ - April 7, 2025 | 1264622.46 | 1266552.19 | 1257331.4
Approved | General Plant | C0053699 | Renewable to Retail Implementation | 2025 ACE Plan (for Subsequent Approval) | OTQ - December 1, 2025 | 5062652.18 | 5644468 | 4805713.4
Approved | Generation | C0059783 | HYD Upper Lake Falls 2 Overhaul | 2025 ACE Plan (for Subsequent Approval) | OTQ - September 9, 2025 | 1678152.72 | 1582014 | 137279.78
Approved | General Plant | C0061284 | IT - OT Cyber Security Control Implementation | 2025 ACE Plan (for Subsequent Approval) | OTQ - March 3, 2025 | 5459312.92 | 6826426 | 2923507.98
Approved | Generation | C0063803 | HYD AVO 2 Access Road Stabilization | 2025 ACE Plan (for Subsequent Approval) | OTQ - April 7, 2025 | 2406283.37 | 1862825.78 | 278488.95
Approved | Generation | C0067023 | LIN2 2024/25 Capacity Requirement | 2025 ACE Plan (for Subsequent Approval) | OTQ - June 9, 2025 | 1083800.37 | 1257127 | 1287652.21
Approved | Generation | C0068566 | LIN DCS Upgrade 2025 | 2025 ACE Plan (for Subsequent Approval) | Q1 - May 16, 2025 | 1440910.59 | 1544190 | 1303674.21
Approved | Generation | C0068655 | LM6000 191-332 Life Extension | 2025 ACE Plan (for Subsequent Approval) | Q2 - August 5, 2025 | 6013453.54 | 18948560 | 18892424.15
Approved | Generation | C0069166 | POT-Turbine Valve Refurbishment | 2025 ACE Plan (for Subsequent Approval) | OTQ - June 6, 2026 | 2872597.56 | 1544021 | 1444621.37
Approved | Generation | C0070486 | HYD LGB Stoplog Replacement | 2025 ACE Plan (for Subsequent Approval) | OTQ - December 1, 2025 | 1288403.9 | 3593884 | 2896459.71
Approved | Distribution | C0071528 | FLISR Implementation | 2025 ACE Plan (for Subsequent Approval) | Q2 - August 5, 2025 | 5299247.73 | 4638245 | 778864.94
Approved | Generation | C0061003 | POA LP HP IP Turbine Refurbishment | 2025 ACE Plan (for Subsequent Approval) | OTQ - July 7, 2025 | 4155130.87 | 4861261 | 5196518.83
Approved | Generation | C0061005 | POA Cell Capping 2025 | 2025 ACE Plan (for Subsequent Approval) | OTQ - July 7, 2025 | 3255439.91 | 2530405 | 2055136.8
Approved | Generation | C0067906 | POA Boiler Refurbishment 2025 | 2025 ACE Plan (for Subsequent Approval) | OTQ - July 7, 2025 | 1213152.46 | 1218254 | 1423703.62
Approved | Generation | C0067908 | POA Boiler Refractory Refurbishment 2025 | 2025 ACE Plan (for Subsequent Approval) | OTQ - July 7, 2025 | 1089478.33 | 1378466 | 1394074.64
Approved | General Plant | C0011159 | Plant Information System Upgrade | 2024 ACE Plan (Less than $1M) | OTQ - March 3, 2025 | 362679 | 1142652 | 1045029.79
Approved | Distribution | C0080104 | 36V-303 Baxter's Harbour Rd Reconductor Phase 1 | 2026 ACE Plan | 2026 ACE Plan | 1062416 | 1062416 | 509130.92
Approved | Generation | C0049192 | HYD - GUL Generator Refurbishment | 2025 ACE Plan (Less than $1M) | Q1 - May 16, 2025 | 732043 | 1316589 | 834283.66
Approved | Generation | C0068662 | TRE5 Baghouse Filter Replacement | 2025 ACE Plan (Less than $1M) | Q1 - May 16, 2025 | 534006 | 1241640 | 1335309.4
Approved | Generation | C0073348 | HYD - WRC Surge Lake Volume Optimization | U&U | Q1 - May 16, 2025 | 0 | 1736278 | 678965.22
Approved | Generation | C0073965 | TRE5 U&U Burner Nest Waterwall Tube Replacement | U&U | Q1 - May 16, 2025 | 0 | 2156407 | 756168.6
Approved | General Plant | C0073777 | IT - Complex Customer Projects | P&A | OTQ - June 9, 2025 | 0 | 3025518 | 988297.46
Approved | General Plant | 49036 | HYD - Avon 2 Controls Upgrade | 2025 ACE Plan (Less than $1M) | Q2 - August 5, 2025 | 0 | 1073463 | 779852.5
Approved | Generation | C0073491 | LM6000 191-443 Engine Replacement | P&A | Q2 - August 5, 2025 | 0 | 24217289 | 4579328.51
Approved | Generation | C0067183 | TUC Wharf Access Bridge Replacement | U&U | Q2 - August 5, 2025 | 0 | 2426669 | 2434764.43
Approved | Transmission | C0074130 | Robie Street Underground | P&A | OTQ - September 9, 2025 | 0 | 4465119 | 2611997.76
Approved | Generation | C0080112 | HYD Big Falls Unit 6 Rotor Re-Insulation | U&U | OTQ - October 10, 2025 | 0 | 1025626 | 870890.26
Approved | General Plant | C0053696 | ECC Wind Integration | 2025 ACE Plan (Less than $1M) | OTQ - December 1, 2025 | 757358 | 4428335 | 1276831.79
Approved | Generation | C0080228 | HYD HOB Stator Rewind and Generator Refurbishment | U&U | OTQ - December 1,2025 | 0 | 2587170 | 1994400.34
Approved | Generation | C0021608 | TUC Shoreline Sheetpile Refurbishment | 2026 ACE Plan | 2026 ACE Plan | 5691466 | 5691466 | 450363.97
Approved | Transmission | C0053214 | 76W-T1 Transformer Replacement | 2026 ACE Plan | 2026 ACE Plan | 2818855 | 2818855 | 2172767.42
Approved | Transmission | C0053234 | 96H-T1 Transformer Replacement | 2026 ACE Plan | 2026 ACE Plan | 2056752 | 2056752 | 70919.4
Approved | Generation | C0068888 | TUC3 Continuous Ash Hauling System | 2026 ACE Plan | 2026 ACE Plan | 1359984 | 1359984 | 36568.41
Approved | Generation | C0068898 | TUC1 IP LP Last Stage Blade Replacement | 2026 ACE Plan | 2026 ACE Plan | 5215861 | 5215861 | 5591991.34
Approved | Transmission | C0068969 | 2026 Pennsylvania Breaker Replacements | 2026 ACE Plan | 2026 ACE Plan | 1620028 | 1620028 | 57143.21
Approved | Transmission | C0070586 | L6536 Switch Replacements | 2026 ACE Plan | 2026 ACE Plan | 2074494 | 2074494 | 240552.27
Approved | Transmission | C0070909 | 70W-T52 Transformer Addition | 2026 ACE Plan | 2026 ACE Plan | 3957128 | 3957128 | 23896.72
Approved | Distribution | C0080266 | New Distribution Right of Way Phase 11 | 2026 ACE Plan | 2026 ACE Plan | 20889694 | 20889694 | 10450619.67
Approved | Transmission | C0080109 | L7001 Replacements and Upgrades Phase 1 | 2026 ACE Plan | 2026 ACE Plan | 3063280 | 3063280 | 2278.91
Approved | Transmission | C0080110 | L7012 Replacements and Upgrades Phase 1 | 2026 ACE Plan | 2026 ACE Plan | 5370318 | 5370318 | 8566.89
Awaiting Approval | General Plant | C0080111 | 2026 RTU Deployment Project | 2026 ACE Plan | 2026 ACE Plan | 8322655 | 8322655 | 0
Approved | Generation | C0080133 | TUC3 IP Turbine Refurbishment | 2026 ACE Plan | 2026 ACE Plan | 2588734 | 2588734 | 0
Approved | Generation | C0080134 | TUC2 Stack Coating and Structural Refurbishment | 2026 ACE Plan | 2026 ACE Plan | 4256511 | 4256511 | 0
Approved | Generation | C0080135 | CT - BGT2 Engine Refurbishment | 2026 ACE Plan | 2026 ACE Plan | 2462664 | 2462664 | 256061.71
Approved | Generation | C0080205 | POA Boiler Refractory Replacement 2026 | 2026 ACE Plan | 2026 ACE Plan | 1024385 | 1024385 | 0
Approved | Generation | C0080206 | POA Boiler Refurbishment 2026 | 2026 ACE Plan | 2026 ACE Plan | 1304600 | 1304600 | 0
Approved | General Plant | C0080252 | Intelligent Asset Data Capture & Integration Platform | 2026 ACE Plan | 2026 ACE Plan | 267941 | 267941 | -227358.86
Approved | Distribution | C0080612 | 57C-426H Melrose Reconductor and Line Extension Phase 1 | 2026 ACE Plan | 2026 ACE Plan | 1288474 | 1288474 | 0
Approved | Distribution | C0080101 | 539N-210 Big Island Sub-Sea Cable Replacement | 2026 ACE Plan (for Subsequent Approval) | OTQ - April 9, 2026 | 3539067 | 4388679 | 41825.86
Pending Submission | Generation | 47649 | HYD Salmontail Gate Pedestal and Main Dam Refurbishment | 2026 ACE Plan (for Subsequent Approval) |  | 5870708 |  | 877410.5
Pending Submission | Generation | 47650 | HYD - Annapolis Decision Analysis | 2026 ACE Plan (for Subsequent Approval) |  | 30732442 |  | 3602212.02
Pending Submission | Generation | 49595 | HYD - TUS 1 Overhaul | 2026 ACE Plan (for Subsequent Approval) |  | 5649954 |  | 722902.84
Pending Submission | Transmission | 51098 | L-6014 Shannon Park Transmission Towers | 2026 ACE Plan (for Subsequent Approval) |  | 39471723 |  | 1734022.1
Pending Submission | General Plant | C0000017 | Storm Management Software Implementation | 2026 ACE Plan (for Subsequent Approval) |  | 2235914 |  | 0
Pending Submission | General Plant | C0021835 | IT - CIS Replacement | 2026 ACE Plan (for Subsequent Approval) |  | 84502844 |  | 3687339.49
Pending Submission | Transmission | C0022247 | 1N Onslow Transformer Addition (1N-T66) | 2026 ACE Plan (for Subsequent Approval) |  | 3645131 |  | 2802549.73
Pending Submission | Transmission | C0023802 | L-6515 Canso Causeway Rebuild | 2026 ACE Plan (for Subsequent Approval) |  | 3925352 |  | 446079.68
Pending Submission | General Plant | C0032202 | Sydney Depot Improvements | 2026 ACE Plan (for Subsequent Approval) |  | 2700000 |  | 0
Pending Submission | Transmission | C0032382 | 142H - Susie Lake Substation | 2026 ACE Plan (for Subsequent Approval) |  | 8256386 |  | 3674857.87
Pending Submission | General Plant | C0047278 | IT - Oracle MDM Upgrade | 2026 ACE Plan (for Subsequent Approval) |  | 7949409 |  | 4033821.39
Pending Submission | General Plant | C0047301 | IT - Cloud Integration Platform | 2026 ACE Plan (for Subsequent Approval) |  | 2004962 |  | 1044308.47
Pending Submission | Generation | C0047973 | HYD ANN Sluice Gates and Check Refurbishment | 2026 ACE Plan (for Subsequent Approval) |  | 5673491 |  | 225849.15
Pending Submission | Generation | C0052514 | HYD MacDonald Dam Access Improvements | 2026 ACE Plan (for Subsequent Approval) |  | 1547398 |  | 184048.19
Pending Submission | Generation | C0057361 | HYD ANN Facility Isolation | 2026 ACE Plan (for Subsequent Approval) |  | 4083925 |  | 3429732.12
Approved | Transmission | C0059483 | 83V L-5017 and L-5046 Rebuild Tap | 2026 ACE Plan (for Subsequent Approval) | Q4 - February 26, 2026 | 1207318 | 1558116 | 467885.88
Awaiting Approval | Transmission | C0061552 | L-6043 Replacements and Upgrades | 2026 ACE Plan (for Subsequent Approval) | Q1 - May 4, 2026 | 2457629 | 3603351 | 0
Pending Submission | General Plant | C0062043 | IT - SharePoint Technical Migration | 2026 ACE Plan (for Subsequent Approval) |  | 3134674 |  | 2010013.52
Awaiting Approval | Generation | C0064966 | Tusket Tidal Pool Fish Passage | 2026 ACE Plan (for Subsequent Approval) | OTQ - March 13, 2026 | 1315495 | 1763971 | 1382615.86
Pending Submission | Generation | C0067686 | HYD Lumsden Rubber Dam Replacement | 2026 ACE Plan (for Subsequent Approval) |  | 1304068 |  | 183728.55
Pending Submission | General Plant | C0067863 | IT - Managed Detect & Respond | 2026 ACE Plan (for Subsequent Approval) |  | 2585071 |  | 923776.36
Awaiting Approval | General Plant | C0068714 | IT - Identity & Access Management | 2026 ACE Plan (for Subsequent Approval) | OTQ - March 13, 2026 | 4324589 | 6756522 | 4081483.11
Pending Submission | General Plant | C0068718 | IT - DERMS Solution Project | 2026 ACE Plan (for Subsequent Approval) |  | 2954002 |  | -125429.83
Awaiting Approval | General Plant | C0068719 | IT - Distributed Intelligence Apps | 2026 ACE Plan (for Subsequent Approval) | Q2 - August 4, 2026 | 2637356 | 3165790 | 46012.65
Deferred | General Plant | C0068721 | IT - ADMS Upgrade 2026 | 2026 ACE Plan (for Subsequent Approval) |  | 7200000 |  | 3068.67
Pending Submission | Transmission | C0069534 | IR 669 Network Upgrade Higgins Mountain Wind | 2026 ACE Plan (for Subsequent Approval) |  | 9496174 |  | -402.82
Pending Submission | Transmission | C0070086 | 10H-T2 Transformer Replacement | 2026 ACE Plan (for Subsequent Approval) |  | 2878891 |  | 1669039.29
Pending Submission | Transmission | C0070327 | IR 673 Network Upgrade Benjamins Mill Wind | 2026 ACE Plan (for Subsequent Approval) |  | 265000 |  | -0.01
Pending Submission | Transmission | C0070367 | IR 618 Network Upgrade Goose Harbour Lake Wind | 2026 ACE Plan (for Subsequent Approval) |  | 11015684 |  | 53.25
Pending Submission | Transmission | C0071888 | 92H-T61 Transformer Replacement | 2026 ACE Plan (for Subsequent Approval) |  | 4141223 |  | 330257.99
Pending Submission | Transmission | C0071889 | 77V-T1 Transformer Replacement | 2026 ACE Plan (for Subsequent Approval) |  | 3486796 |  | 91072.44
Pending Submission | Transmission | C0072808 | ECEI Synchronous Condensers | 2026 ACE Plan (for Subsequent Approval) |  | 364566804 |  | 1356434.23
Pending Submission | Generation | C0073368 | HYD Malay Falls Rubber Dam | 2026 ACE Plan (for Subsequent Approval) |  | 2237339 |  | 145709.61
Pending Submission | Generation | C0076273 | Bear Head Ash Management Site - Life Extension | 2026 ACE Plan (for Subsequent Approval) |  | 10148108 |  | 749082.59
Approved | Generation | C0084033 | RC SCR Bridge 10.10 Refurbishment | 2026 ACE Plan (for Subsequent Approval) | Q1 - May 4, 2026 | 1353592 | 1008941 | 176556.98
Approved | Distribution | C0080102 | 92H-331 Double Circuit Peggy's Cove Rd | 2026 ACE Plan (for Subsequent Approval) | OTQ - March 13, 2026 | 1882573 | 4303210 | 206452.07
Pending Submission | Transmission | C0080107 | L-5532 Reliability Upgrade - 91W Middle Field Substation | 2026 ACE Plan (for Subsequent Approval) |  | 3053526 |  | 7236.57
Approved | Transmission | C0080108 | L-5532 Replacements and Upgrades Phase 1 | 2026 ACE Plan (for Subsequent Approval) | OTQ - April 9, 2026 | 2490532 | 3455473 | 685655.68
Pending Submission | Generation | C0080219 | HYD Deep Brook Spillway & Intake Refurbishment | 2026 ACE Plan (for Subsequent Approval) |  | 3142201 |  | 179960.53
Approved | Generation | C0080671 | LIN1 HP IP Turbine Refurbishment 2026 | 2026 ACE Plan (for Subsequent Approval) | OTQ - March 13, 2026 | 3244992 | 3249384 | 1362.71
Pending Submission | Generation | C0080691 | LIN3 DCS Migration 2026 | 2026 ACE Plan (for Subsequent Approval) |  | 1359218 |  | 0
Pending Submission | Generation | C0080732 | POA Ash Cell Capping/ Cell Development 2026 | 2026 ACE Plan (for Subsequent Approval) |  | 2420358 |  | 883.27
Deferred | Generation | C0080768 | POT - CW Pump & Motor Replacement | 2026 ACE Plan (for Subsequent Approval) |  | 2872183 |  | 0
Pending Submission | Transmission | C0081985 | Michelin DVR Phase 2 | 2026 ACE Plan (for Subsequent Approval) |  | 13000000 |  | 5210001.61
Approved | General Plant | C0082133 | IT - Renew Microsoft Enterprise Agreement | 2026 ACE Plan (for Subsequent Approval) | Q1 - May 4, 2026 | 1800000 | 1814873 | 68491
Awaiting Approval | Generation | C0082195 | LIN2 2025/26 Capacity Requirement | 2026 ACE Plan (for Subsequent Approval) | OTQ - July 13, 2026 | 3162203 | 4392251 | 4392251
Awaiting Approval | Transmission | C0044172 | L7005 Canso Crossing Vibration Mitigation | P&A | Q1 - May 4, 2026 | 0 | 2431095 | 2581538.87
Approved | Generation | C0080150 | TUC1 HP Turbine Refurbishment | U&U | Q1 - May 4, 2026 | 0 | 2527606 | 2397100.93
Approved | Distribution | C0083589 | IR751 Brooklyn Community Solar | U&U | Q1 - May 4, 2026 | 0 | 0 | 3531.59
Approved | Distribution | C0083591 | IR746 Petpeswick Community Solar | U&U | Q1 - May 4, 2026 | 0 | 0 | 0
Awaiting Approval | Transmission | C0082085 | 67C-T64 Transformer Replacement | U&U | OTQ - June 6, 2026 | 0 | 2418415 | 2400606.88
Awaiting Approval | Distribution | C0083451 | Seton Ridge Underground Network | U&U | OTQ - June 6, 2026 | 0 | 3656609 | 0

## R3 - Deferred or Cancelled
NS Power 2026 ACE Plan Items – Deferred or Cancelled
2nd Quarter Overview - as of June 30, 2026
This report includes any deferred or cancelled projects that were included in the 2026 ACE Plan. | [9 empty] | Remove before filing
CI | Project Title | 2026 ACE Amount | 2026 ACE Project Total | Cancelled / Deferred | Deferred To | Prior Approval | 2026 ACE Plan Reference | Commentary
[10 empty] | Generation | Distribution | Transmission | General Plant
[9 empty] | Cancelled | 2884093.0138 | 0 | 0 | 140000 | 3024093.0138
Generation | [8 empty] | Deferred | 7254297.5977 | 1092310.2895 | 256374.4538 | 5541986 | 14144968.341
C0076672 | ICP - RC SCR Bridge 10.10 Refurbishment | 1102575 | 1353592.1 | Cancelled |  |  | Subsequent Submittal | Replaced by new CI number (C0084033). | [5 empty] | 17169061.3548
C0070306 | PP FW Valve Critical Spare | 423942.8588 | 453486.0288 | Deferred | 2027 |  | Less than $1M | Deferred due to unplanned carry-over and U&U capital work utilizing available resources. The existing approach to management of this asset is expected to address near term risks. |  | 10138390.6115 | 1092310.2895 | 256374.4538 | 5681986 | 17169061.3548
C0080866 | TUC1 Enhanced Monitoring | 204442.5494 | 204442.5494 | Deferred | 2027 |  | Less than $1M | Deferred due to unplanned carry-over and U&U capital work utilizing available resources. The existing approach to management of this asset is expected to address near term risks. |  | 0 | 0 | 0 | 0 | 0
C0080291 | CT Gas Compressor Refubishment | 447731.75 | 447731.75 | Cancelled |  |  | Less than $1M | Cancelled as the scope of this project will now be included in CIs C0080304 East Gas Compressor B and C0080330 West Gas Compressor B.
C0080277 | BGT1 Vibration System Upgrade | 150421.2757 | 150421.2757 | Deferred | 2027 |  | Less than $1M | Deferred to better define project scope. The existing approach to management of this asset is expected to address near term risks.
C0080272 | BGT Switch Gear Doors Replacement | 39917.595 | 39917.595 | Cancelled |  |  | Less than $1M | Cancelled as other alternative technical solutions were utilized to mitigate risk and avoid replacement at this time.
C0080392 | TUS Fencing Replacement | 10038.556 | 10038.556 | Deferred | 2027 |  | Less than $1M | Deferred as updated condition assessments indicated that the fencing is still in acceptable condition, and could remain in-service for an additional year.
C0080391 | TUS Battery Bank Relocation | 9957.478 | 9957.478 | Cancelled |  |  | Less than $1M | Cancelled as engineering did further investigation and determined project was not required.
C0038876 | HYD - HMS Veritcal Boring Mill Repl | 159439.3112 | 159439.3112 | Deferred | 2027 |  | Less than $1M | Deferred due to delays in material availability from suppliers.
C0038134 | HYD LUM Crane Replacement | 149630.3701 | 149630.3701 | Deferred | 2027 |  | Less than $1M | Deferred due to higher priority work utilizing available resources. The existing approach to management of this asset is expected to address near term risks.
C0080709 | LIN4 RH1 Boiler Tube Replacement 2026 | 411936.7353 | 411936.7353 | Cancelled |  |  | Less than $1M | Cancelled as engineering did further investigation and determined project was not required.
C0080696 | LIN3 SCC Drive Replacement | 242371.5784 | 242371.5784 | Deferred | 2028 |  | Less than $1M | Deferred due to higher priority work utilizing available resources. The existing approach to management of this asset is expected to address near term risks.
C0080647 | LIN Emergency Flyte Pump Replacement | 182728.2669 | 182728.2669 | Deferred | 2028 |  | Less than $1M | Deferred due to higher priority work utilizing available resources. The existing approach to management of this asset is expected to address near term risks.
C0080747 | POA Fire System Upgrade 2026 | 76243.5182 | 76243.5182 | Cancelled |  |  | Less than $1M | Cancelled as engineering did further investigation and determined project was not required.
C0080748 | POA Kubota RTV Replacement | 42383.9269 | 42383.9269 | Cancelled |  |  | Less than $1M | Cancelled as other alternative technical solutions were utilized to mitigate risk and avoid replacement at this time.
C0080768 | POT - CW Pump & Motor Replacement | 2615777 | 2872183 | Deferred | 2027 |  | Subsequent Submittal | Deferred to complete additional scoping and preliminary engineering to ensure efficient and cost-effective project execution.
C0080788 | POT - Seal Oil Cooler Replacement 2026 | 606666.8353 | 606666.8353 | Deferred | 2027 |  | Less than $1M | Deferred to complete additional scoping and preliminary engineering to ensure efficient and cost-effective project execution.
C0080769 | POT - CW Pump House Power Cable Replacement | 525753.0838 | 525753.0838 | Deferred | 2027 |  | Less than $1M | Deferred as continued project planning is required in 2026 to understand the full scope of the cable replacement, in particular, avoiding the disruption of other cables in the trench.
C0080770 | POT - East CW Pump Refurbishment 2026 | 495955 | 495955 | Deferred | 2027 |  | Less than $1M | Deferred due to higher priority work utilizing available resources. The existing approach to management of this asset is expected to address near term risks.
C0080855 | TRE6 6A BFP Refurbishment (volute) | 211460 | 211460 | Deferred | 2027 |  | Less than $1M | Deferred due to higher priority work utilizing available resources. The existing approach to management of this asset is expected to address near term risks.
C0080808 | TRE - Roof Drain Replacements | 168035 | 168035 | Deferred | 2027 |  | Less than $1M | Deferred due to higher priority work utilizing available resources. The existing approach to management of this asset is expected to address near term risks.
C0080843 | TRE6 - 6A Seal Air Fan Replacement | 92093 | 92093 | Deferred | 2027 |  | Less than $1M | Deferred due to materials delays from vendor. The existing approach to management of this asset is expected to address near term risks.
C0080364 | TUC3 Boiler Safety Valves Replacement | 499799.9643 | 499799.9643 | Cancelled |  |  | Less than $1M | Cancelled as the scope of this project will now be included in CI C0060607 TUC3 Boiler Safety Valves Replacement.
C0080303 | TUC Degas North & South | 499516.9585 | 499516.9585 | Deferred | 2027 |  | Less than $1M | Deferred to better align with expected procurement and execution timelines for the project. The existing approach to management of this asset is expected to address near term risks.
C0080339 | TUC1 Feedwater MCC Replacement | 199693.2465 | 199693.2465 | Deferred | 2027 |  | Less than $1M | Deferred to better align with expected procurement and execution timelines for the project. The existing approach to management of this asset is expected to address near term risks.
C0080299 | TUC Battery Bank Monitoring | 99632.5211 | 99632.5211 | Cancelled |  |  | Less than $1M | Cancelled as the scope of this project will now be included in CI C0080593 Battery Monitoring - Steam.
C0080331 | TUC WTP4 RO Caustic Injection and Meter Replacements | 79544.525 | 79544.525 | Cancelled |  |  | Less than $1M | Cancelled as engineering did further investigation and determined project was not required.
C0080348 | TUC1 2 Wire Ni RTDs Replacements | 74370 | 74370 | Cancelled |  |  | Less than $1M | Cancelled as engineering did further investigation and determined project was not required.
C0080635 | HYD SIS Grand Lake Telemetry | 316332.7069 | 316332.7069 | Deferred | 2027 |  | Less than $1M | Deferred due to higher priority work utilizing available resources. The existing approach to management of this asset is expected to address near term risks.
Distribution
C0080605 | 19C Canso Conversion Phase 1 (Union and Water) | 444005.1605 | 459008.1005 | Deferred | 2027 |  | Less than $1M | Deferred due to unplanned carry-over and U&U capital work utilizing available resources. The existing approach to management of this asset is expected to address near term risks.
C0080251 | 84W-302 Subsea Cable Removal | 383896.6219 | 383896.6219 | Deferred | 2027 |  | Less than $1M | Deferred due to unplanned carry-over and U&U capital work utilizing available resources. The existing approach to management of this asset is expected to address near term risks.
C0080246 | 99H-311 Windmill Rd Wyse Rd Reconductor | 264408.507 | 264408.507 | Deferred | 2027 |  | Less than $1M | Deferred as continued project planning is required in 2026 to understand the full scope of the implementation.
Transmission
C0080881 | Partial Discharge Monitoring - Inspection Pilot | 205337.6575 | 205337.6575 | Deferred | 2027 |  | Less than $1M | Deferred due to higher priority work utilizing available resources. The existing approach to management of this asset is expected to address near term risks.
C0080624 | Tableau to Power BI Translation for ED | 51036.7963 | 151658.9563 | Deferred | 2027 |  | Less than $1M | Deferred to better define project scope. The existing approach to management of this asset is expected to address near term risks.
General Plant
C0080620 | IT - Responsible AI foundations | 562596 | 562596 | Deferred | 2027 |  | Less than $1M | Deferred due to higher priority work utilizing available resources.
C0068726 | IT - BlueCross Integration with PeopleSoft | 140000 | 140000 | Cancelled |  |  | Less than $1M | Cancelled as the Company is migrating to a new product, so the project is no longer required.
C0061347 | IT - Wireless Video Solution | 61819 | 61819 | Deferred | 2027 |  | Less than $1M | Deferred to better align with expected procurement and execution timelines for the project. The existing approach to management of this asset is expected to address near term risks.
C0068721 | IT - ADMS Upgrade 2026 | 3500000 | 7200000 | Deferred | 2027 |  | Subsequent Submittal | Deferred to better align with expected procurement and execution timelines for the project. The existing approach to management of this asset is expected to address near term risks.
C0082131 | IT - Customer Biling Enhancements | 517571 | 552000 | Deferred | 2027 |  | Less than $1M | Deferred to better align with expected procurement and execution timelines for the project. The existing approach to management of this asset is expected to address near term risks.
C0080618 | IT - Lifecycle: DR Hardware Refresh | 900000 | 900000 | Deferred | 2027 |  | Less than $1M | Deferred to better align with expected procurement and execution timelines for the project. The existing approach to management of this asset is expected to address near term risks.

## R4 - FIN Report
NS Power Final Cost Report
2nd Quarter Overview - as of June 30, 2026
This report includes a list of all FIN capital work orders that have fallen outside the timelines under the CEJC. (Within six months of in-service.)
These projects have either been completed and are outside the FIN tolerances or forecast to be outside of the FIN tolerances. (The greater of +/- 5% or +/- $250,000.)
Projects that have been in-service for 6 months, but have a project forecast within the allowed FIN tolerance, are not included on this list.
Project # | Project | In-service Date | NSEB Approval | Spend to June 30, 2026 | Comment
C0033644 | 2021-2022 Steel Tower Life Extension | 2021-09-30 | 2332745.87 | 1831087.15 | This project is now complete and a Final Cost Application is planned for submission in 2026.
C0010778 | Smart Grid Nova Scotia Project | 2020-05-31 | 7053622 | 6661381.46 | This project is now complete and a Final Cost Application is planned for submission in 2026.
51975 | 5P Mobile Substation replacement | 2024-12-31 | 4829458 | 2982405.69 | This project is now complete and a Final Cost Application is planned for submission in 2026.
C0026285 | TRE Heavy Fuel Oil Tank Refurbishment | 2021-12-17 | 2979545.51 | 2463573.91 | This project is now complete and a Final Cost Application is planned for submission in 2026.